## PTC-1 (Blank Template)
APPENDIX A
POST TENDER CLARIFICATION SCHEDULE - [TENDERER NAME]
|  |  | INITIAL TENDER REVIEW | PTC-1 |  |  | BAFO
Ref | COMMERCIAL COMPLIANCE |  | CONSULTANT COMMENTS / RECOMMENDATIONS | EMPLOYER'S CLARIFICATIONS | PTC-1 REVIEW MEETING DATED ___________ | TENDERER RESPONSE | EMPLOYER'S CLARIFICATIONS | TENDERER RESPONSE
A | FORM OF TENDER
1 | Form of Tender | •
2 | Time for Completion (____ days) | •
3 | Overhead & Profit (4%) | •
4 | Validity (90 days) | •
B | TERMS AND CONDITIONS
1 | Terms & Conditions | •
2 | Payment Terms | •
C | SIGNATURE AUTHORITY
1 | Power of Attorney
D | BILLS OF QUANTITIES
1 | Received in hard copy manuscript | • | No — this submission was received as a file, not in hard copy manuscript.
| Excel |  | Yes — received as BOQ T3 — GR1, 2 - Main, 3 - Ext, Bill 4.xlsx
| PDF |  | No
2 | Arithmetical Errors | • | The bid's own arithmetic does not close — a difference of 0.01. · Total as the bill prints it: 2,537,676,914.00 · Total the bidder's own quantity × rate produces: 2,537,676,914.01 · What the bid's internal arithmetic contradictions are worth: 0.01
3 | Deviations from Tender Bill |  | 6 sections do not total what the summary declares. · GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORK — declared 270,300,000.00, lines total 0.00: 270,300,000.00 · PROVISIONAL SUMS — declared 4,950,000.00, lines total 0.00: 4,950,000.00 · SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS — declared 224,680,102.00, lines total 239,912,525.00: 15,232,423.00 · SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (ADD items) — declared 15,232,423.00, lines total 239,912,525.00: 224,680,102.00 · SECTION R - ELECTRICAL INSTALLATIONS — declared 247,001,372.00, lines total 254,576,943.00: 7,575,571.00 · SECTION R - ELECTRICAL INSTALLATIONS (ADD items) — declared 7,575,571.00, lines total 254,576,943.00: 247,001,372.00
a | General Requirements | • | 2 blocks of scope sit outside the measured lines, worth 275,250,000.00. · BILL NO. 1 -GENERAL REQUIREMENTS: 270,300,000.00 · BILL NO. 4 -PROVISIONAL SUMS: 4,950,000.00
b | Excluded, unpriced items | • | Scope this bid does not price — put each to the bidder before comparing. · 586 lines print words where a figure belongs: 586 · 209 lines carry no rate, so nothing reaches the totals: 209 · Listed below; full detail on “PTC lines”, rows 2–794 (793 lines).
| GR1/1-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Generally — Where any item, clause or sub-clause of the General Requirements has not been priced, it will be deemed that the value of such item, clause or sub-clause is included in the rates for measured items elsewhere in the Bills of Quantities. |  | Candidate · Amount prints “Included” · GR1!A8
| GR1/1-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Generally — The rates and prices in these Bills of Quantities are fixed for the duration of the Contract and shall not be subject to any adjustment in respect of rise or fall in the cost of labour, materials, plant, equipment, transport or any other matters affecting the cost of execution of the Contract. |  | Candidate · Amount prints “Included” · GR1!A10
| GR1/1-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Generally — References hereunder to the Schedule of Project Requirements (SOPR) are intended solely to direct the Contractor to the specific requirements of the Schedule of Project Requirements in respect of a particular item and do not in any way limit the scope of such item to the requirements of the Schedule of Project Requirements. |  | Candidate · Amount prints “Included” · GR1!A12
| GR1/2-F — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 6 Professional Indemnity insurance |  | Candidate · Amount prints “Included” · GR1!A56
| GR1/2-H — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 8 Plant and Contractor's Equipment Insurance |  | Candidate · Amount prints “Included” · GR1!A60
| GR1/2-J — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 9 Motor Vehicle Third Party and Passenger Liability Insurance |  | Candidate · Amount prints “Included” · GR1!A62
| GR1/3-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — The Contractor shall price hereunder any special requirements related to the specification clauses |  | Candidate · Amount prints “Included” · GR1!A89
| GR1/4-D — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 4 The Maintenance of existing services on, under or over the Site |  | Candidate · Amount prints “Excluded” · GR1!A145
| GR1/4-E — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 5 The Execution of the Works in the required specific order, sections or phases |  | Candidate · Amount prints “Included” · GR1!A147
| GR1/5-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — i. Establishment |  | Candidate · Amount prints “Included in A7.1” · GR1!A193
| GR1/5-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — ii. Maintenance |  | Candidate · Amount prints “Included in A7.1” · GR1!A195
| GR1/5-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — iii. Removal |  | Candidate · Amount prints “Included in A7.1” · GR1!A197
| GR1/5-G — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — 5 Transport of workpeople |  | Candidate · Amount prints “Included in A5.1” · GR1!A205
| GR1/9-G — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 3 Screens and guardrails — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “Included in A4.1” · GR1!A405
| GR1/9-H — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 3 Screens and guardrails — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “Included in A4.1” · GR1!A407
| GR1/9-J — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 3 Screens and guardrails — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “Included in A4.1” · GR1!A409
| GR1/11-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A8 - Temporary Works — A8.1 An item shall be given for temporary works including design, which shall include: — 3 Pumping |  | Candidate · Amount prints “Included in Site Works (Bill Nr 2)” · GR1!A488
| GR1/12-E — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 5 - Traffic regulations |  | Candidate · Amount prints “Included in A8.1” · GR1!A543
| GR1/12-G — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 7 - Drying the Works |  | Candidate · Amount prints “Included in A7.1” · GR1!A547
| GR1/12-H — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 8 - Control of noise and pollution |  | Candidate · Amount prints “Included in A7.1” · GR1!A549
| GR1/12-J — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 9 - All Statutory obligations |  | Candidate · Amount prints “Included in A7.1” · GR1!A551
| GR1/12-N — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 4 - Off site storage |  | Candidate · Amount prints “Included in A7.1” · GR1!A561
| GR1/13-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 6 - Specialist Third Party Testing, Commissioning and Certification |  | Candidate · Amount prints “Included in A9.1” · GR1!A577
| GR1/13-H — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 12 - Internet connection requirements on site |  | Candidate · Amount prints “Included in A7.1” · GR1!A591
| GR1/13-J — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 13 - Precautions against Fire |  | Candidate · Amount prints “Included in A4.1” · GR1!A593
| GR1/13-K — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 15 - Project Health, Safety, Environment and Security Guidelines |  | Candidate · Amount prints “Included in A4.1” · GR1!A595
| GR1/13-L — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 16 - General cleaning and waste disposal during construction |  | Candidate · Amount prints “Included in A9.1” · GR1!A597
| GR1/13-P — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 19 - Contract Spares/Attic stock |  | Candidate · Amount prints “Excluded” · GR1!A603
| GR1/13-Q — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 20 - As-built drawings |  | Candidate · Amount prints “Included in BIM” · GR1!A605
| GR1/13-S — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 22 - Warranties |  | Candidate · Amount prints “Included” · GR1!A609
| GR1/15-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Additional Items — Any items that may not be covered elsewhere in the Bills of Quantities which the Tenderer deemed to be necessary in order to carry out the works in full compliance with the SOPR must be itemised and price below |  | Candidate · Amount prints “0” · GR1!A674
| 2/B/3 Item A — Bill 2 — SECTION B - SITE WORKS (2/B) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Site Work in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A102
| 2/C/2 Item J — Bill 2 — SECTION C - CONCRETE WORKS (2/C) — POURED CONCRETE — Reinforced concrete; concrete grade C50/60 — Columns |  | Candidate · Amount prints “0” · 2 - Main!A276
| 2/C/3 Item M — Bill 2 — SECTION C - CONCRETE WORKS (2/C) — POURED CONCRETE — Reinforced concrete; concrete grade C70/85 — Blade wall; 400mm thick |  | Candidate · Amount prints “0” · 2 - Main!A343
| 2/C/6 Item B — Bill 2 — SECTION C - CONCRETE WORKS (2/C) — REINFORCEMENT — Reinforcing steel bars; high yield deformed; grade 60 — Planter wall |  | Candidate · Amount prints “0” · 2 - Main!A486
| 2/C/9 Item D — Bill 2 — SECTION C - CONCRETE WORKS (2/C) — PRESTRESSED CONCRETE — Post tensioning (PT) system; comprise of design, approvals including prestressing steel, anchorages, plates, ducts, grouts, protection, accessories and all ancillary works as necessary — PT system; to post tensioned slab |  | Candidate · Amount prints “Please refer ADD items” · 2 - Main!A664
| 2/C/11 Item A — Bill 2 — SECTION C - CONCRETE WORKS (2/C) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Concrete Work in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A748
| 2/D/2 Item A — Bill 2 — SECTION D - MASONRY (2/D) — SUNDRIES — Joints in masonry; including fire resistant compressible joint filler, sealant, angle head restraints, telescopic, sleeved and/or debonded ties and the like — Dowelled control joints |  | Candidate · Amount prints “Included” · 2 - Main!A1049
| 2/D/2 Item B — Bill 2 — SECTION D - MASONRY (2/D) — SUNDRIES — Joints in masonry; including fire resistant compressible joint filler, sealant, angle head restraints, telescopic, sleeved and/or debonded ties and the like — Dowelled control joints (RATE ONLY) |  | Candidate · Amount prints “Rate Only” · 2 - Main!A1051
| 2/D/2 Item C — Bill 2 — SECTION D - MASONRY (2/D) — SUNDRIES — Joints in masonry; including fire resistant compressible joint filler, sealant, angle head restraints, telescopic, sleeved and/or debonded ties and the like — Isolation joints |  | Candidate · Amount prints “Included” · 2 - Main!A1053
| 2/D/2 Item D — Bill 2 — SECTION D - MASONRY (2/D) — SUNDRIES — Joints in masonry; including fire resistant compressible joint filler, sealant, angle head restraints, telescopic, sleeved and/or debonded ties and the like — Isolation joints (RATE ONLY) |  | Candidate · Amount prints “Rate Only” · 2 - Main!A1055
| 2/D/3 Item A — Bill 2 — SECTION D - MASONRY (2/D) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Masonry in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A1101
| 2/E/9 Item C — Bill 2 — SECTION E - METALWORK (2/E) — NON-STRUCTURAL METALWORK — Stainless steel ladders to water tanks; type AM-451; wall mounted stainless steel with safety cage; including finishes, frames, supports, fixings, accessories and all ancillary works as necessary — Type 2; size 960 x 690 x 10300mm high |  | Candidate · Amount prints “0” · 2 - Main!A1610
| 2/E/11 Item A — Bill 2 — SECTION E - METALWORK (2/E) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Metalwork in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A1688
| 2/F/24 Item A — Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Woodwork in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A3001
| 2/F/24 Item ADD — Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Kitchen cabinets; to show kitchen; including countertop, forming of holes, frames, carcass, supports, front/back/side panels, doors, shelves, drawers, concealed light (measured separately), skirting, hardware, finishes, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 2 - Main!A3005
| 2/F/24 Item ADD — Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Vanity counters; including countertop, forming of holes, front/side panels, drawers, hardware, finishes, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 2 - Main!A3009
| 2/F/24 Item ADD — Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — To powder room |  | Candidate · Amount prints “0” · 2 - Main!A3011
| 2/F/24 Item ADD — Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Veneered shelves; including finishes, fixings, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 2 - Main!A3014
| 2/F/24 Item ADD — Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — To powder room |  | Candidate · Amount prints “0” · 2 - Main!A3016
| 2/F/24 Item ADD — Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Cabinets with veneered open shelf; including concealed light (measured separately), front/side panels, hardware, finishes, fixings, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 2 - Main!A3019
| 2/F/24 Item ADD — Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — To powder room |  | Candidate · Amount prints “0” · 2 - Main!A3021
| 2/F/24 Item ADD — Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Wardrobes; comprising 18mm thick MDF shelving and glass shutter; including MDF backing, carcass, frames, supports, front/side/back panels, doors, shelves, drawers, concealed light (measured separately), hardware, finishes, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 2 - Main!A3025
| 2/G/4 Item A — Bill 2 — SECTION G - THERMAL AND MOISTURE PROTECTION (2/G) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Thermal and Moisture Protection in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A3438
| 2/H/16 Item A — Bill 2 — SECTION H - DOORS AND WINDOWS (2/H) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Doors and Windows in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A4262
| 2/H/16 Item ADD — Bill 2 — SECTION H - DOORS AND WINDOWS (2/H) — GENERALLY — Double glazed vision panel screen; Type V1; light smokey grey; Buildup: IGU; Outer lite: 8mm FT, Low E coating on surface #2 + 16mm AS + Inner lite: 6mm FT; U-value = 1.7W/m²K; Shading coefficient 0.25 max.; including frames, sub-frame, door system, finishes, joint, gasket, toggle clip, sealant, insulation, plaster board, fixings, fittings, accessories and all ancillary works as per drawings and specifications |  | Candidate · Amount prints “0” · 2 - Main!A4266
| 2/H/16 Item ADD — Bill 2 — SECTION H - DOORS AND WINDOWS (2/H) — GENERALLY — Double glazed vision panel screen; Type V2; light smokey grey; Buildup: IGU; Outer lite: 8mm FT, Low E coating on surface #2 + 16mm AS + Inner lite: 8mm FT; U-value = 1.7W/m²K; Shading coefficient 0.25 max.; including frames, sub-frame, door system, finishes, joint, gasket, toggle clip, sealant, insulation, plaster board, fixings, fittings, accessories and all ancillary works as per drawings and specifications |  | Candidate · Amount prints “0” · 2 - Main!A4273
| 2/H/16 Item ADD — Bill 2 — SECTION H - DOORS AND WINDOWS (2/H) — GENERALLY — Double glazed spandrel panel screen; Type S1; light smokey grey; Buildup: IGU; Outer lite: 8mm FT, Low E coating on surface #2 + 16mm AS + Inner lite: 6mm FT; including frames, sub-frame, door system, finishes, joint, gasket, toggle clip, sealant, plaster board, insulation, fixings, fittings, accessories and all ancillary works as per drawings and specifications |  | Candidate · Amount prints “0” · 2 - Main!A4279
| 2/J/9 Item B — Bill 2 — SECTION J - FINISHES (2/J) — CEILING FINISHES — Gypsum board tile ceiling system; including finishes, suspended metal support framing system, brackets, fastenings, accessories and all necessary fixings and accessories — Extra over for access panel |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A4854
| 2/J/9 Item D — Bill 2 — SECTION J - FINISHES (2/J) — CEILING FINISHES — Concealed grid aluminium tile ceiling system; demountable, perforated aluminium tiles; including finishes, suspended metal support framing system, brackets, fastenings, accessories and all necessary fixings and accessories — Extra over for access panel |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A4860
| 2/J/17 Item A — Bill 2 — SECTION J - FINISHES (2/J) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Finishes in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A5218
| 2/K/1 Item J — Bill 2 — SECTION K - ACCESSORIES (2/K) — TOILET ACCESSORIES — Sanitary accessories — Sanitary accessories; fixed to tiled or plastered concrete or blockwork; including connections, supports, sealants, accessories and all ancillary works as necessary — Common Areas — Type SAN-711; toilet paper holder |  | Candidate · Amount prints “0” · 2 - Main!A5625
| 2/K/5 Item J — Bill 2 — SECTION K - ACCESSORIES (2/K) — SIGNAGE AND WAYFINDING — Signage and wayfinding; in English and Arabic text; including finishes, fixings, accessories and all ancillary works as necessary — Internal Signage — Retail sign by others |  | Candidate · Amount prints “By Others” · 2 - Main!A5834
| 2/K/6 Item B — Bill 2 — SECTION K - ACCESSORIES (2/K) — PARKING ACCESSORIES — Kerbs; precast concrete fixed to floor slab; including fixings, finishes, accessories and all ancillary works as necessary — Type EXH-301; 100mm high |  | Candidate · Amount prints “0” · 2 - Main!A5880
| 2/K/6 Item C — Bill 2 — SECTION K - ACCESSORIES (2/K) — PARKING ACCESSORIES — Kerbs; precast concrete fixed to floor slab; including fixings, finishes, accessories and all ancillary works as necessary — 150mm high; to ramps |  | Candidate · Amount prints “0” · 2 - Main!A5882
| 2/K/13 Item A — Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Accessories in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A6224
| 2/K/13 Item ADD — Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Tempered mirror; type GL-101; 6mm thick clear mirror with metal frame; including, backing, supports, finishes, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 2 - Main!A6231
| 2/K/13 Item ADD — Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Shower glass partition; fixed glass with doors; glass; 10mm thick; including ironmongery, fixings, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 2 - Main!A6239
| 2/K/13 Item ADD — Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Clear Glass |  | Candidate · Amount prints “0” · 2 - Main!A6240
| 2/K/13 Item ADD — Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Fluted Tinted Glass |  | Candidate · Amount prints “0” · 2 - Main!A6243
| 2/L/1 Item J — Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-111; freestanding cooker |  | Candidate · Amount prints “0” · 2 - Main!A6479
| 2/L/1 Item K — Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-112; freestanding fridge |  | Candidate · Amount prints “0” · 2 - Main!A6481
| 2/L/1 Item L — Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-113; freestanding freezer |  | Candidate · Amount prints “0” · 2 - Main!A6483
| 2/L/1 Item M — Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-114; freestanding dishwasher |  | Candidate · Amount prints “0” · 2 - Main!A6485
| 2/L/1 Item P — Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-116; coffee machine |  | Candidate · Amount prints “0” · 2 - Main!A6489
| 2/L/1 Item Q — Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-117; tv screen |  | Candidate · Amount prints “0” · 2 - Main!A6491
| 2/L/1 Item R — Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-118; tv screen |  | Candidate · Amount prints “0” · 2 - Main!A6493
| 2/L/1 Item S — Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-119; water dispenser |  | Candidate · Amount prints “0” · 2 - Main!A6495
| 2/L/1 Item T — Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-120; tv screen |  | Candidate · Amount prints “0” · 2 - Main!A6497
| 2/L/2 Item A — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-101; run 19" excite live |  | Candidate · Amount prints “0” · 2 - Main!A6517
| 2/L/2 Item B — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-102; climb 16" excite live |  | Candidate · Amount prints “0” · 2 - Main!A6519
| 2/L/2 Item C — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-103; synchro ar 16" excite live |  | Candidate · Amount prints “0” · 2 - Main!A6521
| 2/L/2 Item D — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-104; technogym bike |  | Candidate · Amount prints “0” · 2 - Main!A6523
| 2/L/2 Item E — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-105; skillrow |  | Candidate · Amount prints “0” · 2 - Main!A6525
| 2/L/2 Item F — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-106; lower back fitness bench |  | Candidate · Amount prints “0” · 2 - Main!A6527
| 2/L/2 Item G — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-107; yoga mat |  | Candidate · Amount prints “0” · 2 - Main!A6529
| 2/L/2 Item H — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-108; crunch bench press |  | Candidate · Amount prints “0” · 2 - Main!A6531
| 2/L/2 Item J — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-109; multi-power |  | Candidate · Amount prints “0” · 2 - Main!A6533
| 2/L/2 Item K — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-110; adjustable bench |  | Candidate · Amount prints “0” · 2 - Main!A6535
| 2/L/2 Item L — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-111; two tier dumbbell rack |  | Candidate · Amount prints “0” · 2 - Main!A6537
| 2/L/2 Item M — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-112; dumbbells (10 pairs) |  | Candidate · Amount prints “0” · 2 - Main!A6539
| 2/L/2 Item N — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-113; dual leg curl/leg extension selection 700 |  | Candidate · Amount prints “0” · 2 - Main!A6541
| 2/L/2 Item P — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-114; lat machine selection 700 |  | Candidate · Amount prints “0” · 2 - Main!A6543
| 2/L/2 Item Q — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-115; shoulder press-selection 700 |  | Candidate · Amount prints “0” · 2 - Main!A6545
| 2/L/2 Item R — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-116; chest press-selection 700 |  | Candidate · Amount prints “0” · 2 - Main!A6547
| 2/L/2 Item S — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-117; skill tools storage |  | Candidate · Amount prints “0” · 2 - Main!A6549
| 2/L/2 Item T — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-118; universe wall 2 virtual |  | Candidate · Amount prints “0” · 2 - Main!A6551
| 2/L/2 Item U — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-119; vario 16" excite live |  | Candidate · Amount prints “0” · 2 - Main!A6553
| 2/L/2 Item V — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-120; skill up |  | Candidate · Amount prints “0” · 2 - Main!A6555
| 2/L/2 Item W — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-121; skillmill |  | Candidate · Amount prints “0” · 2 - Main!A6557
| 2/L/2 Item X — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-122; skillrun unity 7000 |  | Candidate · Amount prints “0” · 2 - Main!A6559
| 2/L/2 Item Y — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-123; plyobox |  | Candidate · Amount prints “0” · 2 - Main!A6561
| 2/L/2 Item Z — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-124; punching bag |  | Candidate · Amount prints “0” · 2 - Main!A6563
| 2/L/2 Item AA — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-125; leg press selection 700 |  | Candidate · Amount prints “0” · 2 - Main!A6565
| 2/L/3 Item C — Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — BMU accessories; including fixing materials, signage, supports, brackets, accessories and all ancillary works as necessary — Galvanized mild steel running track; including galvanized steel base plates, clip ears, stainless steel A4/80 u-bolts, high-strength grout, fixings; complete — BMU tracks at 4000mm center to center |  | Candidate · Amount prints “Included” · 2 - Main!A6593
| 2/L/5 Item C — Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — To tower 1 |  | Candidate · Amount prints “0” · 2 - Main!A6664
| 2/L/5 Item D — Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — To tower 2 |  | Candidate · Amount prints “0” · 2 - Main!A6666
| 2/L/5 Item E — Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — To tower 3 |  | Candidate · Amount prints “0” · 2 - Main!A6668
| 2/L/5 Item F — Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — To tower 4 |  | Candidate · Amount prints “0” · 2 - Main!A6670
| 2/L/5 Item G — Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — Allow to mobile elevated work platform (MEWP) including accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 2 - Main!A6672
| 2/L/6 Item A — Bill 2 — SECTION L - EQUIPMENT (2/L) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Equipment in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A6688
| 2/M/1 Item A — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-101; coffee table |  | Candidate · Amount prints “0” · 2 - Main!A6806
| 2/M/1 Item B — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-102; side table |  | Candidate · Amount prints “0” · 2 - Main!A6808
| 2/M/1 Item C — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-103; side table |  | Candidate · Amount prints “0” · 2 - Main!A6810
| 2/M/1 Item D — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-104; console behind sofa |  | Candidate · Amount prints “0” · 2 - Main!A6812
| 2/M/1 Item E — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-105; console |  | Candidate · Amount prints “0” · 2 - Main!A6814
| 2/M/1 Item F — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-106; side table |  | Candidate · Amount prints “0” · 2 - Main!A6816
| 2/M/1 Item G — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-107; table |  | Candidate · Amount prints “0” · 2 - Main!A6818
| 2/M/1 Item H — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-108; console |  | Candidate · Amount prints “0” · 2 - Main!A6820
| 2/M/1 Item J — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-109; coffee table |  | Candidate · Amount prints “0” · 2 - Main!A6822
| 2/M/1 Item K — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-110; side table vintage bronze |  | Candidate · Amount prints “0” · 2 - Main!A6824
| 2/M/1 Item L — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-111; side table |  | Candidate · Amount prints “0” · 2 - Main!A6826
| 2/M/1 Item M — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-112; side table |  | Candidate · Amount prints “0” · 2 - Main!A6828
| 2/M/1 Item N — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-113; communal table travertine |  | Candidate · Amount prints “0” · 2 - Main!A6830
| 2/M/1 Item P — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-114; coffee table |  | Candidate · Amount prints “0” · 2 - Main!A6832
| 2/M/1 Item Q — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-115; coffee table |  | Candidate · Amount prints “0” · 2 - Main!A6834
| 2/M/1 Item R — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-116; armchairs side table |  | Candidate · Amount prints “0” · 2 - Main!A6836
| 2/M/1 Item S — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-117; sofa side table |  | Candidate · Amount prints “0” · 2 - Main!A6838
| 2/M/1 Item T — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-118; coffee table |  | Candidate · Amount prints “0” · 2 - Main!A6840
| 2/M/1 Item U — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-119; coffee table |  | Candidate · Amount prints “0” · 2 - Main!A6842
| 2/M/1 Item V — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-120; dining table |  | Candidate · Amount prints “0” · 2 - Main!A6844
| 2/M/1 Item W — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-121; console |  | Candidate · Amount prints “0” · 2 - Main!A6846
| 2/M/1 Item X — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-122; gaming area side table |  | Candidate · Amount prints “0” · 2 - Main!A6848
| 2/M/2 Item A — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-123; kids table |  | Candidate · Amount prints “0” · 2 - Main!A6858
| 2/M/2 Item B — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-124; pool table |  | Candidate · Amount prints “0” · 2 - Main!A6860
| 2/M/2 Item C — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-125; foosball table |  | Candidate · Amount prints “0” · 2 - Main!A6862
| 2/M/2 Item D — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-126; shower bench |  | Candidate · Amount prints “0” · 2 - Main!A6864
| 2/M/2 Item E — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-101; seating area loose rug |  | Candidate · Amount prints “0” · 2 - Main!A6868
| 2/M/2 Item F — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-102; big table loose rug |  | Candidate · Amount prints “0” · 2 - Main!A6870
| 2/M/2 Item G — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-103; rectangular loose rug |  | Candidate · Amount prints “0” · 2 - Main!A6872
| 2/M/2 Item H — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-104; rectangular loose rug |  | Candidate · Amount prints “0” · 2 - Main!A6874
| 2/M/2 Item J — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-105; loose rug |  | Candidate · Amount prints “0” · 2 - Main!A6876
| 2/M/2 Item K — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-106; loose rug |  | Candidate · Amount prints “0” · 2 - Main!A6878
| 2/M/2 Item L — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-107; loose rug |  | Candidate · Amount prints “0” · 2 - Main!A6880
| 2/M/2 Item M — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-101; sheer curtains |  | Candidate · Amount prints “0” · 2 - Main!A6884
| 2/M/2 Item N — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-102; plant pots |  | Candidate · Amount prints “0” · 2 - Main!A6886
| 2/M/2 Item P — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-103; lift lobby entrance |  | Candidate · Amount prints “0” · 2 - Main!A6888
| 2/M/2 Item Q — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-104; artwork behind sofa |  | Candidate · Amount prints “0” · 2 - Main!A6890
| 2/M/2 Item R — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-105; artwork above console- hand painted art painting |  | Candidate · Amount prints “0” · 2 - Main!A6892
| 2/M/2 Item S — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-106; artwork at table area |  | Candidate · Amount prints “0” · 2 - Main!A6894
| 2/M/2 Item T — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-107; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6896
| 2/M/2 Item U — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-108; entrance lobby corridor artwork |  | Candidate · Amount prints “0” · 2 - Main!A6898
| 2/M/2 Item V — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-109; roller blinds |  | Candidate · Amount prints “0” · 2 - Main!A6900
| 2/M/2 Item W — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-110; accessories |  | Candidate · Amount prints “0” · 2 - Main!A6902
| 2/M/3 Item A — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-111; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6912
| 2/M/3 Item B — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-112; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6914
| 2/M/3 Item C — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-113; curtains manual |  | Candidate · Amount prints “0” · 2 - Main!A6916
| 2/M/3 Item D — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-114; plant pots |  | Candidate · Amount prints “0” · 2 - Main!A6918
| 2/M/3 Item E — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-115; sheer curtains-seating area and table area only (deleted) |  | Candidate · Amount prints “0” · 2 - Main!A6920
| 2/M/3 Item F — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-116; plant pots |  | Candidate · Amount prints “0” · 2 - Main!A6922
| 2/M/3 Item G — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-117; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6924
| 2/M/3 Item H — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-118; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6926
| 2/M/3 Item J — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-119; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6928
| 2/M/3 Item K — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-120; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6930
| 2/M/3 Item L — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-121; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6932
| 2/M/3 Item M — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-122; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6934
| 2/M/3 Item N — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-123; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6936
| 2/M/3 Item P — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-124; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6938
| 2/M/3 Item Q — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-125; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6940
| 2/M/3 Item R — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-126; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6942
| 2/M/3 Item S — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-127; printed artwork |  | Candidate · Amount prints “0” · 2 - Main!A6944
| 2/M/3 Item T — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-128; printed artwork |  | Candidate · Amount prints “0” · 2 - Main!A6946
| 2/M/3 Item U — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-129; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6948
| 2/M/3 Item V — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-130; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6950
| 2/M/3 Item W — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-131; printed artwork |  | Candidate · Amount prints “0” · 2 - Main!A6952
| 2/M/3 Item X — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-132; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6954
| 2/M/3 Item Y — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-133; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6956
| 2/M/3 Item Z — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-134; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6958
| 2/M/4 Item A — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-135; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6968
| 2/M/4 Item B — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-136; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6970
| 2/M/4 Item C — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-137; mirror |  | Candidate · Amount prints “0” · 2 - Main!A6972
| 2/M/4 Item D — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-138; artwork |  | Candidate · Amount prints “0” · 2 - Main!A6974
| 2/M/4 Item E — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-101; sofa |  | Candidate · Amount prints “0” · 2 - Main!A6978
| 2/M/4 Item F — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-102; armchair |  | Candidate · Amount prints “0” · 2 - Main!A6980
| 2/M/4 Item G — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-103; bench |  | Candidate · Amount prints “0” · 2 - Main!A6982
| 2/M/4 Item H — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-104; armchair |  | Candidate · Amount prints “0” · 2 - Main!A6984
| 2/M/4 Item J — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-105; dining chair |  | Candidate · Amount prints “0” · 2 - Main!A6986
| 2/M/4 Item K — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-106; sofa |  | Candidate · Amount prints “0” · 2 - Main!A6988
| 2/M/4 Item L — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-107; lounge chair |  | Candidate · Amount prints “0” · 2 - Main!A6990
| 2/M/4 Item M — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-108; pouf-leather |  | Candidate · Amount prints “0” · 2 - Main!A6992
| 2/M/4 Item N — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-109; armchair-leather |  | Candidate · Amount prints “0” · 2 - Main!A6994
| 2/M/4 Item P — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-110; dining chair |  | Candidate · Amount prints “0” · 2 - Main!A6996
| 2/M/4 Item Q — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-111; bench seat |  | Candidate · Amount prints “0” · 2 - Main!A6998
| 2/M/4 Item R — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-112; ottoman |  | Candidate · Amount prints “0” · 2 - Main!A7000
| 2/M/4 Item S — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-113; armchair & pouf |  | Candidate · Amount prints “0” · 2 - Main!A7002
| 2/M/4 Item T — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-114; sofa |  | Candidate · Amount prints “0” · 2 - Main!A7004
| 2/M/4 Item U — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-115; armchair |  | Candidate · Amount prints “0” · 2 - Main!A7006
| 2/M/4 Item V — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-116; ottoman |  | Candidate · Amount prints “0” · 2 - Main!A7008
| 2/M/5 Item A — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-117; armchair |  | Candidate · Amount prints “0” · 2 - Main!A7023
| 2/M/5 Item B — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-118; sofa in joinery |  | Candidate · Amount prints “0” · 2 - Main!A7025
| 2/M/5 Item C — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-119; sofa in small seating |  | Candidate · Amount prints “0” · 2 - Main!A7027
| 2/M/5 Item D — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-120; kids chair 1 |  | Candidate · Amount prints “0” · 2 - Main!A7029
| 2/M/5 Item E — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-121; reception chair |  | Candidate · Amount prints “0” · 2 - Main!A7031
| 2/M/5 Item F — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-122; built in bench |  | Candidate · Amount prints “0” · 2 - Main!A7033
| 2/M/5 Item H — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Chairs; to guard rooms |  | Candidate · Amount prints “0” · 2 - Main!A7041
| 2/M/5 Item J — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Chairs; to meeting room |  | Candidate · Amount prints “0” · 2 - Main!A7043
| 2/M/5 Item K — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Chairs; to security manager room |  | Candidate · Amount prints “0” · 2 - Main!A7045
| 2/M/5 Item L — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Chairs; to staff pantry |  | Candidate · Amount prints “0” · 2 - Main!A7047
| 2/M/5 Item M — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Table; size 900 x 900mm wide; to staff pantry |  | Candidate · Amount prints “0” · 2 - Main!A7049
| 2/M/5 Item N — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Table; size 1500 x 600mm wide; to security manager room |  | Candidate · Amount prints “0” · 2 - Main!A7051
| 2/M/5 Item P — Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Table; size 3600 x 1500mm wide; to meeting room |  | Candidate · Amount prints “0” · 2 - Main!A7053
| 2/M/6 Item A — Bill 2 — SECTION M - FURNISHING (2/M) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Furnishings in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A7075
| 2/P/5 Item A — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — SUNDRIES — Allow for providing shop drawings, as built drawings and material submittal approvals |  | Candidate · Amount prints “Included” · 2 - Main!A7390
| 2/P/5 Item B — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — SUNDRIES — Allow for providing catalogues, operation and maintenance manuals |  | Candidate · Amount prints “Included” · 2 - Main!A7392
| 2/P/5 Item C — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — SUNDRIES — Allow for labeling, tagging of equipment with their related control panel and components as specified |  | Candidate · Amount prints “Included” · 2 - Main!A7394
| 2/P/5 Item D — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — SUNDRIES — Allow for testing and commissioning the complete installation |  | Candidate · Amount prints “Included” · 2 - Main!A7396
| 2/P/6 Item A — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow for cutting or forming all holes, mortices, chases and the like and making good finishes for conveying systems |  | Candidate · Amount prints “Included” · 2 - Main!A7429
| 2/P/6 Item B — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow for fixing all sleeves, frames and built-in firestop system and making good finishes for conveying systems |  | Candidate · Amount prints “Included” · 2 - Main!A7431
| 2/P/6 Item C — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow for firestopping for all holes and making good finishes for conveying systems |  | Candidate · Amount prints “Included” · 2 - Main!A7433
| 2/P/6 Item D — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow for building in or cutting and pinning brackets or the like and making good finishes for conveying systems |  | Candidate · Amount prints “Included” · 2 - Main!A7435
| 2/P/6 Item E — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow connection to elevator monitoring system (EMS) at BMS room |  | Candidate · Amount prints “Included” · 2 - Main!A7437
| 2/P/6 Item F — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — BWIC — Builders work in connection with conveying systems |  | Candidate · Amount prints “Included” · 2 - Main!A7441
| 2/P/7 Item A — Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Conveying Systems in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A7485
| 2/Q/4 Item H — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere |  | Candidate · Amount prints “Included” · 2 - Main!A7777
| 2/Q/4 Item J — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for all identification including painting, marking and labelling |  | Candidate · Amount prints “Included” · 2 - Main!A7779
| 2/Q/4 Item L — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installation |  | Candidate · Amount prints “Included” · 2 - Main!A7783
| 2/Q/4 Item M — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for providing spares for the Mechanical Engineering Installation |  | Candidate · Amount prints “0” · 2 - Main!A7785
| 2/Q/5 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like |  | Candidate · Amount prints “Included” · 2 - Main!A7808
| 2/Q/5 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades |  | Candidate · Amount prints “Included” · 2 - Main!A7812
| 2/Q/5 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for liaison with obtaining approvals and attendance on approved Authorities, other statutory bodies and service providers as required |  | Candidate · Amount prints “Included” · 2 - Main!A7814
| 2/Q/5 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good |  | Candidate · Amount prints “Included” · 2 - Main!A7816
| 2/Q/5 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good |  | Candidate · Amount prints “Included” · 2 - Main!A7818
| 2/Q/5 Item F — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Mechanical Engineering Installations |  | Candidate · Amount prints “Included” · 2 - Main!A7820
| 2/Q/5 Item G — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work to the Mechanical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “Included” · 2 - Main!A7822
| 2/Q/8 Item M — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — U-trap; size 110mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A7972
| 2/Q/8 Item N — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — U-trap; size 160mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A7974
| 2/Q/8 Item P — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 110mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A7976
| 2/Q/8 Item Q — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 160mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A7978
| 2/Q/8 Item R — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 200mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A7980
| 2/Q/9 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 250mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A7995
| 2/Q/9 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 350mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A7997
| 2/Q/10 Item P — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 32mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8070
| 2/Q/10 Item Q — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 50mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8072
| 2/Q/10 Item R — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 82mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8074
| 2/Q/10 Item S — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 110mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8076
| 2/Q/11 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 160mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8091
| 2/Q/12 Item S — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — U-trap; size 110mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8178
| 2/Q/13 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — U-trap; size 160mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8193
| 2/Q/13 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 32mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8195
| 2/Q/13 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 50mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8197
| 2/Q/13 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 82mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8199
| 2/Q/13 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 110mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8201
| 2/Q/13 Item F — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 160mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8203
| 2/Q/13 Item G — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 200mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8205
| 2/Q/13 Item H — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 250mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8207
| 2/Q/13 Item J — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 300mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8209
| 2/Q/13 Item K — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 350mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8211
| 2/Q/13 Item L — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 450mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A8213
| 2/Q/28 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To ground and podium |  | Candidate · Amount prints “Included” · 2 - Main!A8852
| 2/Q/28 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To tower 1 |  | Candidate · Amount prints “Included” · 2 - Main!A8854
| 2/Q/28 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To tower 2 |  | Candidate · Amount prints “Included” · 2 - Main!A8856
| 2/Q/28 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To tower 3 |  | Candidate · Amount prints “Included” · 2 - Main!A8858
| 2/Q/28 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To tower 4 |  | Candidate · Amount prints “Included” · 2 - Main!A8860
| 2/Q/31 Item Q — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Accessories; including hangers, supports, fixings and all ancillary works as necessary — Deluge valve; 50mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A9017
| 2/Q/31 Item R — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Accessories; including hangers, supports, fixings and all ancillary works as necessary — Foam tank |  | Candidate · Amount prints “Included” · 2 - Main!A9019
| 2/Q/34 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-BF-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 1000gpm and duty pump head of 11bar |  | Candidate · Amount prints “Included” · 2 - Main!A9123
| 2/Q/34 Item F — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-P2-FF-DP-02, Diesel engine driven fire pump; with estimated flow rate of 1000gpm and duty pump head of 18.6bar |  | Candidate · Amount prints “Included” · 2 - Main!A9125
| 2/Q/34 Item G — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T1-29F-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 16.2bar |  | Candidate · Amount prints “Included” · 2 - Main!A9127
| 2/Q/34 Item H — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 14.3bar |  | Candidate · Amount prints “Included” · 2 - Main!A9129
| 2/Q/34 Item J — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-48F-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 13.6bar |  | Candidate · Amount prints “Included” · 2 - Main!A9131
| 2/Q/34 Item K — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-DP-01,Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 17.8bar |  | Candidate · Amount prints “Included” · 2 - Main!A9133
| 2/Q/35 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 17.8bar |  | Candidate · Amount prints “Included” · 2 - Main!A9147
| 2/Q/35 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-BF-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 11bar |  | Candidate · Amount prints “Included” · 2 - Main!A9149
| 2/Q/35 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-P2-FF-JP-02, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 18.6bar |  | Candidate · Amount prints “Included” · 2 - Main!A9151
| 2/Q/35 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 16.2bar |  | Candidate · Amount prints “Included” · 2 - Main!A9153
| 2/Q/35 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 14.3bar |  | Candidate · Amount prints “Included” · 2 - Main!A9155
| 2/Q/35 Item F — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-48F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 13.6bar |  | Candidate · Amount prints “Included” · 2 - Main!A9157
| 2/Q/35 Item G — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-29F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 17.6bar |  | Candidate · Amount prints “Included” · 2 - Main!A9159
| 2/Q/35 Item H — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T4-29F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 17.8bar |  | Candidate · Amount prints “Included” · 2 - Main!A9161
| 2/Q/35 Item J — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting diesel tank; including supports, concrete base and all ancillary works as necessary — Diesel tank; 350US gallon |  | Candidate · Amount prints “Included” · 2 - Main!A9165
| 2/Q/37 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Clean agent extinguishing system including hangers, supports, fixings, clean agent pipes, fittings, accessories and all ancillary works as necessary — Tower 1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A9229
| 2/Q/37 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Clean agent extinguishing system including hangers, supports, fixings, clean agent pipes, fittings, accessories and all ancillary works as necessary — Tower 2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A9231
| 2/Q/37 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Clean agent extinguishing system including hangers, supports, fixings, clean agent pipes, fittings, accessories and all ancillary works as necessary — Tower 3 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A9233
| 2/Q/37 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Clean agent extinguishing system including hangers, supports, fixings, clean agent pipes, fittings, accessories and all ancillary works as necessary — Tower 4 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A9235
| 2/Q/41 Item R — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — HVAC INSTALLATION — Valve package assembly; including gate valves, binder test port, strainer, 2 port modulating PICV valve, union, reducers, MAV, bypass pipe with valve, fixings; complete — 20mm diameter |  | Candidate · Amount prints “Duplicated item, Refer FCU Connection Assembly” · 2 - Main!A9431
| 2/Q/41 Item S — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — HVAC INSTALLATION — Valve package assembly; including gate valves, binder test port, strainer, 2 port modulating PICV valve, union, reducers, MAV, bypass pipe with valve, fixings; complete — 25mm diameter |  | Candidate · Amount prints “Duplicated item, Refer FCU Connection Assembly” · 2 - Main!A9433
| 2/Q/43 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — HVAC INSTALLATION — Plant and equipment including hangers, supports, fixings, pipe connections, wire connections, flexible connections and all ancillary works as necessary — Heat exchanger unit complete with valves, dosing pumpset, sensor, controllers and all ancillary works as necessary — T2-GF-PHEX 01 to 06; plate heat exchanger (6 duty); with cold side flow of 77.6l/s and hot side flow of 77.6l/s, design pressure of 20bar and maximum fluid pressure drop of 40kPa |  | Candidate · Amount prints “N/A, Since MEP scope start from Secondary side of Heat exchanger as per TA-05, Item no. 5.22” · 2 - Main!A9509
| 2/Q/173 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Soft copper pipe tubes to BS EN 1057 tableX; including fittings, perforated covers, hangers, supports, fixings, sleeves, accessories and all ancillary works as necessary — 15mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15048
| 2/Q/174 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 20mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15072
| 2/Q/174 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 25mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15074
| 2/Q/174 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 32mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15076
| 2/Q/174 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 40mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15078
| 2/Q/174 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 50mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15080
| 2/Q/174 Item F — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, containment pipe, pipe in pipe gas detectors, socket, sensors, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 50mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15084
| 2/Q/174 Item G — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, containment pipe, pipe in pipe gas detectors, socket, sensors, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 80mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15086
| 2/Q/174 Item H — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, containment pipe, pipe in pipe gas detectors, socket, sensors, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 100mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15088
| 2/Q/174 Item J — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Fire rated duct to LPG pipe — To LPG pipe in various sizes; 2hr. fire rating |  | Candidate · Amount prints “Included” · 2 - Main!A15092
| 2/Q/174 Item K — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 32mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15096
| 2/Q/175 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 40mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15114
| 2/Q/175 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 50mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15116
| 2/Q/175 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 65mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15118
| 2/Q/175 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 80mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15120
| 2/Q/175 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 100mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15122
| 2/Q/175 Item F — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Gas detectors |  | Candidate · Amount prints “Included” · 2 - Main!A15126
| 2/Q/175 Item J — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Isolation valve; 32mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15132
| 2/Q/175 Item K — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Isolation valve; 50mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15134
| 2/Q/175 Item L — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Isolation valve; 65mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15136
| 2/Q/175 Item M — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Isolation valve; 80mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15138
| 2/Q/175 Item P — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Kitchen gas pipe assembly; including isolating valve, second stage regulator, solenoid valve, automatic shut-off valve, wirings, connections, fixings, accessories and all ancillary works as necessary — 20mm diameter |  | Candidate · Amount prints “Included” · 2 - Main!A15146
| 2/Q/176 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To ground and podium |  | Candidate · Amount prints “Included” · 2 - Main!A15166
| 2/Q/176 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To tower 1 |  | Candidate · Amount prints “Included” · 2 - Main!A15168
| 2/Q/176 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To tower 2 |  | Candidate · Amount prints “Included” · 2 - Main!A15170
| 2/Q/176 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To tower 3 |  | Candidate · Amount prints “Included” · 2 - Main!A15172
| 2/Q/176 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To tower 4 |  | Candidate · Amount prints “Included” · 2 - Main!A15174
| 2/Q/177 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for all connections to existing services mains |  | Candidate · Amount prints “Included within plot” · 2 - Main!A15212
| 2/Q/177 Item H — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for providing spares for Mechanical Engineering Installations |  | Candidate · Amount prints “0” · 2 - Main!A15226
| 2/Q/179 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for marking the positions of and cutting or forming holes, mortices, chases or the like and all making good |  | Candidate · Amount prints “Included” · 2 - Main!A15286
| 2/Q/179 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for supplying and fixing all sleeves, frames and built-in fire stoppers for building into concrete structures and masonry walls |  | Candidate · Amount prints “Included” · 2 - Main!A15288
| 2/Q/179 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good |  | Candidate · Amount prints “Included” · 2 - Main!A15290
| 2/Q/179 Item J — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for all decorative painting including removing protective coatings or wrappings and cleaning and polishing exposed surfaces for Mechanical installations. |  | Candidate · Amount prints “Included” · 2 - Main!A15298
| 2/Q/180 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work to the Mechanical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “Included” · 2 - Main!A15316
| 2/Q/181 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Mechanical Engineering Installations in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A15344
| 2/R/11 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 6mm² XLPE/SWA/LSOH + 1C x 6mm² ECC — From SMDB-T2-GF-LV to 20A TP isolator for CHEMI DOZ UNIT - GF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A16334
| 2/R/12 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 6mm² XLPE/SWA/LSOH + 1C x 6mm² ECC — From SMDB-T2-GF-LV to 20A TP isolator for DOZ CIRCULATION PUMP - GF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A16349
| 2/R/16 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC — From SMDB-T1-03-LL01 to DB-T1-03-EXT |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A16578
| 2/R/43 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 25mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T3-55-LL01 to DB-T3-55-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A17799
| 2/R/44 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 50mm² XLPE/SWA/LSOH + 1C x 25mm² ECC — From SMDB-T1-B2-LL01 to MCC-T1-B2-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A17846
| 2/R/45 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 70mm² XLPE/SWA/LSOH + 1C x 35mm² ECC — From 160A MCCB tap-off (SMDB-T3-54-BR01) to SMDB-T3-54-BR01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A17888
| 2/R/46 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 70mm² XLPE/SWA/LSOH + 1C x 35mm² ECC — From 160A MCCB tap-off to SMDB-T4-54-BR01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A17907
| 2/R/49 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 6mm² XLPE/SWA/FR + 1C x 6mm² ECC — From ESMDB-T2-GF-LV-01 to 32A TP isolator for ISO-TF-GF-UPS1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18058
| 2/R/50 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 6mm² XLPE/SWA/FR + 1C x 6mm² ECC — From ESMDB-T2-GF-LV-01 to 32A TP isolator for ISO-TF-GF-UPS1 (MAINTENANCE BYPASS) |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18069
| 2/R/50 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 6mm² XLPE/SWA/FR + 1C x 6mm² ECC — From ESMDB-T2-GF-LV-01 to 32A TP isolator for ISO-TF-GF-UPS1 (MAINTENANCE BYPASS) |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18071
| 2/R/59 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 25mm² XLPE/SWA/FR + 1C x 16mm² ECC — From EMCC-T2-GF-FAN-02 to 20A TP isolator for T2-GF-SPF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18506
| 2/R/61 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 50mm² XLPE/SWA/FR + 1C x 25mm² ECC — From EMDB-T3-GF-LV01 to ESMDB-T3-55-FAN |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18606
| 2/R/65 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator at water feature pump room |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18758
| 2/R/65 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-B1-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18760
| 2/R/65 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-B1-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18762
| 2/R/65 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-B1-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18764
| 2/R/65 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-B2-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18766
| 2/R/65 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-B2-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18768
| 2/R/65 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-B1-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18770
| 2/R/66 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-B2-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18784
| 2/R/66 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to DB-T2-GF-SS-01 |  | Candidate · Amount prints “Included” · 2 - Main!A18786
| 2/R/66 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EDB-T2-GF-LL02 |  | Candidate · Amount prints “Included” · 2 - Main!A18794
| 2/R/66 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EMCC-T2-GF-FAN-02 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18796
| 2/R/66 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18798
| 2/R/66 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18800
| 2/R/66 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SP isolator |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18802
| 2/R/66 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to TPN isolator |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18804
| 2/R/66 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18806
| 2/R/66 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-GF-LL02 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18808
| 2/R/66 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-01-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18810
| 2/R/66 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to UDB-T1-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18812
| 2/R/66 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to UDB-T2-GF-LV01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18814
| 2/R/66 Item S — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to UDB-T4-GF-LV01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18816
| 2/R/66 Item T — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to UDB-T4-GF-SEC-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18818
| 2/R/66 Item U — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to USMDB-T2-BR-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18820
| 2/R/66 Item V — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to USMDB-T2-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18822
| 2/R/66 Item W — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to USMDB-T3-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18824
| 2/R/66 Item X — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to USMDB-T4-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18826
| 2/R/67 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T1-50-LIFT2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18839
| 2/R/67 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T1-59-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18841
| 2/R/67 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for GEF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18843
| 2/R/67 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for HEAT RECOVERY WHEEL |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18845
| 2/R/67 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for BOOSTER PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18847
| 2/R/67 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for CBS |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18849
| 2/R/67 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for FAHU-EXTRACTION FAN |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18851
| 2/R/67 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for FAHU-SUPPLYFAN |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18853
| 2/R/67 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for HEATER |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18855
| 2/R/67 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for JOCKEY PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18857
| 2/R/67 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18859
| 2/R/67 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for T1-51F-GEF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18861
| 2/R/67 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18863
| 2/R/67 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for shaft lighting |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18865
| 2/R/67 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18867
| 2/R/67 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18869
| 2/R/67 Item S — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18871
| 2/R/68 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18890
| 2/R/68 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18892
| 2/R/68 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-51-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18894
| 2/R/68 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EMCC-48-T2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18896
| 2/R/68 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T2-59-LIFT2 |  | Candidate · Amount prints “Included” · 2 - Main!A18898
| 2/R/68 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T2-59-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18900
| 2/R/68 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for HEAT RECOVERY WHEEL |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18902
| 2/R/68 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for T2-29F-GEF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18904
| 2/R/68 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for BOOSTER PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18906
| 2/R/68 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for WATER TRANSFER PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18908
| 2/R/68 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP fire rated isolator for JOCKEY PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18910
| 2/R/68 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for CBS |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18912
| 2/R/68 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for FAHU-EXTRACT FAN |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18914
| 2/R/68 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for FAHU-SUPPLY FAN |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18916
| 2/R/68 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for HEATER |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18918
| 2/R/68 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator for CHWP-1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18920
| 2/R/68 Item S — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator for CHWP-2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18922
| 2/R/69 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator for CHWP-3 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18937
| 2/R/69 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for T2-48F-FPEF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18939
| 2/R/69 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for TRANSFER PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18941
| 2/R/69 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP fire rated isolator for JOCKEY PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18943
| 2/R/69 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator for LEVEL 55 - GSM ETISALAT |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18945
| 2/R/69 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator for LEVEL 56 - GSM DU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18947
| 2/R/69 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18949
| 2/R/69 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP fire rated isolator for T2-59F-GEF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18951
| 2/R/69 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A SP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18953
| 2/R/69 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 80A SP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18955
| 2/R/69 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for shaft lighting |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18957
| 2/R/69 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-29-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18959
| 2/R/69 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-29-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18961
| 2/R/69 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-29-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18963
| 2/R/69 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-29-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18965
| 2/R/69 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-59-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18967
| 2/R/70 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-RF-FAHU1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18981
| 2/R/70 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-48-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18983
| 2/R/70 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-48-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18985
| 2/R/70 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-48-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18987
| 2/R/70 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-48-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18989
| 2/R/70 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T3-55-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18991
| 2/R/70 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SPN isolator for GEF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18993
| 2/R/70 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SPN isolator for heat recovery wheel |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18995
| 2/R/70 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TPN isolator for BOOSTER PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18997
| 2/R/70 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN fire rated isolator for jockey pump |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A18999
| 2/R/70 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for CBS |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19001
| 2/R/70 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for FAHU-EXTRACTION FAN |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19003
| 2/R/70 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for FAHU-SUPPLY FAN |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19005
| 2/R/70 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for HEATER |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19007
| 2/R/70 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19009
| 2/R/70 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP fire rated isolator for T3-55F-GEF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19011
| 2/R/71 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19024
| 2/R/71 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for shaft lighting |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19026
| 2/R/71 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19028
| 2/R/71 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19030
| 2/R/71 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19032
| 2/R/71 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19034
| 2/R/71 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19036
| 2/R/71 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-55-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19038
| 2/R/71 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EMCC-T3-55-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19040
| 2/R/71 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T4-53-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19042
| 2/R/71 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T4-59-LIFT2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19044
| 2/R/71 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for HEAT WHEEL |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19046
| 2/R/71 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for T4-29F-GEF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19048
| 2/R/71 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TPN isolator for BOOSTER PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19050
| 2/R/71 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TPN isolator for WATER TRANSFER PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19052
| 2/R/71 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for CBS |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19054
| 2/R/71 Item S — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for HEAT WHEEL |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19056
| 2/R/71 Item T — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for FAHU-EXTRACT FAN |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19058
| 2/R/72 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for FAHU-SUPPLY FAN |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19073
| 2/R/72 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for JOCKEY PUMP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19075
| 2/R/72 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator for CHWP-3 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19077
| 2/R/72 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19079
| 2/R/72 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP fire rated isolator for T4-59F-GEF |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19081
| 2/R/72 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A SP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19083
| 2/R/72 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 80A SP isolator for FAHU-RF-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19085
| 2/R/72 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for shaft lighting |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19087
| 2/R/72 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-29-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19089
| 2/R/72 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-L29-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19091
| 2/R/72 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-L29-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19093
| 2/R/72 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-L29-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19095
| 2/R/72 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-L29-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19097
| 2/R/72 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-RF-FAHU1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19099
| 2/R/81 Item T — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-01-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19563
| 2/R/84 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-B1-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19713
| 2/R/84 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-B2-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19715
| 2/R/84 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19717
| 2/R/84 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-GF-LL02 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19719
| 2/R/87 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T1-50-LIFT2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19890
| 2/R/87 Item S — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T1-59-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19894
| 2/R/88 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T2-60-LIFT, TCL = 366kW |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19919
| 2/R/88 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T2-59-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19923
| 2/R/88 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T3-55-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19935
| 2/R/88 Item T — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T4-53-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19949
| 2/R/88 Item V — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T4-59-LIFT2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19953
| 2/R/89 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible sub-main distribution board — USMDB-T2-BR-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19976
| 2/R/89 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible sub-main distribution board — USMDB-T2-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19978
| 2/R/89 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible sub-main distribution board — USMDB-T3-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19980
| 2/R/89 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible sub-main distribution board — USMDB-T4-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A19982
| 2/R/101 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Distribution board — DB-T3-55-LL01, TCL = 15kW |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A20646
| 2/R/111 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible distribution board — UDB-T1-GF-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21204
| 2/R/111 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible distribution board — UDB-T2-GF-LV01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21206
| 2/R/111 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible distribution board — UDB-T4-GF-LV01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21208
| 2/R/111 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible distribution board — UDB-T4-GF-SEC-01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21210
| 2/R/111 Item T — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21216
| 2/R/111 Item U — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21218
| 2/R/111 Item V — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21220
| 2/R/112 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21232
| 2/R/112 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21234
| 2/R/112 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-51-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21236
| 2/R/112 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-B1-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21238
| 2/R/112 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-B2-LL01, TCL = 60kW |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21240
| 2/R/112 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-29-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21244
| 2/R/112 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-29-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21246
| 2/R/112 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-29-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21248
| 2/R/112 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-29-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21250
| 2/R/112 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-59-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21252
| 2/R/112 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-RF-FAHU1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21254
| 2/R/112 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-48-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21256
| 2/R/112 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-48-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21258
| 2/R/112 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-48-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21260
| 2/R/112 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-48-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21262
| 2/R/112 Item U — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-B2-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21268
| 2/R/112 Item W — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-29-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21272
| 2/R/112 Item X — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-29-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21274
| 2/R/113 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — B4.3: L29: MCC-T3-29-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21286
| 2/R/113 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-29-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21288
| 2/R/113 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-29-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21290
| 2/R/113 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-55-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21292
| 2/R/113 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-B1-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21294
| 2/R/113 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-29-TP2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21300
| 2/R/113 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-L29-FAHU |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21302
| 2/R/113 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-L29-FP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21304
| 2/R/113 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-L29-JP |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21306
| 2/R/113 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-L29-TP1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21308
| 2/R/113 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-RF-FAHU1 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21310
| 2/R/113 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-B1-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21312
| 2/R/113 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-B2-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21314
| 2/R/113 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Emergency motor control center — EMCC-48-T2 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21318
| 2/R/113 Item W — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Emergency motor control center — EMCC-T2-02-FAN1, TCL = 120kW |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21328
| 2/R/114 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Emergency motor control center — EMCC-T2-GF-FAN-02 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21346
| 2/R/114 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Emergency motor control center — EMCC-T3-55-LL01 |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21356
| 2/R/116 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Tap-off unit — 500A MCCB tap-off |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21446
| 2/R/117 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Isolating switch — 100A TP isolator, weatherproof |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21498
| 2/R/117 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Isolating switch — SP isolator |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21512
| 2/R/117 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Isolating switch — TPN isolator |  | Candidate · Amount prints “Not Applicable” · 2 - Main!A21514
| 2/R/128 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Luminaires; including fixings, supports, hangers, accessories and all ancillary works as necessary; as specialist lighting specification — Apartment lighting — ID lightings; fixed decorative lights such as pendant lights, chandelier lights, picture lights to FOH areas - Supply by Emaar; Contractor to allow for storage, protection and installation of ID lightings |  | Candidate · Amount prints “Included” · 2 - Main!A22007
| 2/R/129 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Lighting controls; including fixings, supports, hangers, accessories and all ancillary works as necessary — LED strip driver for 1BR-A unit |  | Candidate · Amount prints “Included” · 2 - Main!A22056
| 2/R/129 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Lighting controls; including fixings, supports, hangers, accessories and all ancillary works as necessary — LED strip driver for 2BR-C unit |  | Candidate · Amount prints “Included” · 2 - Main!A22058
| 2/R/141 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Accessories; including fixings, supports, hangers and all ancillary works as necessary — Photocell |  | Candidate · Amount prints “0” · 2 - Main!A22664
| 2/R/146 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Accessories; including fixings, supports, hangers and all ancillary works as necessary — FM 200 |  | Candidate · Amount prints “Included” · 2 - Main!A22879
| 2/R/150 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Accessories; including fixings, supports, hangers and all ancillary works as necessary — Emergency lighting installations at Tower 3 Level 29 common areas |  | Candidate · Amount prints “Included” · 2 - Main!A23032
| 2/R/150 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Accessories; including fixings, supports, hangers and all ancillary works as necessary — Emergency lighting installations at Tower 4 Level 55 common areas |  | Candidate · Amount prints “Included” · 2 - Main!A23034
| 2/R/163 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Cables and conduits to termination points; including terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — From BMS IP network to DDC points |  | Candidate · Amount prints “Included” · 2 - Main!A23601
| 2/R/163 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Equipment; including active and passive network components, terminations, software, configuration, setup and programming, interface connections, fixings, supports, hangers, accessories and all ancillary works as necessary — Direct digital control, DDC |  | Candidate · Amount prints “Included” · 2 - Main!A23607
| 2/R/163 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To ACB trip status |  | Candidate · Amount prints “Included” · 2 - Main!A23615
| 2/R/164 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To access control panel (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23629
| 2/R/164 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To BCWS pumps |  | Candidate · Amount prints “Included” · 2 - Main!A23631
| 2/R/164 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To booster pumps |  | Candidate · Amount prints “Included” · 2 - Main!A23633
| 2/R/164 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To CBS panel (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23635
| 2/R/164 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To CCTV system (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23637
| 2/R/164 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To chemical dosing unit system |  | Candidate · Amount prints “Included” · 2 - Main!A23639
| 2/R/164 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To chilled water pumps |  | Candidate · Amount prints “Included” · 2 - Main!A23641
| 2/R/164 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To clean agent fire suppression system (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23643
| 2/R/164 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To common fault alarm |  | Candidate · Amount prints “Included” · 2 - Main!A23645
| 2/R/164 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To co-monitoring panel |  | Candidate · Amount prints “Included” · 2 - Main!A23647
| 2/R/164 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To co-monitoring/sensor |  | Candidate · Amount prints “Included” · 2 - Main!A23649
| 2/R/164 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To domestic water pumps (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23651
| 2/R/164 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To elevators (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23653
| 2/R/164 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To extract fan |  | Candidate · Amount prints “Included” · 2 - Main!A23655
| 2/R/164 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To FAHU |  | Candidate · Amount prints “Included” · 2 - Main!A23657
| 2/R/164 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To fire alarm panel (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23659
| 2/R/164 Item S — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To fire pump (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23661
| 2/R/164 Item T — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To FLS fans and dampers (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23663
| 2/R/164 Item U — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To FLS fans/MSFD's (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23665
| 2/R/164 Item V — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To garbage extract fans (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23667
| 2/R/164 Item W — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To gate barrier (thru FAS) |  | Candidate · Amount prints “Included” · 2 - Main!A23669
| 2/R/165 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To GEF-1 & 2 (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23684
| 2/R/165 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To generator (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23686
| 2/R/165 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To integrated panel with ATS |  | Candidate · Amount prints “Included” · 2 - Main!A23688
| 2/R/165 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To irrigation water pumps (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23690
| 2/R/165 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To jet fan (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23692
| 2/R/165 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To lighting control system (control and monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23694
| 2/R/165 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To LPG detecting panel (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23696
| 2/R/165 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To LPG tank high level alarm (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23698
| 2/R/165 Item J — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To LV/EMU (current/voltage) (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23700
| 2/R/165 Item K — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To motor control centres |  | Candidate · Amount prints “Included” · 2 - Main!A23702
| 2/R/165 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To MFSD (smoke control) (thru FAS) |  | Candidate · Amount prints “Included” · 2 - Main!A23704
| 2/R/165 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To PMU's |  | Candidate · Amount prints “Included” · 2 - Main!A23706
| 2/R/165 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To pool plant equipment (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23708
| 2/R/165 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To pressurization unit system |  | Candidate · Amount prints “Included” · 2 - Main!A23710
| 2/R/165 Item Q — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To sump pumps |  | Candidate · Amount prints “Included” · 2 - Main!A23712
| 2/R/165 Item R — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To supply fans |  | Candidate · Amount prints “Included” · 2 - Main!A23714
| 2/R/165 Item S — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To thermostat (common area) |  | Candidate · Amount prints “Included” · 2 - Main!A23716
| 2/R/165 Item T — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To UPS for security system (monitoring) |  | Candidate · Amount prints “Included” · 2 - Main!A23718
| 2/R/165 Item U — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To water tank level (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23720
| 2/R/165 Item V — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To water transfer pumps (monitoring only) |  | Candidate · Amount prints “Included” · 2 - Main!A23722
| 2/R/166 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere |  | Candidate · Amount prints “Included” · 2 - Main!A23737
| 2/R/166 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for all identification including painting, marking and labeling |  | Candidate · Amount prints “Included” · 2 - Main!A23739
| 2/R/166 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installation |  | Candidate · Amount prints “Included” · 2 - Main!A23743
| 2/R/166 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for providing spares for the Electrical Engineering Installation |  | Candidate · Amount prints “0” · 2 - Main!A23745
| 2/R/166 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like |  | Candidate · Amount prints “Included” · 2 - Main!A23747
| 2/R/167 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades |  | Candidate · Amount prints “Included” · 2 - Main!A23762
| 2/R/167 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for liaison with obtaining approvals and attendance on approved Authorities, other statutory bodies and service providers as required |  | Candidate · Amount prints “Included” · 2 - Main!A23764
| 2/R/167 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for marking the positions of and cutting or forming holes, mortices, chases or the like and all making good |  | Candidate · Amount prints “Included” · 2 - Main!A23766
| 2/R/167 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for supplying and fixing all sleeves, frames and built-in fire stoppers for building into concrete structures and masonry walls |  | Candidate · Amount prints “Included” · 2 - Main!A23768
| 2/R/167 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good |  | Candidate · Amount prints “Included” · 2 - Main!A23770
| 2/R/167 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for fire stopping all cables, conduit, trucking, cable tray and the like at penetrations through fire walls and other structures and making good |  | Candidate · Amount prints “Included” · 2 - Main!A23772
| 2/R/167 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good |  | Candidate · Amount prints “Included” · 2 - Main!A23774
| 2/R/167 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for all protective painting including removing protective coatings or wrappings and cleaning exposed surfaces for Electrical installations. |  | Candidate · Amount prints “Included” · 2 - Main!A23776
| 2/R/168 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for all decorative painting including removing protective coatings or wrappings and cleaning exposed surfaces for Electrical installations. |  | Candidate · Amount prints “Included” · 2 - Main!A23792
| 2/R/168 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Electrical Engineering Installations |  | Candidate · Amount prints “Included” · 2 - Main!A23794
| 2/R/168 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for all incidental work to the Electrical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “Included” · 2 - Main!A23796
| 2/R/169 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Electrical Engineering Installations in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 2 - Main!A23821
| 3/B/4 Item N — Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for the provision of water only for maintenance purpose during defect liability period |  | Candidate · Amount prints “Included” · 3 - Ext!A156
| 3/B/5 Item A — Bill 3 — SECTION B - SITE WORKS (3/B) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Site Works in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A173
| 3/C/3 Item B — Bill 3 — SECTION C - CONCRETE WORKS (3/C) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Concrete Works in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A414
| 3/E/2 Item A — Bill 3 — SECTION E - METALWORK (3/E) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Metalwork in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A613
| 3/G/2 Item A — Bill 3 — SECTION G - THERMAL AND MOISTURE PROTECTION (3/G) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Thermal and Moisture Protection in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A762
| 3/J/8 Item A — Bill 3 — SECTION J - FINISHES (3/J) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Finishes in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A1150
| 3/K/2 Item A — Bill 3 — SECTION K - ACCESSORIES (3/K) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Accessories in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A1435
| 3/L/2 Item A — Bill 3 — SECTION L - EQUIPMENT (3/L) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Equipment in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A1598
| 3/M/1 Item B — Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Lounge table |  | Candidate · Amount prints “0” · 3 - Ext!A1713
| 3/M/1 Item C — Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Outdoor chaise |  | Candidate · Amount prints “0” · 3 - Ext!A1715
| 3/M/1 Item D — Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Pool umbrella |  | Candidate · Amount prints “0” · 3 - Ext!A1717
| 3/M/1 Item E — Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Lifeguard station |  | Candidate · Amount prints “0” · 3 - Ext!A1719
| 3/M/1 Item F — Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Raised cabana |  | Candidate · Amount prints “0” · 3 - Ext!A1721
| 3/M/1 Item G — Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Code: FE-02-G; Waste and recycling aluminium bins; size 775 x 260 dia x 985mm high |  | Candidate · Amount prints “0” · 3 - Ext!A1723
| 3/M/2 Item E — Bill 3 — SECTION M - FURNISHING (3/M) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Furnishing in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A1766
| 3/N/1 Item A — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 450mm dia Sand filter to swimming pool 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A1863
| 3/N/1 Item B — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 500mm dia Sand filter |  | Candidate · Amount prints “Included” · 3 - Ext!A1865
| 3/N/1 Item C — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 550mm dia Sand filter to swimming pool 04 & 05 |  | Candidate · Amount prints “Included” · 3 - Ext!A1867
| 3/N/1 Item D — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 1000mm dia Sand filter to swimming pool 02 |  | Candidate · Amount prints “Included” · 3 - Ext!A1869
| 3/N/1 Item E — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 1200mm dia Sand filter to swimming pool 01 + kids pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1871
| 3/N/1 Item F — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 0.75 HP (2D + 1S) |  | Candidate · Amount prints “Included” · 3 - Ext!A1873
| 3/N/1 Item G — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 1 Hp/Ph (2D + 1S) to swimming pool 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A1875
| 3/N/1 Item J — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 3Hp / 3Ph (2D + 1S) to swimming pool 02 |  | Candidate · Amount prints “Included” · 3 - Ext!A1879
| 3/N/1 Item K — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 3.5 Hp/3Ph to swimming pool 04 |  | Candidate · Amount prints “Included” · 3 - Ext!A1881
| 3/N/1 Item L — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 5.5Hp / 3Ph (2D + 1S) to swimming pool 01 + kids pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1883
| 3/N/1 Item M — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Small Tank to swimming pool 02, 03, 04 & 05 |  | Candidate · Amount prints “Included” · 3 - Ext!A1885
| 3/N/1 Item N — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Big Tank to swimming pool 03 & 04 |  | Candidate · Amount prints “Included” · 3 - Ext!A1887
| 3/N/1 Item P — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Balancing tank 10m3 to swimming pool 04 |  | Candidate · Amount prints “Included” · 3 - Ext!A1889
| 3/N/1 Item Q — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Balancing tank (2m x 3m x 2m) to swimming pool 05 |  | Candidate · Amount prints “Included” · 3 - Ext!A1891
| 3/N/1 Item R — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Balancing tank (4m x 2m x 2m) to swimming pool 01 + kids pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1893
| 3/N/1 Item S — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — UV Disinfection System to swimming pool 01, 02, 03, 04 & 05 |  | Candidate · Amount prints “Included” · 3 - Ext!A1895
| 3/N/1 Item T — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank 100 Ltr including stirrer to swimming pool 03 & penthouse pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1897
| 3/N/1 Item U — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank 200 Ltr, flow 80 m3/hr including manual mixer to swimming pool 02 |  | Candidate · Amount prints “Included” · 3 - Ext!A1899
| 3/N/2 Item A — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank 250 Ltr, flow 112 m3/hr including manual mixer to swimming pool 01 + kids pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1912
| 3/N/2 Item B — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank 200 ltr, flow 20 m3/hr including manual mixer swimming pool 04 & 05 |  | Candidate · Amount prints “Included” · 3 - Ext!A1914
| 3/N/2 Item C — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Automatic chemical dosing system for swimming pool 01, 02, 03, 04 & 05 and penthouse pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1916
| 3/N/2 Item D — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 100 Ltr including stirrer to swimming pool 03 & penthouse pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1918
| 3/N/2 Item E — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 200 ltr, flow 20 m3/hr including stirrer to swimming pool 04 & 05 |  | Candidate · Amount prints “Included” · 3 - Ext!A1920
| 3/N/2 Item F — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 200 Ltr, flow 80 m3/hr including stirrer to swimming pool 02 |  | Candidate · Amount prints “Included” · 3 - Ext!A1922
| 3/N/2 Item G — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 250 Ltr, flow 112 m3/hr including stirrer to swimming pool 01 + kids pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1924
| 3/N/2 Item H — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 35kW/25kW to swimming pool 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A1926
| 3/N/2 Item J — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 45kW/32kW to swimming pool 05 |  | Candidate · Amount prints “Included” · 3 - Ext!A1928
| 3/N/2 Item K — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 160kW/115kW to swimming pool 04 |  | Candidate · Amount prints “Included” · 3 - Ext!A1930
| 3/N/2 Item L — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 250kW/180kW to swimming pool 02 |  | Candidate · Amount prints “Included” · 3 - Ext!A1932
| 3/N/2 Item M — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 135kW/97kW to swimming pool 01 + kids pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1934
| 3/N/2 Item N — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Water meter to swimming pool 01, 02, 03, 04 & 05 and penthouse pool |  | Candidate · Amount prints “Included” · 3 - Ext!A1936
| 3/N/2 Item P — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Electrical heater 60kW |  | Candidate · Amount prints “Included” · 3 - Ext!A1938
| 3/N/2 Item Q — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat Exchanger, capacity: 40kW |  | Candidate · Amount prints “Included” · 3 - Ext!A1940
| 3/N/2 Item R — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Pressure breaking chamber (600 x 800 x 600mm) |  | Candidate · Amount prints “Included” · 3 - Ext!A1942
| 3/N/2 Item S — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 25mm (1 inch) Ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1946
| 3/N/2 Item T — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 40mm (1 1/2 inch) Ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1948
| 3/N/3 Item A — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2") Ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1958
| 3/N/3 Item B — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 60mm (2 1/2 inch) Ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1960
| 3/N/3 Item C — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 75mm (3 inch) ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1962
| 3/N/3 Item D — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 80mm (3") Ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1964
| 3/N/3 Item E — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 100mm (4") Ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1966
| 3/N/3 Item F — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 25mm (1 inch) NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A1968
| 3/N/3 Item G — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 40mm (2") NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A1970
| 3/N/3 Item H — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2") NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A1972
| 3/N/3 Item J — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 60mm (2 1/2 inch) NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A1974
| 3/N/3 Item K — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 75mm (3 inch) NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A1976
| 3/N/3 Item L — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 80mm (3") NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A1978
| 3/N/3 Item M — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 100mm (4") NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A1980
| 3/N/3 Item N — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 150mm (6") NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A1982
| 3/N/3 Item P — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 25mm (1 inch) Butterfly valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1984
| 3/N/3 Item Q — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2") Butterfly valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1986
| 3/N/3 Item R — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 63mm (2 1/2") Butterfly valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1988
| 3/N/3 Item S — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 75mm (2") Butterfly valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1990
| 3/N/3 Item T — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 80mm (3") Butterfly valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1992
| 3/N/3 Item U — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 100mm (4") Butterfly valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1994
| 3/N/3 Item V — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 150mm (6") Butterfly valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1996
| 3/N/3 Item W — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2") solenoid valve |  | Candidate · Amount prints “Included” · 3 - Ext!A1998
| 3/N/3 Item X — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2 inch) Bypass valve |  | Candidate · Amount prints “Included” · 3 - Ext!A2000
| 3/N/3 Item Y — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 60mm (2 1/2 inch) discharge header, flow 22m3/hr |  | Candidate · Amount prints “Included” · 3 - Ext!A2004
| 3/N/3 Item Z — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 75mm (3 inch) discharge header, flow 16 m3/hr to SP 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A2006
| 3/N/4 Item A — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") fabricated discharge header, flow 20m3/hr to SP 04 |  | Candidate · Amount prints “Included” · 3 - Ext!A2016
| 3/N/4 Item B — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") Discharge header, flow 20m3/hr to SP 05 |  | Candidate · Amount prints “Included” · 3 - Ext!A2018
| 3/N/4 Item C — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 150mm (6") fabricated discharge header, flow 112 m3/hr to SP 01 + kids pool |  | Candidate · Amount prints “Included” · 3 - Ext!A2020
| 3/N/4 Item D — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 150mm (6") fabricated discharge header, flow 80m3/hr to SP 02 |  | Candidate · Amount prints “0” · 3 - Ext!A2022
| 3/N/4 Item E — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 7" Suction header, flow 20m3/hr to SP 04 |  | Candidate · Amount prints “Included” · 3 - Ext!A2024
| 3/N/4 Item F — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") Suction header, flow 20m3/hr to SP 05 |  | Candidate · Amount prints “Included” · 3 - Ext!A2026
| 3/N/4 Item G — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 150mm (6") fabricated suction header, flow 80m3/hr to SP 02 |  | Candidate · Amount prints “0” · 3 - Ext!A2028
| 3/N/4 Item H — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 200 x 200mm frame and grate anti-vortex drain |  | Candidate · Amount prints “Included” · 3 - Ext!A2030
| 3/N/4 Item J — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 300 x 300mm frame and grate anti-vortex drain |  | Candidate · Amount prints “Included” · 3 - Ext!A2032
| 3/N/4 Item K — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Acid injection point |  | Candidate · Amount prints “Included” · 3 - Ext!A2034
| 3/N/4 Item L — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Chlorine injection point |  | Candidate · Amount prints “Included” · 3 - Ext!A2036
| 3/N/4 Item M — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Drain fittings |  | Candidate · Amount prints “Included” · 3 - Ext!A2038
| 3/N/4 Item N — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Main drain point |  | Candidate · Amount prints “Included” · 3 - Ext!A2040
| 3/N/4 Item P — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Floor Drain |  | Candidate · Amount prints “Included” · 3 - Ext!A2042
| 3/N/4 Item Q — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Filtration inlet (wall) |  | Candidate · Amount prints “Included” · 3 - Ext!A2044
| 3/N/4 Item R — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Skimmer |  | Candidate · Amount prints “Included” · 3 - Ext!A2046
| 3/N/4 Item S — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Vacuum point |  | Candidate · Amount prints “Included” · 3 - Ext!A2048
| 3/N/4 Item T — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Wire inlet fitting (wall) |  | Candidate · Amount prints “Included” · 3 - Ext!A2050
| 3/N/4 Item U — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Wall inlet |  | Candidate · Amount prints “Included” · 3 - Ext!A2052
| 3/N/4 Item V — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Overflow fitting |  | Candidate · Amount prints “Included” · 3 - Ext!A2054
| 3/N/4 Item W — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Overflow drain |  | Candidate · Amount prints “Included” · 3 - Ext!A2056
| 3/N/4 Item X — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Water level regulator |  | Candidate · Amount prints “Included” · 3 - Ext!A2058
| 3/N/4 Item Y — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Infinity channel drain |  | Candidate · Amount prints “Included” · 3 - Ext!A2060
| 3/N/5 Item A — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 1 + Kids Pool |  | Candidate · Amount prints “Included” · 3 - Ext!A2073
| 3/N/5 Item B — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 2 |  | Candidate · Amount prints “Included” · 3 - Ext!A2075
| 3/N/5 Item C — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 3 (Kids Pool) |  | Candidate · Amount prints “Included” · 3 - Ext!A2077
| 3/N/5 Item D — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 4 |  | Candidate · Amount prints “Included” · 3 - Ext!A2079
| 3/N/5 Item E — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 5 (Kids Pool) |  | Candidate · Amount prints “Included” · 3 - Ext!A2081
| 3/N/5 Item F — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Penthouse Pool |  | Candidate · Amount prints “Included” · 3 - Ext!A2083
| 3/N/5 Item G — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 1 + Kids Pool |  | Candidate · Amount prints “Included” · 3 - Ext!A2089
| 3/N/5 Item H — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 2 |  | Candidate · Amount prints “Included” · 3 - Ext!A2091
| 3/N/5 Item J — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 3 (Kids Pool) |  | Candidate · Amount prints “Included” · 3 - Ext!A2093
| 3/N/5 Item K — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 4 |  | Candidate · Amount prints “Included” · 3 - Ext!A2095
| 3/N/5 Item L — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 5 (Kids Pool) |  | Candidate · Amount prints “Included” · 3 - Ext!A2097
| 3/N/5 Item M — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Penthouse Pool |  | Candidate · Amount prints “Included” · 3 - Ext!A2099
| 3/N/6 Item A — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 450mm dia Sand filter to WF 02, 03, PH |  | Candidate · Amount prints “Included” · 3 - Ext!A2126
| 3/N/6 Item B — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 550mm dia Sand filter to WF 01 |  | Candidate · Amount prints “Included” · 3 - Ext!A2128
| 3/N/6 Item C — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Small tank to WF 02, 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A2130
| 3/N/6 Item D — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank - 100 Ltr, flow 10m3/hr including manual mixer to WF 01 |  | Candidate · Amount prints “Included” · 3 - Ext!A2132
| 3/N/6 Item E — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank - 100 Ltr, flow 16m3/hr including manual mixer to WF 02, 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A2134
| 3/N/6 Item F — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Automatic chemical dosing system to WF 01, 02, 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A2136
| 3/N/6 Item G — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — UV disinfection system to WF 02, 03, PH |  | Candidate · Amount prints “Included” · 3 - Ext!A2138
| 3/N/6 Item H — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 100 Ltr, flow 10m3/hr including stirrer to WF 01 |  | Candidate · Amount prints “Included” · 3 - Ext!A2140
| 3/N/6 Item J — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 100 Ltr, flow 16m3/hr including stirrer to WF 02, 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A2142
| 3/N/6 Item K — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 1Hp /1 Ph (2D + 1S) for WF-01 to WF 01 |  | Candidate · Amount prints “Included” · 3 - Ext!A2144
| 3/N/6 Item L — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 1.5Hp/1 Ph (2D + 1S) to WF 02, 03, PH |  | Candidate · Amount prints “Included” · 3 - Ext!A2146
| 3/N/6 Item M — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Water meter to WF 01, 02, 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A2148
| 3/N/6 Item N — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 25mm (1 inch) Ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A2152
| 3/N/6 Item P — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 40mm (1 1/2") Ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A2154
| 3/N/6 Item Q — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 50mm (2" ) Ball valve |  | Candidate · Amount prints “Included” · 3 - Ext!A2156
| 3/N/6 Item R — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 80mm (3") Ball Valve |  | Candidate · Amount prints “Included” · 3 - Ext!A2158
| 3/N/6 Item S — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 50mm (2" ) NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A2160
| 3/N/6 Item T — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 80mm (3" ) NRV |  | Candidate · Amount prints “Included” · 3 - Ext!A2162
| 3/N/6 Item U — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — Allow for pipe accessories for penthouse water feature |  | Candidate · Amount prints “Included” · 3 - Ext!A2164
| 3/N/7 Item A — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 50mm (2" ) discharge header, flow 10m3/hr to WF 01 |  | Candidate · Amount prints “Included” · 3 - Ext!A2178
| 3/N/7 Item B — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") discharge header, flow 16m3/hr to WF 02, 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A2180
| 3/N/7 Item C — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 50mm (2") suction header, flow 10m3/hr to WF 01 |  | Candidate · Amount prints “Included” · 3 - Ext!A2182
| 3/N/7 Item D — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 50mm (3") suction header, flow 16m3/hr to WF 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A2184
| 3/N/7 Item E — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") suction header, flow 16m3/hr to WF 02 |  | Candidate · Amount prints “Included” · 3 - Ext!A2186
| 3/N/7 Item F — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 200x200mm frame & grate anti-vortex drain to WF 01, 02, 03 |  | Candidate · Amount prints “Included” · 3 - Ext!A2188
| 3/N/7 Item G — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Floor Drain |  | Candidate · Amount prints “Included” · 3 - Ext!A2190
| 3/N/7 Item H — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Filtration inlet (wall) |  | Candidate · Amount prints “Included” · 3 - Ext!A2192
| 3/N/7 Item J — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Skimmer fitting |  | Candidate · Amount prints “Included” · 3 - Ext!A2194
| 3/N/7 Item K — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Vacuum point |  | Candidate · Amount prints “Included” · 3 - Ext!A2196
| 3/N/7 Item L — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Acid injection point |  | Candidate · Amount prints “Included” · 3 - Ext!A2198
| 3/N/7 Item M — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Chlorine injection point |  | Candidate · Amount prints “Included” · 3 - Ext!A2200
| 3/N/7 Item N — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Allow for water feature accessories for penthouse water feature |  | Candidate · Amount prints “Included” · 3 - Ext!A2202
| 3/N/7 Item P — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 1 + Kids Pool |  | Candidate · Amount prints “Included” · 3 - Ext!A2206
| 3/N/7 Item Q — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 2 |  | Candidate · Amount prints “Included” · 3 - Ext!A2208
| 3/N/7 Item R — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 3 (Kids Pool) |  | Candidate · Amount prints “Included” · 3 - Ext!A2210
| 3/N/7 Item S — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 4 |  | Candidate · Amount prints “Included” · 3 - Ext!A2212
| 3/N/7 Item T — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 5 (Kids Pool) |  | Candidate · Amount prints “Included” · 3 - Ext!A2214
| 3/N/7 Item U — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Penthouse Pool |  | Candidate · Amount prints “Included” · 3 - Ext!A2216
| 3/N/7 Item V — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Water Feature 01 at Ground Floor |  | Candidate · Amount prints “Included” · 3 - Ext!A2218
| 3/N/7 Item W — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Water Feature 02 at Podium |  | Candidate · Amount prints “Included” · 3 - Ext!A2220
| 3/N/7 Item X — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Water Feature 03 at Podium |  | Candidate · Amount prints “Included” · 3 - Ext!A2222
| 3/N/7 Item Y — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Penthouse water feature |  | Candidate · Amount prints “Included” · 3 - Ext!A2224
| 3/N/8 Item A — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 1 + Kids Pool |  | Candidate · Amount prints “Included” · 3 - Ext!A2238
| 3/N/8 Item B — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 2 |  | Candidate · Amount prints “Included” · 3 - Ext!A2240
| 3/N/8 Item C — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 3 (Kids Pool) |  | Candidate · Amount prints “Included” · 3 - Ext!A2242
| 3/N/8 Item D — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 4 |  | Candidate · Amount prints “Included” · 3 - Ext!A2244
| 3/N/8 Item E — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 5 (Kids Pool) |  | Candidate · Amount prints “Included” · 3 - Ext!A2246
| 3/N/8 Item F — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Penthouse Pool |  | Candidate · Amount prints “Included” · 3 - Ext!A2248
| 3/N/8 Item G — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Water Feature 01 at Ground Floor |  | Candidate · Amount prints “Included” · 3 - Ext!A2250
| 3/N/8 Item H — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Water Feature 02 at Podium |  | Candidate · Amount prints “Included” · 3 - Ext!A2252
| 3/N/8 Item J — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Water Feature 03 at Podium |  | Candidate · Amount prints “Included” · 3 - Ext!A2254
| 3/N/8 Item K — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Penthouse water feature |  | Candidate · Amount prints “Included” · 3 - Ext!A2256
| 3/N/8 Item L — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Final sub-circuits and ancillary installations complete; including cabling, wiring, containment and terminations as necessary — Light points |  | Candidate · Amount prints “Included” · 3 - Ext!A2262
| 3/N/8 Item M — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 4.1; Recessed elliptical beam pool light; 3000 K |  | Candidate · Amount prints “Included” · 3 - Ext!A2266
| 3/N/8 Item N — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 4.2; Recessed elliptical beam pool step light; 3000 K |  | Candidate · Amount prints “Included” · 3 - Ext!A2268
| 3/N/8 Item P — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 4.3; Recessed diffused pool marker light; 4000K |  | Candidate · Amount prints “Included” · 3 - Ext!A2270
| 3/N/8 Item Q — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 8.2; Surface mounted floor washer; 3000 K |  | Candidate · Amount prints “Included” · 3 - Ext!A2272
| 3/N/9 Item A — Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Special Construction in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A2284
| 3/Q/8 Item B — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for all identification including painting, marking and labelling |  | Candidate · Amount prints “Included” · 3 - Ext!A2754
| 3/Q/8 Item C — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations |  | Candidate · Amount prints “Included” · 3 - Ext!A2756
| 3/Q/8 Item D — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installation |  | Candidate · Amount prints “Included” · 3 - Ext!A2758
| 3/Q/8 Item E — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for providing spares for the Mechanical Engineering Installation |  | Candidate · Amount prints “0” · 3 - Ext!A2760
| 3/Q/8 Item F — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like |  | Candidate · Amount prints “Included” · 3 - Ext!A2762
| 3/Q/8 Item G — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades |  | Candidate · Amount prints “Included” · 3 - Ext!A2766
| 3/Q/8 Item H — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for liaison with obtaining approvals and attendance on approved Authorities, other statutory bodies and service providers as required |  | Candidate · Amount prints “Included” · 3 - Ext!A2768
| 3/Q/8 Item K — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good |  | Candidate · Amount prints “Included” · 3 - Ext!A2772
| 3/Q/8 Item L — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Mechanical Engineering Installations |  | Candidate · Amount prints “Included” · 3 - Ext!A2774
| 3/Q/8 Item M — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work to the Mechanical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “Included” · 3 - Ext!A2776
| 3/Q/9 Item A — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Mechanical Engineering Installations in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A2790
| 3/R/1 Item A — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Sub-main cables; including fixings, supports, terminations, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 3 - Ext!A2899
| 3/R/1 Item B — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Equipment (DB, kwh meter, containment, ducts, etc); including fixings, supports, hangers, concrete base, plinths, earth works, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 3 - Ext!A2901
| 3/R/1 Item C — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Excavation of trenches; including earthwork support, disposal, compaction, backfilling, marking tape, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 3 - Ext!A2903
| 3/R/1 Item D — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Connection to supply mains; including cables, conduits, fixings, supports, terminations, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 3 - Ext!A2905
| 3/R/1 Item E — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Earthing system; including earthworks, fixings, bondings, connections, joints, earthing cables, earth rods, earth pits, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 3 - Ext!A2907
| 3/R/1 Item F — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Small power including cables, conduits to termination points and accessories; including terminations, fixings, supports, hangers, accessories and all ancillary works as necessary |  | Candidate · Amount prints “0” · 3 - Ext!A2909
| 3/R/1 Item K — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — uPVC duct — 2x160mm diameter uPVC duct sleeve |  | Candidate · Amount prints “Included” · 3 - Ext!A2927
| 3/R/3 Item C — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 1.1n - Tree Spike light, Narrow beam, 3000K |  | Candidate · Amount prints “0” · 3 - Ext!A3004
| 3/R/3 Item K — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — TLTL 8.2 -Asymmetric drive over floor washer, 3000K |  | Candidate · Amount prints “0” · 3 - Ext!A3018
| 3/R/3 Item L — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for earthing and bonding as specified; in particular all metal containments shall be |  | Candidate · Amount prints “Included” · 3 - Ext!A3022
| 3/R/3 Item M — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere |  | Candidate · Amount prints “Included” · 3 - Ext!A3024
| 3/R/3 Item N — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for all identification including painting, marking and labeling |  | Candidate · Amount prints “Included” · 3 - Ext!A3026
| 3/R/3 Item Q — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installation |  | Candidate · Amount prints “Included” · 3 - Ext!A3030
| 3/R/4 Item A — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for providing spares for the Electrical Engineering Installation |  | Candidate · Amount prints “0” · 3 - Ext!A3040
| 3/R/4 Item B — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like |  | Candidate · Amount prints “Included” · 3 - Ext!A3042
| 3/R/4 Item C — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades |  | Candidate · Amount prints “Included” · 3 - Ext!A3046
| 3/R/4 Item D — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for liaison with obtaining approvals and attendance on DEWA, other statutory bodies and service providers as required |  | Candidate · Amount prints “Included” · 3 - Ext!A3048
| 3/R/4 Item E — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for marking the positions of and cutting or forming holes, mortices, chases or the like and all making good |  | Candidate · Amount prints “Included” · 3 - Ext!A3050
| 3/R/4 Item F — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for supplying and fixing all sleeves, frames and built-in fire stoppers for building into concrete structures and masonry walls |  | Candidate · Amount prints “Included” · 3 - Ext!A3052
| 3/R/4 Item G — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good |  | Candidate · Amount prints “Included” · 3 - Ext!A3054
| 3/R/4 Item H — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for fire stopping all cables, conduit, trucking, cable tray and the like at penetrations through fire walls and other structures and making good |  | Candidate · Amount prints “Included” · 3 - Ext!A3056
| 3/R/4 Item J — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good |  | Candidate · Amount prints “Included” · 3 - Ext!A3058
| 3/R/4 Item K — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Electrical Engineering Installation |  | Candidate · Amount prints “Included” · 3 - Ext!A3060
| 3/R/4 Item L — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for all incidental work to the Electrical Engineering Installation where not included above or elsewhere |  | Candidate · Amount prints “Included” · 3 - Ext!A3062
| 3/R/5 Item A — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Electrical Engineering Installations in accordance with the Specification and the Drawings (Tenderer to list below): |  | Candidate · Amount prints “0” · 3 - Ext!A3079
4 | Key High / Low Analysis | • | Not yet assessed — a rate can only be called high or low against a benchmark, and none is set for this submission.
5 | BOQ line items should be priced individually. | • | 7,350 of 8,256 lines carry a unit rate, worth 2,246,018,361.00 — 88.5% of the printed total. · Lines priced at a unit rate: 7,350 · Lines priced as a whole: 110 · Listed below; full detail on “PTC lines”, rows 795–935 (141 lines) and rows 936–966 (31 lines).
| GR1/2-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 1 As per Emaar standard CoC |  | Candidate · Amount prints “1859450” · GR1!A46
| GR1/2-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 2 Advance Payment Guarantee |  | Candidate · Amount prints “4441500” · GR1!A48
| GR1/2-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 3 Performance Bond |  | Candidate · Amount prints “5710500” · GR1!A50
| GR1/2-E — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 5 Workmen's Compensation Insurance |  | Candidate · Amount prints “2579252” · GR1!A54
| GR1/4-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 1 Access for and Possession or use of the Site |  | Candidate · Amount prints “326000” · GR1!A139
| GR1/4-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 2 Limitations of working space |  | Candidate · Amount prints “875150” · GR1!A141
| GR1/4-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 3 Limitations of working hours |  | Candidate · Amount prints “2579252” · GR1!A143
| GR1/5-D — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — 2 Supervision |  | Candidate · Amount prints “127607506” · GR1!A199
| GR1/5-E — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — 3 Security |  | Candidate · Amount prints “1677101” · GR1!A201
| GR1/5-F — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — 4 Safety, health and welfare of workpeople |  | Candidate · Amount prints “14390609” · GR1!A203
| GR1/6-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 1 Small plant and tools — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “255272” · GR1!A243
| GR1/6-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 1 Small plant and tools — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “2169815” · GR1!A245
| GR1/6-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 1 Small plant and tools — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “127636” · GR1!A247
| GR1/6-D — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 2 Scaffoldings — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “254997” · GR1!A251
| GR1/6-E — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 2 Scaffoldings — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “4589946” · GR1!A253
| GR1/6-F — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 2 Scaffoldings — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “254997” · GR1!A255
| GR1/6-G — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 3 Cranes and lifting plant — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “1903672” · GR1!A259
| GR1/6-H — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 3 Cranes and lifting plant — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “16561946” · GR1!A261
| GR1/6-J — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 3 Cranes and lifting plant — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “571102” · GR1!A263
| GR1/6-K — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 4 Plant required for specific trades — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “954406” · GR1!A267
| GR1/6-L — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 4 Plant required for specific trades — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “8112451” · GR1!A269
| GR1/6-M — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 4 Plant required for specific trades — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “477203” · GR1!A271
| GR1/6-N — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 5 Site Transport — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “216157” · GR1!A275
| GR1/6-P — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 5 Site Transport — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “3890822” · GR1!A277
| GR1/6-Q — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 5 Site Transport — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “216157” · GR1!A279
| GR1/6-R — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 5 Site Transport — 6 Other plant not listed above but necessary for the completion of the Works |  | Candidate · Amount prints “3378750” · GR1!A281
| GR1/7-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — A6 - Employer's Facilities — Particulars shall be given of any facilities required for the Employer or the Employer's representatives, which shall include: — 1 - Temporary fully functional site facilities — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “356150” · GR1!A294
| GR1/7-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — A6 - Employer's Facilities — Particulars shall be given of any facilities required for the Employer or the Employer's representatives, which shall include: — 1 - Temporary fully functional site facilities — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “336125” · GR1!A296
| GR1/7-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — A6 - Employer's Facilities — Particulars shall be given of any facilities required for the Employer or the Employer's representatives, which shall include: — 1 - Temporary fully functional site facilities — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “7500” · GR1!A298
| GR1/7-D — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Telephones, including costs of calls — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “228000” · GR1!A302
| GR1/7-E — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Telephones, including costs of calls — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “410600” · GR1!A304
| GR1/7-F — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Telephones, including costs of calls — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “15750” · GR1!A306
| GR1/7-G — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Telephones, including costs of calls — 3 - Attendance of staff (for example, drivers, laboratory assistants) |  | Candidate · Amount prints “575000” · GR1!A308
| GR1/7-H — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 - Equipment (for example surveying equipment, laboratory equipment) — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “35130” · GR1!A312
| GR1/7-J — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 - Equipment (for example surveying equipment, laboratory equipment) — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “76200” · GR1!A314
| GR1/7-K — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 - Equipment (for example surveying equipment, laboratory equipment) — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “2500” · GR1!A316
| GR1/7-L — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 - Equipment (for example surveying equipment, laboratory equipment) — 5 - Special requirements for programmes or progress charts |  | Candidate · Amount prints “147000” · GR1!A318
| GR1/8-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Any other facilities (for example, progress photographs). — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “6500” · GR1!A339
| GR1/8-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Any other facilities (for example, progress photographs). — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “63000” · GR1!A341
| GR1/8-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Any other facilities (for example, progress photographs). — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “2500” · GR1!A343
| GR1/8-D — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Signboard — Existing signboard to be taken over from Enabling Works contractor and Main Works contractor to update the names, maintain as required, remove after completion of the Works |  | Candidate · Amount prints “25000” · GR1!A348
| GR1/9-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A7 - Contractor's Facilities — A7.1 An item shall be given for facilities required by the contractor, which shall include: — 1 - Contractor's Facilities, including offices, toilets, laboratories, compounds, stores, mess rooms — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “2292840” · GR1!A389
| GR1/9-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A7 - Contractor's Facilities — A7.1 An item shall be given for facilities required by the contractor, which shall include: — 1 - Contractor's Facilities, including offices, toilets, laboratories, compounds, stores, mess rooms — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “5197105” · GR1!A391
| GR1/9-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A7 - Contractor's Facilities — A7.1 An item shall be given for facilities required by the contractor, which shall include: — 1 - Contractor's Facilities, including offices, toilets, laboratories, compounds, stores, mess rooms — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “152856” · GR1!A393
| GR1/9-D — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Temporary fencing, hoardings — i. Existing temporary site perimeter hoarding to be taken over from Enabling Works contractor and Main Works contractor to move / remove / adjust, maintain as required |  | Candidate · Amount prints “35750” · GR1!A397
| GR1/9-E — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Temporary fencing, hoardings — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “147000” · GR1!A399
| GR1/9-F — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Temporary fencing, hoardings — ii. Final Removal (Fixed Charges) |  | Candidate · Amount prints “8500” · GR1!A401
| GR1/9-K — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 Temporary roads, hard standings and crossings — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “48250” · GR1!A413
| GR1/9-L — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 Temporary roads, hard standings and crossings — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “475100” · GR1!A415
| GR1/9-M — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 Temporary roads, hard standings and crossings — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “7800” · GR1!A417
| GR1/10-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 5 Water for the Works — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “870813” · GR1!A433
| GR1/10-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 5 Water for the Works — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “4644336” · GR1!A435
| GR1/10-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 5 Water for the Works — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “290271” · GR1!A437
| GR1/10-D — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Lighting and power for the Works — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “3367938” · GR1!A441
| GR1/10-E — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Lighting and power for the Works — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “29637854” · GR1!A443
| GR1/10-F — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Lighting and power for the Works — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “673588” · GR1!A445
| GR1/10-G — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 7 Temporary telephones, electronic mail and facsimile — i. Establishment (Fixed Charges) |  | Candidate · Amount prints “105600” · GR1!A449
| GR1/10-H — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 7 Temporary telephones, electronic mail and facsimile — ii. Maintenance (Time Related Charges) |  | Candidate · Amount prints “376150” · GR1!A451
| GR1/10-J — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 7 Temporary telephones, electronic mail and facsimile — iii. Removal (Fixed Charges) |  | Candidate · Amount prints “5600” · GR1!A453
| GR1/11-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A8 - Temporary Works — A8.1 An item shall be given for temporary works including design, which shall include: — 1 Traffic diversion |  | Candidate · Amount prints “813450” · GR1!A484
| GR1/11-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A8 - Temporary Works — A8.1 An item shall be given for temporary works including design, which shall include: — 2 Access roads |  | Candidate · Amount prints “474513” · GR1!A486
| GR1/12-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 1 - Testing of materials |  | Candidate · Amount prints “488070” · GR1!A535
| GR1/12-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 2 - Testing of the Works |  | Candidate · Amount prints “1762475” · GR1!A537
| GR1/12-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 3 - Protecting the Works from inclement weather |  | Candidate · Amount prints “623645” · GR1!A539
| GR1/12-D — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 4 - Removing rubbish, protective casings and coverings and cleaning the Works at completion |  | Candidate · Amount prints “813450” · GR1!A541
| GR1/12-F — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 6 - Maintenance of public and private roads |  | Candidate · Amount prints “216920” · GR1!A545
| GR1/12-K — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 1 - Coordination with the Works by Others |  | Candidate · Amount prints “325380” · GR1!A555
| GR1/12-L — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 2 - Surveys, Setting-out and Levels |  | Candidate · Amount prints “515185” · GR1!A557
| GR1/12-M — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 3 - Dust Control, Pest Control and Lightning Protection |  | Candidate · Amount prints “623645” · GR1!A559
| GR1/12-P — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 5 - Packing, marking, storage, handling and unpacking |  | Candidate · Amount prints “113883” · GR1!A563
| GR1/13-B — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 7 - Shop Drawings |  | Candidate · Amount prints “406725” · GR1!A579
| GR1/13-C — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 8 - Submittal program, drawings and revisions |  | Candidate · Amount prints “176248” · GR1!A581
| GR1/13-D — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 9 - Method Statements |  | Candidate · Amount prints “162690” · GR1!A583
| GR1/13-E — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 10 - Operation and Maintenance Manuals |  | Candidate · Amount prints “140998” · GR1!A585
| GR1/13-F — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 11 - Building Information Modelling (BIM) System |  | Candidate · Amount prints “3308030” · GR1!A587
| GR1/13-G — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 12 - Project Management System - Unifier |  | Candidate · Amount prints “437500” · GR1!A589
| GR1/13-M — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 17 - Final Cleaning for Project Handover |  | Candidate · Amount prints “1382865” · GR1!A599
| GR1/13-N — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 18 - Provision of Handover Documentation |  | Candidate · Amount prints “149133” · GR1!A601
| GR1/13-R — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 21 - Design of the Works to the extent provided for in the Contract |  | Candidate · Amount prints “433840” · GR1!A607
| GR1/14-A — GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 23 - All mock-ups, prototypes and samples required by the Specification, the Drawings and the Schedule of Project Requirements |  | Candidate · Amount prints “325400” · GR1!A624
| 2/B/1 Item D — Bill 2 — SECTION B - SITE WORKS (2/B) — SITE PREPARATION — Dewatering; including design, maintenance, consumables, accessories and all ancillary works as necessary; complete — Maintenance of de-watering system |  | Candidate · Amount prints “3049200” · 2 - Main!A21
| 2/B/1 Item E — Bill 2 — SECTION B - SITE WORKS (2/B) — SITE PREPARATION — Dewatering; including design, maintenance, consumables, accessories and all ancillary works as necessary; complete — Allow for removal of the dewatering system and closing of raft suction pipe opening, etc.. |  | Candidate · Amount prints “246400” · 2 - Main!A23
| 2/J/9 Item F — Bill 2 — SECTION J - FINISHES (2/J) — CEILING FINISHES — Calcium silicate board ceiling system; 13mm thick; non-combustible board panels supported by metal frame system; including insulation, finishes, suspended metal support framing system, brackets, fastenings, accessories and all necessary fixings and accessories — Extra over for access panel |  | Candidate · Amount prints “29155” · 2 - Main!A4866
| 2/J/11 Item B — Bill 2 — SECTION J - FINISHES (2/J) — SUSPENDED CEILING — Monolithic gypsum board ceiling; including ceiling suspension system, shadows gaps, trims, corner protection profile, accessories and all ancillary works as necessary — Extra over for access panel; size 450 x 450mm |  | Candidate · Amount prints “309” · 2 - Main!A4948
| 2/J/12 Item J — Bill 2 — SECTION J - FINISHES (2/J) — SUSPENDED CEILING — Monolithic gypsum board ceiling; moisture resistant; including ceiling suspension system, shadows gaps, trims, corner protection profile, accessories and all ancillary works as necessary — Extra over for access panel; size 450 x 450mm |  | Candidate · Amount prints “167” · 2 - Main!A5005
| 2/L/5 Item H — Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — Allow to panel transport trolley including accessories and all ancillary works as necessary |  | Candidate · Amount prints “14102” · 2 - Main!A6674
| 2/Q/4 Item K — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations |  | Candidate · Amount prints “241378” · 2 - Main!A7781
| 2/Q/5 Item H — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Builders work in connection (BWIC) with Mechanical Engineering Installations — Allow for all BWIC with Mechanical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “444555” · 2 - Main!A7826
| 2/Q/177 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for earthing and bonding as specified; in particular all ductwork systems shall be provided with earth continuity protection at all joints |  | Candidate · Amount prints “104875” · 2 - Main!A15214
| 2/Q/177 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for all supports, fixings, anchors, insulating blocks and anti-vibration devices where not included above or elsewhere |  | Candidate · Amount prints “104875” · 2 - Main!A15216
| 2/Q/177 Item D — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for all identification including painting, marking and labeling, including labeling all valves |  | Candidate · Amount prints “104875” · 2 - Main!A15218
| 2/Q/177 Item E — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for flushing, cleaning, sterilization and chlorination of the completed installations as necessary |  | Candidate · Amount prints “31462” · 2 - Main!A15220
| 2/Q/177 Item F — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations |  | Candidate · Amount prints “4553660” · 2 - Main!A15222
| 2/Q/177 Item G — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installations |  | Candidate · Amount prints “104875” · 2 - Main!A15224
| 2/Q/177 Item J — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like |  | Candidate · Amount prints “178287” · 2 - Main!A15228
| 2/Q/178 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for vibration and noise control where not included above or elsewhere |  | Candidate · Amount prints “83902” · 2 - Main!A15249
| 2/Q/179 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades |  | Candidate · Amount prints “20976” · 2 - Main!A15282
| 2/Q/179 Item B — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for liaison with obtaining approvals and attendance on DEWA, other statutory bodies and service providers as required |  | Candidate · Amount prints “20976” · 2 - Main!A15284
| 2/Q/179 Item F — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for fire stopping all pipes, ducts and the like at penetrations through fire walls and other structures and making good |  | Candidate · Amount prints “104875” · 2 - Main!A15292
| 2/Q/179 Item G — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good |  | Candidate · Amount prints “83902” · 2 - Main!A15294
| 2/Q/179 Item H — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for all protective painting including removing protective coatings or wrappings and cleaning exposed surfaces for Mechanical installations. |  | Candidate · Amount prints “83902” · 2 - Main!A15296
| 2/Q/180 Item A — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Mechanical Engineering Installations |  | Candidate · Amount prints “20976” · 2 - Main!A15314
| 2/Q/180 Item C — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Builders work in connection (BWIC) with Mechanical Engineering Installations — Allow for all BWIC with Mechanical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “4880115” · 2 - Main!A15320
| 2/R/13 Item S — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC — From SMDB-T2-GF-LV to DB-T2-GF-WF1 |  | Candidate · Amount prints “2863” · 2 - Main!A16430
| 2/R/37 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T1-GF-LV01 to 40A TP isolator for signage (ISO-T1-GF-SIGNAGE) |  | Candidate · Amount prints “5627” · 2 - Main!A17548
| 2/R/37 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T1-GF-LV01 to 40A TP isolator for signage (ISO-T3-GF-SIGNAGE) |  | Candidate · Amount prints “5627” · 2 - Main!A17550
| 2/R/39 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T4-02-LL01 to DB-T4-02-GYM |  | Candidate · Amount prints “845” · 2 - Main!A17622
| 2/R/66 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to DB-T3-GF-LL02 |  | Candidate · Amount prints “515” · 2 - Main!A18788
| 2/R/66 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to DB-T2-03-KDCB |  | Candidate · Amount prints “6845” · 2 - Main!A18790
| 2/R/66 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EDB-T2-GF-ETS |  | Candidate · Amount prints “2556” · 2 - Main!A18792
| 2/R/118 Item U — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Containment; including fixings, supports, hangers, fittings, accessories and all ancillary works as necessary — PVC pipe — Cable containment to Retail DB |  | Candidate · Amount prints “24876” · 2 - Main!A21586
| 2/R/141 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To BMS system |  | Candidate · Amount prints “16025” · 2 - Main!A22672
| 2/R/141 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Aircraft warning lighting at Tower 3 |  | Candidate · Amount prints “10685” · 2 - Main!A22674
| 2/R/141 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Aircraft warning lighting at Tower 4 |  | Candidate · Amount prints “10685” · 2 - Main!A22676
| 2/R/148 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To BMS |  | Candidate · Amount prints “20031” · 2 - Main!A22949
| 2/R/148 Item B — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To access control panel, ACP |  | Candidate · Amount prints “16025” · 2 - Main!A22951
| 2/R/148 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To gas leak detection panel |  | Candidate · Amount prints “16025” · 2 - Main!A22953
| 2/R/148 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Fire alarm installations at Tower 3 Level 29 common areas |  | Candidate · Amount prints “13354” · 2 - Main!A22955
| 2/R/148 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Fire alarm installations at Tower 4 Level 55 common areas |  | Candidate · Amount prints “13354” · 2 - Main!A22957
| 2/R/150 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — Graphic workstation with touch screen at Tower 4 FCC room |  | Candidate · Amount prints “26709” · 2 - Main!A23044
| 2/R/150 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — Master PC at Security room |  | Candidate · Amount prints “33385” · 2 - Main!A23046
| 2/R/161 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To ACS system |  | Candidate · Amount prints “25227” · 2 - Main!A23542
| 2/R/161 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To ANPR system |  | Candidate · Amount prints “25227” · 2 - Main!A23544
| 2/R/161 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To intercom system |  | Candidate · Amount prints “25227” · 2 - Main!A23546
| 2/R/161 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To key management system |  | Candidate · Amount prints “25227” · 2 - Main!A23548
| 2/R/162 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To video management system |  | Candidate · Amount prints “163592” · 2 - Main!A23561
| 2/R/166 Item C — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations |  | Candidate · Amount prints “5151382” · 2 - Main!A23741
| 2/R/168 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Builders work in connection (BWIC) with Electrical Engineering Installations — Allow for all BWIC with Electrical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “5601893” · 2 - Main!A23800
| 3/B/4 Item L — Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for planting edging |  | Candidate · Amount prints “66444” · 3 - Ext!A152
| 3/B/4 Item M — Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for maintenance of soft landscaping works during defect liability period for a period of one year after the date of Taking over Certificate and for complying with all the requirements |  | Candidate · Amount prints “244080” · 3 - Ext!A154
| 3/Q/7 Item A — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — IRRIGATION INSTALLATION — Irrigation controller; including foundation, 100mm diameter conduit for valve cables, 40mm diameter conduit for ground cable, copper earthing, electrical connection, supports and ancillary work as necessary — Allow for connection of irrigation pipe with existing infrastructure network including ancillary work as necessary |  | Candidate · Amount prints “84750” · 3 - Ext!A2698
| 3/Q/8 Item A — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere |  | Candidate · Amount prints “42375” · 3 - Ext!A2752
| 3/Q/8 Item J — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good |  | Candidate · Amount prints “73569” · 3 - Ext!A2770
| 3/Q/8 Item N — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Builders work in connection (BWIC) with Mechanical Engineering Installations — Allow for all BWIC with Mechanical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “76998” · 3 - Ext!A2780
| 3/R/2 Item A — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — Tie-in Connection — Tie-in connection to existing electrical line |  | Candidate · Amount prints “107365” · 3 - Ext!A2944
| 3/R/2 Item M — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — External Communication Services — Electrical point — External Communication Services — Allow for ICT installation (Data connection); including cables, conduits, terminations, fixings, supports, hangers, data outlets, accessories and all ancillary works as necessary |  | Candidate · Amount prints “127075” · 3 - Ext!A2986
| 3/R/3 Item P — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant Specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations |  | Candidate · Amount prints “59885.95” · 3 - Ext!A3028
| Bill 4/1-A — PROVISIONAL SUMS — Items of Works to be Tendered — The Employer shall ascertain and determine by measurement the value of work done and/or Plant provided to which the following Provisional Sums relate in accordance with the Conditions of Contract — Workforce Productivity System — Workforce productivity monitoring system (AED1,000,000) |  | Candidate · Amount prints “1000000” · Bill 4!A12
| Bill 4/1-B — PROVISIONAL SUMS — Items of Works to be Tendered — The Employer shall ascertain and determine by measurement the value of work done and/or Plant provided to which the following Provisional Sums relate in accordance with the Conditions of Contract — Workforce Productivity System — Main Contractor's OH&P of 10% |  | Candidate · Amount prints “100000” · Bill 4!A14
| Bill 4/1-C — PROVISIONAL SUMS — Items of Works to be Tendered — The Employer shall ascertain and determine by measurement the value of work done and/or Plant provided to which the following Provisional Sums relate in accordance with the Conditions of Contract — RTA ROW Access — Design and build of the RTA ROW accesses in the adjacent DM-owned plot as per SOPR, Clause 1.6 b |  | Candidate · Amount prints “3500000” · Bill 4!A18
| Bill 4/1-D — PROVISIONAL SUMS — Items of Works to be Tendered — The Employer shall ascertain and determine by measurement the value of work done and/or Plant provided to which the following Provisional Sums relate in accordance with the Conditions of Contract — RTA ROW Access — Main Contractor's OH&P of 10% |  | Candidate · Amount prints “350000” · Bill 4!A20
| 2/B/1 Item D — Bill 2 — SECTION B - SITE WORKS (2/B) — SITE PREPARATION — Dewatering; including design, maintenance, consumables, accessories and all ancillary works as necessary; complete — Maintenance of de-watering system |  | Candidate · Amount prints “3049200” · 2 - Main!A21
| 2/B/1 Item E — Bill 2 — SECTION B - SITE WORKS (2/B) — SITE PREPARATION — Dewatering; including design, maintenance, consumables, accessories and all ancillary works as necessary; complete — Allow for removal of the dewatering system and closing of raft suction pipe opening, etc.. |  | Candidate · Amount prints “246400” · 2 - Main!A23
| 2/J/9 Item F — Bill 2 — SECTION J - FINISHES (2/J) — CEILING FINISHES — Calcium silicate board ceiling system; 13mm thick; non-combustible board panels supported by metal frame system; including insulation, finishes, suspended metal support framing system, brackets, fastenings, accessories and all necessary fixings and accessories — Extra over for access panel |  | Candidate · Amount prints “29155” · 2 - Main!A4866
| 2/J/11 Item B — Bill 2 — SECTION J - FINISHES (2/J) — SUSPENDED CEILING — Monolithic gypsum board ceiling; including ceiling suspension system, shadows gaps, trims, corner protection profile, accessories and all ancillary works as necessary — Extra over for access panel; size 450 x 450mm |  | Candidate · Amount prints “309” · 2 - Main!A4948
| 2/J/12 Item J — Bill 2 — SECTION J - FINISHES (2/J) — SUSPENDED CEILING — Monolithic gypsum board ceiling; moisture resistant; including ceiling suspension system, shadows gaps, trims, corner protection profile, accessories and all ancillary works as necessary — Extra over for access panel; size 450 x 450mm |  | Candidate · Amount prints “167” · 2 - Main!A5005
| 2/L/5 Item H — Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — Allow to panel transport trolley including accessories and all ancillary works as necessary |  | Candidate · Amount prints “14102” · 2 - Main!A6674
| 2/R/13 Item S — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC — From SMDB-T2-GF-LV to DB-T2-GF-WF1 |  | Candidate · Amount prints “2863” · 2 - Main!A16430
| 2/R/37 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T1-GF-LV01 to 40A TP isolator for signage (ISO-T1-GF-SIGNAGE) |  | Candidate · Amount prints “5627” · 2 - Main!A17548
| 2/R/37 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T1-GF-LV01 to 40A TP isolator for signage (ISO-T3-GF-SIGNAGE) |  | Candidate · Amount prints “5627” · 2 - Main!A17550
| 2/R/39 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T4-02-LL01 to DB-T4-02-GYM |  | Candidate · Amount prints “845” · 2 - Main!A17622
| 2/R/118 Item U — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Containment; including fixings, supports, hangers, fittings, accessories and all ancillary works as necessary — PVC pipe — Cable containment to Retail DB |  | Candidate · Amount prints “24876” · 2 - Main!A21586
| 2/R/141 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To BMS system |  | Candidate · Amount prints “16025” · 2 - Main!A22672
| 2/R/141 Item E — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Aircraft warning lighting at Tower 3 |  | Candidate · Amount prints “10685” · 2 - Main!A22674
| 2/R/141 Item F — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Aircraft warning lighting at Tower 4 |  | Candidate · Amount prints “10685” · 2 - Main!A22676
| 2/R/150 Item G — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — Graphic workstation with touch screen at Tower 4 FCC room |  | Candidate · Amount prints “26709” · 2 - Main!A23044
| 2/R/150 Item H — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — Master PC at Security room |  | Candidate · Amount prints “33385” · 2 - Main!A23046
| 2/R/161 Item L — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To ACS system |  | Candidate · Amount prints “25227” · 2 - Main!A23542
| 2/R/161 Item M — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To ANPR system |  | Candidate · Amount prints “25227” · 2 - Main!A23544
| 2/R/161 Item N — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To intercom system |  | Candidate · Amount prints “25227” · 2 - Main!A23546
| 2/R/161 Item P — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To key management system |  | Candidate · Amount prints “25227” · 2 - Main!A23548
| 2/R/162 Item A — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To video management system |  | Candidate · Amount prints “163592” · 2 - Main!A23561
| 2/R/168 Item D — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Builders work in connection (BWIC) with Electrical Engineering Installations — Allow for all BWIC with Electrical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “5601893” · 2 - Main!A23800
| 3/B/4 Item L — Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for planting edging |  | Candidate · Amount prints “66444” · 3 - Ext!A152
| 3/B/4 Item M — Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for maintenance of soft landscaping works during defect liability period for a period of one year after the date of Taking over Certificate and for complying with all the requirements |  | Candidate · Amount prints “244080” · 3 - Ext!A154
| 3/Q/7 Item A — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — IRRIGATION INSTALLATION — Irrigation controller; including foundation, 100mm diameter conduit for valve cables, 40mm diameter conduit for ground cable, copper earthing, electrical connection, supports and ancillary work as necessary — Allow for connection of irrigation pipe with existing infrastructure network including ancillary work as necessary |  | Candidate · Amount prints “84750” · 3 - Ext!A2698
| 3/Q/8 Item A — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere |  | Candidate · Amount prints “42375” · 3 - Ext!A2752
| 3/Q/8 Item J — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good |  | Candidate · Amount prints “73569” · 3 - Ext!A2770
| 3/Q/8 Item N — Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Builders work in connection (BWIC) with Mechanical Engineering Installations — Allow for all BWIC with Mechanical Engineering Installations where not included above or elsewhere |  | Candidate · Amount prints “76998” · 3 - Ext!A2780
| 3/R/2 Item A — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — Tie-in Connection — Tie-in connection to existing electrical line |  | Candidate · Amount prints “107365” · 3 - Ext!A2944
| 3/R/2 Item M — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — External Communication Services — Electrical point — External Communication Services — Allow for ICT installation (Data connection); including cables, conduits, terminations, fixings, supports, hangers, data outlets, accessories and all ancillary works as necessary |  | Candidate · Amount prints “127075” · 3 - Ext!A2986
| 3/R/3 Item P — Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant Specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations |  | Candidate · Amount prints “59885.95” · 3 - Ext!A3028
6 | Any Other Observations | • | Nothing else about this submission is outstanding. · Listed below; full detail on “PTC lines”, rows 967–1020 (54 lines) and row 1021 and rows 1022–1029 (8 lines).
| 2/Q/181 Item ADD — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Water Heater, WH-04 |  | Candidate · Amount prints “211200” · 2 - Main!A15348
| 2/Q/181 Item ADD — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Water Heater, EWH120 |  | Candidate · Amount prints “111044” · 2 - Main!A15349
| 2/Q/181 Item ADD — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Aluminium cladding for Chilled water pipe |  | Candidate · Amount prints “1052379” · 2 - Main!A15350
| 2/Q/181 Item ADD — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Aluminium Cladding (GI + Fire rated) |  | Candidate · Amount prints “4851207” · 2 - Main!A15351
| 2/Q/181 Item ADD — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Acoustic Lining |  | Candidate · Amount prints “1542368” · 2 - Main!A15352
| 2/Q/181 Item ADD — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Pre insulated duct work as per TQ Response |  | Candidate · Amount prints “6601975” · 2 - Main!A15353
| 2/Q/181 Item ADD — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Flow Meter 600mm |  | Candidate · Amount prints “100130” · 2 - Main!A15354
| 2/Q/181 Item ADD — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Flow Meter 200mm |  | Candidate · Amount prints “23482” · 2 - Main!A15355
| 2/Q/181 Item ADD — Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Secondary side valve Assembly for Main Heat exchanger |  | Candidate · Amount prints “508224” · 2 - Main!A15356
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Energy metering & monitoring system |  | Candidate · Amount prints “1645985” · 2 - Main!A23823
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Lift related Electrical Works |  | Candidate · Amount prints “358958” · 2 - Main!A23824
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Garbage & Linen Chute - Electrical Related Works |  | Candidate · Amount prints “254262” · 2 - Main!A23825
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — LPG System Related Electrical Works |  | Candidate · Amount prints “600935” · 2 - Main!A23826
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Control Panels for mechanical Equipments |  | Candidate · Amount prints “1148879” · 2 - Main!A23827
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-01-FAHU-T1 |  | Candidate · Amount prints “35416” · 2 - Main!A23830
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-01-FAHU-T3 |  | Candidate · Amount prints “39502” · 2 - Main!A23831
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T1-51-FAHU |  | Candidate · Amount prints “39502” · 2 - Main!A23832
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T3-55-FAHU |  | Candidate · Amount prints “49718” · 2 - Main!A23833
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T2-01-FAHU |  | Candidate · Amount prints “39502” · 2 - Main!A23834
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T2-29-FAHU |  | Candidate · Amount prints “38821” · 2 - Main!A23835
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T2-59-FAHU |  | Candidate · Amount prints “49718” · 2 - Main!A23836
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T4-01-FAHU |  | Candidate · Amount prints “36096” · 2 - Main!A23837
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T4-29-FAHU |  | Candidate · Amount prints “38821” · 2 - Main!A23838
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T4-55-FAHU |  | Candidate · Amount prints “46313” · 2 - Main!A23839
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 16mm² XLPE/SWA/PVC/CU +1C x 16mm² ECC |  | Candidate · Amount prints “6392” · 2 - Main!A23841
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 2 x 4C x 150mm² XLPE/SWA/PVC/CU + 2 x 1C x 70mm² ECC |  | Candidate · Amount prints “109326” · 2 - Main!A23842
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 2C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC |  | Candidate · Amount prints “900” · 2 - Main!A23844
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 6mm² XLPE/SWA/LSOH + 1C x 6mm² ECC |  | Candidate · Amount prints “18420” · 2 - Main!A23845
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC |  | Candidate · Amount prints “25872” · 2 - Main!A23846
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC |  | Candidate · Amount prints “15975” · 2 - Main!A23847
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 25mm² XLPE/SWA/LSOH + 1C x 16mm² ECC |  | Candidate · Amount prints “52574” · 2 - Main!A23848
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 35mm² XLPE/SWA/LSOH + 1C x 16mm² ECC |  | Candidate · Amount prints “7860” · 2 - Main!A23849
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 70mm² XLPE/SWA/LSOH + 1C x 35mm² ECC |  | Candidate · Amount prints “6840” · 2 - Main!A23850
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 6mm² XLPE/SWA/FR + 1C x6mm² ECC |  | Candidate · Amount prints “4488” · 2 - Main!A23866
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 10mm² XLPE/SWA/FR + 1C x10mm² ECC |  | Candidate · Amount prints “11900” · 2 - Main!A23867
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 16mm² XLPE/SWA/FR + 1C x 16mm² ECC |  | Candidate · Amount prints “7440” · 2 - Main!A23868
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 35mm² XLPE/SWA/FR + 1C x 16mm² ECC |  | Candidate · Amount prints “6084” · 2 - Main!A23869
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 50mm² XLPE/SWA/FR + 1C x 25mm² ECC |  | Candidate · Amount prints “61568” · 2 - Main!A23870
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 800A MCCB tap-off |  | Candidate · Amount prints “10592” · 2 - Main!A23872
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Fixed outdoor wall: Monitoring |  | Candidate · Amount prints “17070” · 2 - Main!A23873
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 40A TPN isolator, fire rated |  | Candidate · Amount prints “747” · 2 - Main!A23874
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 63A TPN isolator, fire rated |  | Candidate · Amount prints “85158” · 2 - Main!A23875
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 80A TPN isolator, fire rated |  | Candidate · Amount prints “39060” · 2 - Main!A23876
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 100A TPN isolator, fire rated |  | Candidate · Amount prints “11904” · 2 - Main!A23877
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 125A TPN isolator, fire rated |  | Candidate · Amount prints “78072” · 2 - Main!A23878
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — To key management system |  | Candidate · Amount prints “173604” · 2 - Main!A23880
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 150mm wide cable tray for Fire Alarm System |  | Candidate · Amount prints “476788” · 2 - Main!A23882
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 100mm x 50mm cable trunking for Emergency Lighting System |  | Candidate · Amount prints “550140” · 2 - Main!A23883
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 150mm wide cable tray for BMS System |  | Candidate · Amount prints “476788” · 2 - Main!A23884
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 150mm wide cable tray for Earthing System |  | Candidate · Amount prints “29978” · 2 - Main!A23885
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 100mm x 50mm dual compartment GI trunking for Light/Power |  | Candidate · Amount prints “667800” · 2 - Main!A23886
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Outdoor speaker landscape with ground stack,ref T5 |  | Candidate · Amount prints “7488” · 2 - Main!A23888
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Outdoor speaker landscape with ground stack,ref T5 |  | Candidate · Amount prints “69984” · 2 - Main!A23889
| 2/R/169 Item ADD — Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Allow for coordination of Transformer installation & Termination |  | Candidate · Amount prints “122331” · 2 - Main!A23891
| 2/L/2 Item — Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Supply and installation by Others: Contractor to allow for Co-ordination, attendance and builders work |  | Candidate · Amount prints “50850” · 2 - Main!A6515
| 2/E/11 Item ADD — Bill 2 — SECTION E - METALWORK (2/E) — GENERALLY — Primary Structural Steel (Non Fire Rated) to inaccessible areas on façade (Dummy Balconies) and Canopies Provisional Qty |  | Candidate · Amount prints “10609104.719999999” · 2 - Main!A1692
| 2/E/11 Item A — Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; UB 533 x 210 x 82 |  | Candidate · Amount prints “-123865.61000000003” · 2 - Main!A1715
| 2/E/11 Item B — Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; UC 203 x 203 x 60 |  | Candidate · Amount prints “100137.40000000001” · 2 - Main!A1716
| 2/E/11 Item C — Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; CHS 219 x 6.3 |  | Candidate · Amount prints “-6095.320000000005” · 2 - Main!A1717
| 2/E/11 Item D — Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; SHS 150 x 150 x 6.3 |  | Candidate · Amount prints “-9578.360000000004” · 2 - Main!A1718
| 2/E/11 Item E — Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; SHS 120 x 120 x 6.3 |  | Candidate · Amount prints “-653.0699999999981” · 2 - Main!A1719
| 2/E/11 Item D — Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Type AL-03; 3mm thick solid core aluminium cladding panels;PVDF coated; colour RAL 050 50 10 (Teakwood Brown - Light Brown, Matte finish, Smooth textured), including secondary support framing system and thermal insulation; water proofing where required; including all fixings, fittings, accessories and all ancillary works as per drawings and specifications — To ground floor and podium walls |  | Candidate · Amount prints “-72512” · 2 - Main!A1777
| 2/E/11 Item E — Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Type AL-03; 3mm thick solid core aluminium cladding panels;PVDF coated; colour RAL 050 50 10 (Teakwood Brown - Light Brown, Matte finish, Smooth textured), including secondary support framing system and thermal insulation; water proofing where required; including all fixings, fittings, accessories and all ancillary works as per drawings and specifications — To tower walls |  | Candidate · Amount prints “-615219” · 2 - Main!A1778
E | TENDER DOCUMENTS
1 | Instructions to Tenders | •
2 | the Conditions of Contract | •
3 | the Schedule of Project Requirements | •
4 | the Drawings | •
5 | the Specification | •
F | TENDER BOND
1 | Tender Bond Provided | •
G | TENDER ADDENDA / ADDITIONAL DOCUMENTATION
1 | Tender Addenda returned & stamped | •
2 | Additional Documentation (ITT Clause 8.1 (g))
| A1: Preliminary Programme | •
| A2: Organization Charts | •
| A3: Key Personnel | •
| A4: Relevant Experience | •
| A5: QA/QC Procedures | •
| A6: Insurance Company | •
| A7: Method Statement | •
| A8: Proposed Subcontractors | •
| A9: Health and Safety | •
| A10: Trade License | •
| A11: Confirmation of Site Visit | •
| A12: Joint Venture Details | •
| A13: Current Commitment | •
| A14: Proposal for Innovative Approaches for this Project | •
| A15: Tenderer’s Sustainability Initiatives/Practices | •
| A16: Value Engineering Suggestions | •
| A17: Tenderer’s Bank Details | •
H | VALUE ENGINEERING / SCHEDULE OF ALTERNATIVES
1 | Value Engineering Suggestions
J | FORM OF MAINTENANCE AGREEMENT
K | TENDERER'S QUALIFICATIONS / CLARIFICATIONS
L | ADDITIONAL ITEMS
1 | Approved banks for Performance and Advance Guarantees/Bonds
2 | Framework rates - Standardization
3 | European Kitchen Cabinet
4 | ID Finishes
M | REVISED OFFER (PTC-XX / BAFO / LAFO etc.)
1 | Revised Offer |  | Tenderer to submit their Revised Offer in accordance with the issued tender documents, Addenda and PTC-1 clarifications.

## PTC lines
Status | Category | Heading | Query | QS note | Scope | Raised | Reference | Item | Description | Qty | Unit | Rate | Amount as printed | Amount (numeric) | Source cell | Bidder's response
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/1-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Generally — Where any item, clause or sub-clause of the General Requirements has not been priced, it will be deemed that the value of such item, clause or sub-clause is included in the rates for measured items elsewhere in the Bills of Quantities. |  | Item |  | Included | 0 | GR1!A8
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/1-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Generally — The rates and prices in these Bills of Quantities are fixed for the duration of the Contract and shall not be subject to any adjustment in respect of rise or fall in the cost of labour, materials, plant, equipment, transport or any other matters affecting the cost of execution of the Contract. |  | Item |  | Included | 0 | GR1!A10
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/1-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Generally — References hereunder to the Schedule of Project Requirements (SOPR) are intended solely to direct the Contractor to the specific requirements of the Schedule of Project Requirements in respect of a particular item and do not in any way limit the scope of such item to the requirements of the Schedule of Project Requirements. |  | Item |  | Included | 0 | GR1!A12
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/2-F | F | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 6 Professional Indemnity insurance |  | Item |  | Included | 0 | GR1!A56
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/2-H | H | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 8 Plant and Contractor's Equipment Insurance |  | Item |  | Included | 0 | GR1!A60
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/2-J | J | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 9 Motor Vehicle Third Party and Passenger Liability Insurance |  | Item |  | Included | 0 | GR1!A62
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/3-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — The Contractor shall price hereunder any special requirements related to the specification clauses |  | Item |  | Included | 0 | GR1!A89
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/4-D | D | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 4 The Maintenance of existing services on, under or over the Site |  | Item |  | Excluded | 0 | GR1!A145
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/4-E | E | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 5 The Execution of the Works in the required specific order, sections or phases |  | Item |  | Included | 0 | GR1!A147
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/5-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — i. Establishment |  | Item |  | Included in A7.1 | 0 | GR1!A193
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/5-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — ii. Maintenance |  | Item |  | Included in A7.1 | 0 | GR1!A195
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/5-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — iii. Removal |  | Item |  | Included in A7.1 | 0 | GR1!A197
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/5-G | G | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — 5 Transport of workpeople |  | Item |  | Included in A5.1 | 0 | GR1!A205
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/9-G | G | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 3 Screens and guardrails — i. Establishment (Fixed Charges) |  | Item |  | Included in A4.1 | 0 | GR1!A405
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/9-H | H | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 3 Screens and guardrails — ii. Maintenance (Time Related Charges) |  | Item |  | Included in A4.1 | 0 | GR1!A407
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/9-J | J | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 3 Screens and guardrails — iii. Removal (Fixed Charges) |  | Item |  | Included in A4.1 | 0 | GR1!A409
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/11-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A8 - Temporary Works — A8.1 An item shall be given for temporary works including design, which shall include: — 3 Pumping |  | Item |  | Included in Site Works (Bill Nr 2) | 0 | GR1!A488
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/12-E | E | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 5 - Traffic regulations |  | Item |  | Included in A8.1 | 0 | GR1!A543
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/12-G | G | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 7 - Drying the Works |  | Item |  | Included in A7.1 | 0 | GR1!A547
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/12-H | H | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 8 - Control of noise and pollution |  | Item |  | Included in A7.1 | 0 | GR1!A549
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/12-J | J | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 9 - All Statutory obligations |  | Item |  | Included in A7.1 | 0 | GR1!A551
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/12-N | N | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 4 - Off site storage |  | Item |  | Included in A7.1 | 0 | GR1!A561
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/13-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 6 - Specialist Third Party Testing, Commissioning and Certification |  | Item |  | Included in A9.1 | 0 | GR1!A577
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/13-H | H | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 12 - Internet connection requirements on site |  | Item |  | Included in A7.1 | 0 | GR1!A591
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/13-J | J | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 13 - Precautions against Fire |  | Item |  | Included in A4.1 | 0 | GR1!A593
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/13-K | K | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 15 - Project Health, Safety, Environment and Security Guidelines |  | Item |  | Included in A4.1 | 0 | GR1!A595
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/13-L | L | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 16 - General cleaning and waste disposal during construction |  | Item |  | Included in A9.1 | 0 | GR1!A597
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/13-P | P | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 19 - Contract Spares/Attic stock |  | Item |  | Excluded | 0 | GR1!A603
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/13-Q | Q | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 20 - As-built drawings |  | Item |  | Included in BIM | 0 | GR1!A605
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/13-S | S | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 22 - Warranties |  | Item |  | Included | 0 | GR1!A609
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | GR1/15-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Additional Items — Any items that may not be covered elsewhere in the Bills of Quantities which the Tenderer deemed to be necessary in order to carry out the works in full compliance with the SOPR must be itemised and price below |  | Item |  | 0 | 0 | GR1!A674
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/B/3 Item A | A | Bill 2 — SECTION B - SITE WORKS (2/B) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Site Work in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A102
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/C/2 Item J | J | Bill 2 — SECTION C - CONCRETE WORKS (2/C) — POURED CONCRETE — Reinforced concrete; concrete grade C50/60 — Columns | 2734 | m3 |  | 0 | 0 | 2 - Main!A276
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/C/3 Item M | M | Bill 2 — SECTION C - CONCRETE WORKS (2/C) — POURED CONCRETE — Reinforced concrete; concrete grade C70/85 — Blade wall; 400mm thick | 1721 | m3 |  | 0 | 0 | 2 - Main!A343
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/C/6 Item B | B | Bill 2 — SECTION C - CONCRETE WORKS (2/C) — REINFORCEMENT — Reinforcing steel bars; high yield deformed; grade 60 — Planter wall | 8.88 | t |  | 0 | 0 | 2 - Main!A486
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/C/9 Item D | D | Bill 2 — SECTION C - CONCRETE WORKS (2/C) — PRESTRESSED CONCRETE — Post tensioning (PT) system; comprise of design, approvals including prestressing steel, anchorages, plates, ducts, grouts, protection, accessories and all ancillary works as necessary — PT system; to post tensioned slab | 1425.72 | t |  | Please refer ADD items | 0 | 2 - Main!A664
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/C/11 Item A | A | Bill 2 — SECTION C - CONCRETE WORKS (2/C) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Concrete Work in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A748
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/D/2 Item A | A | Bill 2 — SECTION D - MASONRY (2/D) — SUNDRIES — Joints in masonry; including fire resistant compressible joint filler, sealant, angle head restraints, telescopic, sleeved and/or debonded ties and the like — Dowelled control joints | 0 | Item |  | Included | 0 | 2 - Main!A1049
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/D/2 Item B | B | Bill 2 — SECTION D - MASONRY (2/D) — SUNDRIES — Joints in masonry; including fire resistant compressible joint filler, sealant, angle head restraints, telescopic, sleeved and/or debonded ties and the like — Dowelled control joints (RATE ONLY) |  | m |  | Rate Only | 0 | 2 - Main!A1051
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/D/2 Item C | C | Bill 2 — SECTION D - MASONRY (2/D) — SUNDRIES — Joints in masonry; including fire resistant compressible joint filler, sealant, angle head restraints, telescopic, sleeved and/or debonded ties and the like — Isolation joints | 0 | Item |  | Included | 0 | 2 - Main!A1053
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/D/2 Item D | D | Bill 2 — SECTION D - MASONRY (2/D) — SUNDRIES — Joints in masonry; including fire resistant compressible joint filler, sealant, angle head restraints, telescopic, sleeved and/or debonded ties and the like — Isolation joints (RATE ONLY) |  | m |  | Rate Only | 0 | 2 - Main!A1055
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/D/3 Item A | A | Bill 2 — SECTION D - MASONRY (2/D) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Masonry in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A1101
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/E/9 Item C | C | Bill 2 — SECTION E - METALWORK (2/E) — NON-STRUCTURAL METALWORK — Stainless steel ladders to water tanks; type AM-451; wall mounted stainless steel with safety cage; including finishes, frames, supports, fixings, accessories and all ancillary works as necessary — Type 2; size 960 x 690 x 10300mm high | 4 | Nr. |  | 0 | 0 | 2 - Main!A1610
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/E/11 Item A | A | Bill 2 — SECTION E - METALWORK (2/E) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Metalwork in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A1688
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/F/24 Item A | A | Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Woodwork in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A3001
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/F/24 Item ADD | ADD | Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Kitchen cabinets; to show kitchen; including countertop, forming of holes, frames, carcass, supports, front/back/side panels, doors, shelves, drawers, concealed light (measured separately), skirting, hardware, finishes, accessories and all ancillary works as necessary |  |  |  | 0 | 0 | 2 - Main!A3005
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/F/24 Item ADD | ADD | Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Vanity counters; including countertop, forming of holes, front/side panels, drawers, hardware, finishes, accessories and all ancillary works as necessary |  |  |  | 0 | 0 | 2 - Main!A3009
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/F/24 Item ADD | ADD | Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — To powder room |  |  |  | 0 | 0 | 2 - Main!A3011
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/F/24 Item ADD | ADD | Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Veneered shelves; including finishes, fixings, accessories and all ancillary works as necessary |  |  |  | 0 | 0 | 2 - Main!A3014
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/F/24 Item ADD | ADD | Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — To powder room |  |  |  | 0 | 0 | 2 - Main!A3016
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/F/24 Item ADD | ADD | Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Cabinets with veneered open shelf; including concealed light (measured separately), front/side panels, hardware, finishes, fixings, accessories and all ancillary works as necessary |  |  |  | 0 | 0 | 2 - Main!A3019
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/F/24 Item ADD | ADD | Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — To powder room |  |  |  | 0 | 0 | 2 - Main!A3021
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/F/24 Item ADD | ADD | Bill 2 — SECTION F - WOOD WORK (2/F) — GENERALLY — Wardrobes; comprising 18mm thick MDF shelving and glass shutter; including MDF backing, carcass, frames, supports, front/side/back panels, doors, shelves, drawers, concealed light (measured separately), hardware, finishes, accessories and all ancillary works as necessary |  |  |  | 0 | 0 | 2 - Main!A3025
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/G/4 Item A | A | Bill 2 — SECTION G - THERMAL AND MOISTURE PROTECTION (2/G) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Thermal and Moisture Protection in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A3438
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/H/16 Item A | A | Bill 2 — SECTION H - DOORS AND WINDOWS (2/H) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Doors and Windows in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A4262
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/H/16 Item ADD | ADD | Bill 2 — SECTION H - DOORS AND WINDOWS (2/H) — GENERALLY — Double glazed vision panel screen; Type V1; light smokey grey; Buildup: IGU; Outer lite: 8mm FT, Low E coating on surface #2 + 16mm AS + Inner lite: 6mm FT; U-value = 1.7W/m²K; Shading coefficient 0.25 max.; including frames, sub-frame, door system, finishes, joint, gasket, toggle clip, sealant, insulation, plaster board, fixings, fittings, accessories and all ancillary works as per drawings and specifications | 0 |  |  | 0 | 0 | 2 - Main!A4266
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/H/16 Item ADD | ADD | Bill 2 — SECTION H - DOORS AND WINDOWS (2/H) — GENERALLY — Double glazed vision panel screen; Type V2; light smokey grey; Buildup: IGU; Outer lite: 8mm FT, Low E coating on surface #2 + 16mm AS + Inner lite: 8mm FT; U-value = 1.7W/m²K; Shading coefficient 0.25 max.; including frames, sub-frame, door system, finishes, joint, gasket, toggle clip, sealant, insulation, plaster board, fixings, fittings, accessories and all ancillary works as per drawings and specifications | 0 |  |  | 0 | 0 | 2 - Main!A4273
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/H/16 Item ADD | ADD | Bill 2 — SECTION H - DOORS AND WINDOWS (2/H) — GENERALLY — Double glazed spandrel panel screen; Type S1; light smokey grey; Buildup: IGU; Outer lite: 8mm FT, Low E coating on surface #2 + 16mm AS + Inner lite: 6mm FT; including frames, sub-frame, door system, finishes, joint, gasket, toggle clip, sealant, plaster board, insulation, fixings, fittings, accessories and all ancillary works as per drawings and specifications | 0 |  |  | 0 | 0 | 2 - Main!A4279
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/J/9 Item B | B | Bill 2 — SECTION J - FINISHES (2/J) — CEILING FINISHES — Gypsum board tile ceiling system; including finishes, suspended metal support framing system, brackets, fastenings, accessories and all necessary fixings and accessories — Extra over for access panel | 0 | Item |  | Not Applicable | 0 | 2 - Main!A4854
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/J/9 Item D | D | Bill 2 — SECTION J - FINISHES (2/J) — CEILING FINISHES — Concealed grid aluminium tile ceiling system; demountable, perforated aluminium tiles; including finishes, suspended metal support framing system, brackets, fastenings, accessories and all necessary fixings and accessories — Extra over for access panel | 0 | Item |  | Not Applicable | 0 | 2 - Main!A4860
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/J/17 Item A | A | Bill 2 — SECTION J - FINISHES (2/J) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Finishes in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A5218
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/K/1 Item J | J | Bill 2 — SECTION K - ACCESSORIES (2/K) — TOILET ACCESSORIES — Sanitary accessories — Sanitary accessories; fixed to tiled or plastered concrete or blockwork; including connections, supports, sealants, accessories and all ancillary works as necessary — Common Areas — Type SAN-711; toilet paper holder | 9 | Nr. |  | 0 | 0 | 2 - Main!A5625
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/K/5 Item J | J | Bill 2 — SECTION K - ACCESSORIES (2/K) — SIGNAGE AND WAYFINDING — Signage and wayfinding; in English and Arabic text; including finishes, fixings, accessories and all ancillary works as necessary — Internal Signage — Retail sign by others | 6 | Nr. |  | By Others | 0 | 2 - Main!A5834
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/K/6 Item B | B | Bill 2 — SECTION K - ACCESSORIES (2/K) — PARKING ACCESSORIES — Kerbs; precast concrete fixed to floor slab; including fixings, finishes, accessories and all ancillary works as necessary — Type EXH-301; 100mm high | 2969 | m2 |  | 0 | 0 | 2 - Main!A5880
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/K/6 Item C | C | Bill 2 — SECTION K - ACCESSORIES (2/K) — PARKING ACCESSORIES — Kerbs; precast concrete fixed to floor slab; including fixings, finishes, accessories and all ancillary works as necessary — 150mm high; to ramps | 609 | m |  | 0 | 0 | 2 - Main!A5882
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/K/13 Item A | A | Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Accessories in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A6224
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/K/13 Item ADD | ADD | Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Tempered mirror; type GL-101; 6mm thick clear mirror with metal frame; including, backing, supports, finishes, accessories and all ancillary works as necessary | 0 |  |  | 0 | 0 | 2 - Main!A6231
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/K/13 Item ADD | ADD | Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Shower glass partition; fixed glass with doors; glass; 10mm thick; including ironmongery, fixings, accessories and all ancillary works as necessary | 0 |  |  | 0 | 0 | 2 - Main!A6239
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/K/13 Item ADD | ADD | Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Clear Glass | 0 |  |  | 0 | 0 | 2 - Main!A6240
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/K/13 Item ADD | ADD | Bill 2 — SECTION K - ACCESSORIES (2/K) — GENERALLY — Fluted Tinted Glass | 0 |  |  | 0 | 0 | 2 - Main!A6243
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/1 Item J | J | Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-111; freestanding cooker | 30 | Nr. |  | 0 | 0 | 2 - Main!A6479
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/1 Item K | K | Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-112; freestanding fridge | 30 | Nr. |  | 0 | 0 | 2 - Main!A6481
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/1 Item L | L | Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-113; freestanding freezer | 30 | Nr. |  | 0 | 0 | 2 - Main!A6483
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/1 Item M | M | Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-114; freestanding dishwasher | 30 | Nr. |  | 0 | 0 | 2 - Main!A6485
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/1 Item P | P | Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-116; coffee machine | 3 | Nr. |  | 0 | 0 | 2 - Main!A6489
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/1 Item Q | Q | Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-117; tv screen | 2 | Nr. |  | 0 | 0 | 2 - Main!A6491
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/1 Item R | R | Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-118; tv screen | 5 | Nr. |  | 0 | 0 | 2 - Main!A6493
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/1 Item S | S | Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-119; water dispenser | 8 | Nr. |  | 0 | 0 | 2 - Main!A6495
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/1 Item T | T | Bill 2 — SECTION L - EQUIPMENT (2/L) — WHITE GOODS — White goods; including accessories and all ancillary works as necessary — Type WG-120; tv screen | 2 | Nr. |  | 0 | 0 | 2 - Main!A6497
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item A | A | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-101; run 19" excite live | 7 | Nr. |  | 0 | 0 | 2 - Main!A6517
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item B | B | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-102; climb 16" excite live | 3 | Nr. |  | 0 | 0 | 2 - Main!A6519
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item C | C | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-103; synchro ar 16" excite live | 3 | Nr. |  | 0 | 0 | 2 - Main!A6521
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item D | D | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-104; technogym bike | 3 | Nr. |  | 0 | 0 | 2 - Main!A6523
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item E | E | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-105; skillrow | 3 | Nr. |  | 0 | 0 | 2 - Main!A6525
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item F | F | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-106; lower back fitness bench | 2 | Nr. |  | 0 | 0 | 2 - Main!A6527
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item G | G | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-107; yoga mat | 9 | Nr. |  | 0 | 0 | 2 - Main!A6529
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item H | H | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-108; crunch bench press | 3 | Nr. |  | 0 | 0 | 2 - Main!A6531
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item J | J | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-109; multi-power | 3 | Nr. |  | 0 | 0 | 2 - Main!A6533
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item K | K | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-110; adjustable bench | 5 | Nr. |  | 0 | 0 | 2 - Main!A6535
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item L | L | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-111; two tier dumbbell rack | 3 | Nr. |  | 0 | 0 | 2 - Main!A6537
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item M | M | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-112; dumbbells (10 pairs) | 3 | Nr. |  | 0 | 0 | 2 - Main!A6539
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item N | N | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-113; dual leg curl/leg extension selection 700 | 3 | Nr. |  | 0 | 0 | 2 - Main!A6541
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item P | P | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-114; lat machine selection 700 | 3 | Nr. |  | 0 | 0 | 2 - Main!A6543
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item Q | Q | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-115; shoulder press-selection 700 | 3 | Nr. |  | 0 | 0 | 2 - Main!A6545
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item R | R | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-116; chest press-selection 700 | 3 | Nr. |  | 0 | 0 | 2 - Main!A6547
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item S | S | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-117; skill tools storage | 3 | Nr. |  | 0 | 0 | 2 - Main!A6549
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item T | T | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-118; universe wall 2 virtual | 3 | Nr. |  | 0 | 0 | 2 - Main!A6551
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item U | U | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-119; vario 16" excite live | 1 | Nr. |  | 0 | 0 | 2 - Main!A6553
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item V | V | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-120; skill up | 1 | Nr. |  | 0 | 0 | 2 - Main!A6555
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item W | W | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-121; skillmill | 1 | Nr. |  | 0 | 0 | 2 - Main!A6557
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item X | X | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-122; skillrun unity 7000 | 1 | Nr. |  | 0 | 0 | 2 - Main!A6559
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item Y | Y | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-123; plyobox | 1 | Nr. |  | 0 | 0 | 2 - Main!A6561
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item Z | Z | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-124; punching bag | 1 | Nr. |  | 0 | 0 | 2 - Main!A6563
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/2 Item AA | AA | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Type EQ-125; leg press selection 700 | 1 | Nr. |  | 0 | 0 | 2 - Main!A6565
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/3 Item C | C | Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — BMU accessories; including fixing materials, signage, supports, brackets, accessories and all ancillary works as necessary — Galvanized mild steel running track; including galvanized steel base plates, clip ears, stainless steel A4/80 u-bolts, high-strength grout, fixings; complete — BMU tracks at 4000mm center to center | 183 | m |  | Included | 0 | 2 - Main!A6593
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/5 Item C | C | Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — To tower 1 | 0 | Item |  | 0 | 0 | 2 - Main!A6664
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/5 Item D | D | Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — To tower 2 | 0 | Item |  | 0 | 0 | 2 - Main!A6666
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/5 Item E | E | Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — To tower 3 | 0 | Item |  | 0 | 0 | 2 - Main!A6668
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/5 Item F | F | Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — To tower 4 | 0 | Item |  | 0 | 0 | 2 - Main!A6670
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/5 Item G | G | Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — Allow to mobile elevated work platform (MEWP) including accessories and all ancillary works as necessary | 0 | Item |  | 0 | 0 | 2 - Main!A6672
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/L/6 Item A | A | Bill 2 — SECTION L - EQUIPMENT (2/L) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Equipment in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A6688
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item A | A | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-101; coffee table | 4 | Nr. |  | 0 | 0 | 2 - Main!A6806
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item B | B | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-102; side table | 6 | Nr. |  | 0 | 0 | 2 - Main!A6808
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item C | C | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-103; side table | 4 | Nr. |  | 0 | 0 | 2 - Main!A6810
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item D | D | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-104; console behind sofa | 4 | Nr. |  | 0 | 0 | 2 - Main!A6812
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item E | E | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-105; console | 6 | Nr. |  | 0 | 0 | 2 - Main!A6814
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item F | F | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-106; side table | 6 | Nr. |  | 0 | 0 | 2 - Main!A6816
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item G | G | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-107; table | 4 | Nr. |  | 0 | 0 | 2 - Main!A6818
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item H | H | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-108; console | 2 | Nr. |  | 0 | 0 | 2 - Main!A6820
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item J | J | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-109; coffee table | 1 | Nr. |  | 0 | 0 | 2 - Main!A6822
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item K | K | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-110; side table vintage bronze | 8 | Nr. |  | 0 | 0 | 2 - Main!A6824
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item L | L | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-111; side table | 4 | Nr. |  | 0 | 0 | 2 - Main!A6826
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item M | M | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-112; side table | 5 | Nr. |  | 0 | 0 | 2 - Main!A6828
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item N | N | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-113; communal table travertine | 1 | Nr. |  | 0 | 0 | 2 - Main!A6830
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item P | P | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-114; coffee table | 1 | Nr. |  | 0 | 0 | 2 - Main!A6832
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item Q | Q | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-115; coffee table | 1 | Nr. |  | 0 | 0 | 2 - Main!A6834
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item R | R | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-116; armchairs side table | 1 | Nr. |  | 0 | 0 | 2 - Main!A6836
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item S | S | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-117; sofa side table | 2 | Nr. |  | 0 | 0 | 2 - Main!A6838
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item T | T | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-118; coffee table | 4 | Nr. |  | 0 | 0 | 2 - Main!A6840
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item U | U | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-119; coffee table | 8 | Nr. |  | 0 | 0 | 2 - Main!A6842
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item V | V | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-120; dining table | 2 | Nr. |  | 0 | 0 | 2 - Main!A6844
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item W | W | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-121; console | 2 | Nr. |  | 0 | 0 | 2 - Main!A6846
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/1 Item X | X | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-122; gaming area side table | 12 | Nr. |  | 0 | 0 | 2 - Main!A6848
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item A | A | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-123; kids table | 4 | Nr. |  | 0 | 0 | 2 - Main!A6858
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item B | B | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-124; pool table | 1 | Nr. |  | 0 | 0 | 2 - Main!A6860
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item C | C | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-125; foosball table | 1 | Nr. |  | 0 | 0 | 2 - Main!A6862
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item D | D | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Case goods; including accessories and all ancillary works as necessary — Type CG-126; shower bench | 4 | Nr. |  | 0 | 0 | 2 - Main!A6864
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item E | E | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-101; seating area loose rug | 4 | Nr. |  | 0 | 0 | 2 - Main!A6868
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item F | F | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-102; big table loose rug | 4 | Nr. |  | 0 | 0 | 2 - Main!A6870
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item G | G | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-103; rectangular loose rug | 5 | Nr. |  | 0 | 0 | 2 - Main!A6872
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item H | H | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-104; rectangular loose rug | 1 | Nr. |  | 0 | 0 | 2 - Main!A6874
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item J | J | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-105; loose rug | 2 | Nr. |  | 0 | 0 | 2 - Main!A6876
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item K | K | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-106; loose rug | 2 | Nr. |  | 0 | 0 | 2 - Main!A6878
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item L | L | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Loose rugs; including accessories and all ancillary works as necessary — Type LR-107; loose rug | 2 | Nr. |  | 0 | 0 | 2 - Main!A6880
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item M | M | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-101; sheer curtains | 8 | Nr. |  | 0 | 0 | 2 - Main!A6884
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item N | N | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-102; plant pots | 10 | Nr. |  | 0 | 0 | 2 - Main!A6886
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item P | P | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-103; lift lobby entrance | 4 | Nr. |  | 0 | 0 | 2 - Main!A6888
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item Q | Q | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-104; artwork behind sofa | 2 | Nr. |  | 0 | 0 | 2 - Main!A6890
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item R | R | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-105; artwork above console- hand painted art painting | 4 | Nr. |  | 0 | 0 | 2 - Main!A6892
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item S | S | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-106; artwork at table area | 2 | Nr. |  | 0 | 0 | 2 - Main!A6894
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item T | T | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-107; artwork | 4 | Nr. |  | 0 | 0 | 2 - Main!A6896
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item U | U | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-108; entrance lobby corridor artwork | 8 | Nr. |  | 0 | 0 | 2 - Main!A6898
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item V | V | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-109; roller blinds | 37 | m |  | 0 | 0 | 2 - Main!A6900
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/2 Item W | W | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-110; accessories | 2 | Nr. |  | 0 | 0 | 2 - Main!A6902
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item A | A | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-111; artwork | 215 | Nr. |  | 0 | 0 | 2 - Main!A6912
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item B | B | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-112; artwork | 870 | Nr. |  | 0 | 0 | 2 - Main!A6914
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item C | C | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-113; curtains manual | 30 | m |  | 0 | 0 | 2 - Main!A6916
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item D | D | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-114; plant pots | 6 | Nr. |  | 0 | 0 | 2 - Main!A6918
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item E | E | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-115; sheer curtains-seating area and table area only (deleted) | 4 | Nr. |  | 0 | 0 | 2 - Main!A6920
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item F | F | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-116; plant pots | 14 | Nr. |  | 0 | 0 | 2 - Main!A6922
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item G | G | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-117; artwork | 4 | Nr. |  | 0 | 0 | 2 - Main!A6924
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item H | H | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-118; artwork | 2 | Nr. |  | 0 | 0 | 2 - Main!A6926
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item J | J | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-119; artwork | 2 | Nr. |  | 0 | 0 | 2 - Main!A6928
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item K | K | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-120; artwork | 2 | Nr. |  | 0 | 0 | 2 - Main!A6930
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item L | L | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-121; artwork | 4 | Nr. |  | 0 | 0 | 2 - Main!A6932
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item M | M | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-122; artwork | 4 | Nr. |  | 0 | 0 | 2 - Main!A6934
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item N | N | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-123; artwork | 2 | Nr. |  | 0 | 0 | 2 - Main!A6936
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item P | P | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-124; artwork | 2 | Nr. |  | 0 | 0 | 2 - Main!A6938
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item Q | Q | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-125; artwork | 4 | Nr. |  | 0 | 0 | 2 - Main!A6940
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item R | R | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-126; artwork | 2 | Nr. |  | 0 | 0 | 2 - Main!A6942
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item S | S | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-127; printed artwork | 2 | Nr. |  | 0 | 0 | 2 - Main!A6944
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item T | T | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-128; printed artwork | 5 | Nr. |  | 0 | 0 | 2 - Main!A6946
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item U | U | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-129; artwork | 1 | Nr. |  | 0 | 0 | 2 - Main!A6948
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item V | V | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-130; artwork | 1 | Nr. |  | 0 | 0 | 2 - Main!A6950
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item W | W | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-131; printed artwork | 1 | Nr. |  | 0 | 0 | 2 - Main!A6952
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item X | X | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-132; artwork | 1 | Nr. |  | 0 | 0 | 2 - Main!A6954
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item Y | Y | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-133; artwork | 1 | Nr. |  | 0 | 0 | 2 - Main!A6956
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/3 Item Z | Z | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-134; artwork | 1 | Nr. |  | 0 | 0 | 2 - Main!A6958
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item A | A | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-135; artwork | 1 | Nr. |  | 0 | 0 | 2 - Main!A6968
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item B | B | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-136; artwork | 1 | Nr. |  | 0 | 0 | 2 - Main!A6970
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item C | C | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-137; mirror | 4 | Nr. |  | 0 | 0 | 2 - Main!A6972
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item D | D | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Miscellaneous; including accessories and all ancillary works as necessary — Type MI-138; artwork | 2 | Nr. |  | 0 | 0 | 2 - Main!A6974
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item E | E | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-101; sofa | 4 | Nr. |  | 0 | 0 | 2 - Main!A6978
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item F | F | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-102; armchair | 8 | Nr. |  | 0 | 0 | 2 - Main!A6980
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item G | G | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-103; bench | 4 | Nr. |  | 0 | 0 | 2 - Main!A6982
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item H | H | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-104; armchair | 12 | Nr. |  | 0 | 0 | 2 - Main!A6984
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item J | J | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-105; dining chair | 32 | Nr. |  | 0 | 0 | 2 - Main!A6986
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item K | K | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-106; sofa | 1 | Nr. |  | 0 | 0 | 2 - Main!A6988
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item L | L | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-107; lounge chair | 1 | Nr. |  | 0 | 0 | 2 - Main!A6990
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item M | M | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-108; pouf-leather | 6 | Nr. |  | 0 | 0 | 2 - Main!A6992
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item N | N | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-109; armchair-leather | 8 | Nr. |  | 0 | 0 | 2 - Main!A6994
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item P | P | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-110; dining chair | 30 | Nr. |  | 0 | 0 | 2 - Main!A6996
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item Q | Q | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-111; bench seat | 1 | Nr. |  | 0 | 0 | 2 - Main!A6998
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item R | R | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-112; ottoman | 2 | Nr. |  | 0 | 0 | 2 - Main!A7000
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item S | S | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-113; armchair & pouf | 7 | Nr. |  | 0 | 0 | 2 - Main!A7002
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item T | T | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-114; sofa | 3 | Nr. |  | 0 | 0 | 2 - Main!A7004
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item U | U | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-115; armchair | 8 | Nr. |  | 0 | 0 | 2 - Main!A7006
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/4 Item V | V | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-116; ottoman | 2 | Nr. |  | 0 | 0 | 2 - Main!A7008
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item A | A | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-117; armchair | 8 | Nr. |  | 0 | 0 | 2 - Main!A7023
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item B | B | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-118; sofa in joinery | 4 | Nr. |  | 0 | 0 | 2 - Main!A7025
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item C | C | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-119; sofa in small seating | 4 | Nr. |  | 0 | 0 | 2 - Main!A7027
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item D | D | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-120; kids chair 1 | 12 | Nr. |  | 0 | 0 | 2 - Main!A7029
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item E | E | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-121; reception chair | 4 | Nr. |  | 0 | 0 | 2 - Main!A7031
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item F | F | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Upholster goods; including accessories and all ancillary works as necessary — Type SG-122; built in bench | 1 | Nr. |  | 0 | 0 | 2 - Main!A7033
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item H | H | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Chairs; to guard rooms | 8 | Nr. |  | 0 | 0 | 2 - Main!A7041
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item J | J | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Chairs; to meeting room | 10 | Nr. |  | 0 | 0 | 2 - Main!A7043
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item K | K | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Chairs; to security manager room | 3 | Nr. |  | 0 | 0 | 2 - Main!A7045
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item L | L | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Chairs; to staff pantry | 10 | Nr. |  | 0 | 0 | 2 - Main!A7047
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item M | M | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Table; size 900 x 900mm wide; to staff pantry | 3 | Nr. |  | 0 | 0 | 2 - Main!A7049
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item N | N | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Table; size 1500 x 600mm wide; to security manager room | 1 | Nr. |  | 0 | 0 | 2 - Main!A7051
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/5 Item P | P | Bill 2 — SECTION M - FURNISHING (2/M) — LOOSE FF&E — Chairs and tables; including finishes, accessories and all ancillary works as necessary — Table; size 3600 x 1500mm wide; to meeting room | 1 | Nr. |  | 0 | 0 | 2 - Main!A7053
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/M/6 Item A | A | Bill 2 — SECTION M - FURNISHING (2/M) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Furnishings in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A7075
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/5 Item A | A | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — SUNDRIES — Allow for providing shop drawings, as built drawings and material submittal approvals | 0 | Item |  | Included | 0 | 2 - Main!A7390
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/5 Item B | B | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — SUNDRIES — Allow for providing catalogues, operation and maintenance manuals | 0 | Item |  | Included | 0 | 2 - Main!A7392
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/5 Item C | C | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — SUNDRIES — Allow for labeling, tagging of equipment with their related control panel and components as specified | 0 | Item |  | Included | 0 | 2 - Main!A7394
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/5 Item D | D | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — SUNDRIES — Allow for testing and commissioning the complete installation | 0 | Item |  | Included | 0 | 2 - Main!A7396
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/6 Item A | A | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow for cutting or forming all holes, mortices, chases and the like and making good finishes for conveying systems | 0 | Item |  | Included | 0 | 2 - Main!A7429
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/6 Item B | B | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow for fixing all sleeves, frames and built-in firestop system and making good finishes for conveying systems | 0 | Item |  | Included | 0 | 2 - Main!A7431
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/6 Item C | C | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow for firestopping for all holes and making good finishes for conveying systems | 0 | Item |  | Included | 0 | 2 - Main!A7433
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/6 Item D | D | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow for building in or cutting and pinning brackets or the like and making good finishes for conveying systems | 0 | Item |  | Included | 0 | 2 - Main!A7435
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/6 Item E | E | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — WORK INCIDENTAL TO CONVEYING SYSTEM AND BWIC — Generally — Allow connection to elevator monitoring system (EMS) at BMS room | 0 | Item |  | Included | 0 | 2 - Main!A7437
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/6 Item F | F | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — BWIC — Builders work in connection with conveying systems | 0 | Item |  | Included | 0 | 2 - Main!A7441
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/P/7 Item A | A | Bill 2 — SECTION P - CONVEYING SYSTEMS (2/P) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Conveying Systems in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A7485
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/4 Item H | H | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere | 0 | Item |  | Included | 0 | 2 - Main!A7777
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/4 Item J | J | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for all identification including painting, marking and labelling | 0 | Item |  | Included | 0 | 2 - Main!A7779
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/4 Item L | L | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installation | 0 | Item |  | Included | 0 | 2 - Main!A7783
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/4 Item M | M | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for providing spares for the Mechanical Engineering Installation | 0 | Item |  | 0 | 0 | 2 - Main!A7785
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/5 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like | 0 | Item |  | Included | 0 | 2 - Main!A7808
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/5 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades | 0 | Item |  | Included | 0 | 2 - Main!A7812
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/5 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for liaison with obtaining approvals and attendance on approved Authorities, other statutory bodies and service providers as required | 0 | Item |  | Included | 0 | 2 - Main!A7814
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/5 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good | 0 | Item |  | Included | 0 | 2 - Main!A7816
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/5 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good | 0 | Item |  | Included | 0 | 2 - Main!A7818
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/5 Item F | F | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Mechanical Engineering Installations | 0 | Item |  | Included | 0 | 2 - Main!A7820
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/5 Item G | G | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work to the Mechanical Engineering Installations where not included above or elsewhere | 0 | Item |  | Included | 0 | 2 - Main!A7822
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/8 Item M | M | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — U-trap; size 110mm diameter | 36 | Nr. |  | Included | 0 | 2 - Main!A7972
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/8 Item N | N | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — U-trap; size 160mm diameter | 7 | Nr. |  | Included | 0 | 2 - Main!A7974
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/8 Item P | P | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 110mm diameter | 302 | Nr. |  | Included | 0 | 2 - Main!A7976
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/8 Item Q | Q | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 160mm diameter | 157 | Nr. |  | Included | 0 | 2 - Main!A7978
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/8 Item R | R | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 200mm diameter | 88 | Nr. |  | Included | 0 | 2 - Main!A7980
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/9 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 250mm diameter | 7 | Nr. |  | Included | 0 | 2 - Main!A7995
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/9 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Accessories; including fixings, brackets, supports and all ancillary works as necessary — Clean out; 350mm diameter | 13 | Nr. |  | Included | 0 | 2 - Main!A7997
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/10 Item P | P | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 32mm diameter | 50 | Nr. |  | Included | 0 | 2 - Main!A8070
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/10 Item Q | Q | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 50mm diameter | 3 | Nr. |  | Included | 0 | 2 - Main!A8072
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/10 Item R | R | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 82mm diameter | 14 | Nr. |  | Included | 0 | 2 - Main!A8074
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/10 Item S | S | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 110mm diameter | 13 | Nr. |  | Included | 0 | 2 - Main!A8076
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/11 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 160mm diameter | 75 | Nr. |  | Included | 0 | 2 - Main!A8091
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/12 Item S | S | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — U-trap; size 110mm diameter | 16 | Nr. |  | Included | 0 | 2 - Main!A8178
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — U-trap; size 160mm diameter | 2 | Nr. |  | Included | 0 | 2 - Main!A8193
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 32mm diameter | 2478 | Nr. |  | Included | 0 | 2 - Main!A8195
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 50mm diameter | 8 | Nr. |  | Included | 0 | 2 - Main!A8197
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 82mm diameter | 16 | Nr. |  | Included | 0 | 2 - Main!A8199
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 110mm diameter | 10510 | Nr. |  | Included | 0 | 2 - Main!A8201
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item F | F | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 160mm diameter | 237 | Nr. |  | Included | 0 | 2 - Main!A8203
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item G | G | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 200mm diameter | 129 | Nr. |  | Included | 0 | 2 - Main!A8205
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item H | H | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 250mm diameter | 39 | Nr. |  | Included | 0 | 2 - Main!A8207
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item J | J | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 300mm diameter | 9 | Nr. |  | Included | 0 | 2 - Main!A8209
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item K | K | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 350mm diameter | 1 | Nr. |  | Included | 0 | 2 - Main!A8211
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/13 Item L | L | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — DRAINAGE INSTALLATION — Pipe accessories; complete including all fixings, supports and all ancillary works as necessary — Clean out; 450mm diameter | 10 | Nr. |  | Included | 0 | 2 - Main!A8213
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/28 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To ground and podium | 0 | item |  | Included | 0 | 2 - Main!A8852
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/28 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To tower 1 | 0 | item |  | Included | 0 | 2 - Main!A8854
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/28 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To tower 2 | 0 | item |  | Included | 0 | 2 - Main!A8856
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/28 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To tower 3 | 0 | item |  | Included | 0 | 2 - Main!A8858
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/28 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WATER INSTALLATION — Allow to advance metering infrastructure (AMI); including PVC and G.I. junction box, PVC and G.I. conduits, copper pipe connection, fixings, hangers, brackets, accessories and all ancillary works as necessary — To tower 4 | 0 | item |  | Included | 0 | 2 - Main!A8860
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/31 Item Q | Q | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Accessories; including hangers, supports, fixings and all ancillary works as necessary — Deluge valve; 50mm diameter | 1 | Nr. |  | Included | 0 | 2 - Main!A9017
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/31 Item R | R | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Accessories; including hangers, supports, fixings and all ancillary works as necessary — Foam tank | 1 | Nr. |  | Included | 0 | 2 - Main!A9019
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/34 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-BF-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 1000gpm and duty pump head of 11bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9123
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/34 Item F | F | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-P2-FF-DP-02, Diesel engine driven fire pump; with estimated flow rate of 1000gpm and duty pump head of 18.6bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9125
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/34 Item G | G | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T1-29F-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 16.2bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9127
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/34 Item H | H | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 14.3bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9129
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/34 Item J | J | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-48F-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 13.6bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9131
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/34 Item K | K | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-DP-01,Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 17.8bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9133
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/35 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-DP-01, Diesel engine driven fire pump; with estimated flow rate of 750gpm and duty pump head of 17.8bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9147
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/35 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-BF-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 11bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9149
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/35 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-P2-FF-JP-02, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 18.6bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9151
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/35 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 16.2bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9153
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/35 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-29F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 14.3bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9155
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/35 Item F | F | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T2-48F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 13.6bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9157
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/35 Item G | G | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T3-29F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 17.6bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9159
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/35 Item H | H | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting pump; including control panels, gages, air vent, flexible connections, strainers, valves, wiring, supports, concrete base, vibration isolators, BMS connection, connection to power supply and all ancillary works as necessary — T4-29F-FF-JP-01, Jockey pump; with estimated flow rate of 10gpm and duty pump head of 17.8bar | 1 | Nr. |  | Included | 0 | 2 - Main!A9161
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/35 Item J | J | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Fire fighting diesel tank; including supports, concrete base and all ancillary works as necessary — Diesel tank; 350US gallon | 2 | Nr. |  | Included | 0 | 2 - Main!A9165
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/37 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Clean agent extinguishing system including hangers, supports, fixings, clean agent pipes, fittings, accessories and all ancillary works as necessary — Tower 1 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A9229
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/37 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Clean agent extinguishing system including hangers, supports, fixings, clean agent pipes, fittings, accessories and all ancillary works as necessary — Tower 2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A9231
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/37 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Clean agent extinguishing system including hangers, supports, fixings, clean agent pipes, fittings, accessories and all ancillary works as necessary — Tower 3 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A9233
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/37 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — FIRE PROTECTION SYSTEM — Clean agent extinguishing system including hangers, supports, fixings, clean agent pipes, fittings, accessories and all ancillary works as necessary — Tower 4 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A9235
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/41 Item R | R | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — HVAC INSTALLATION — Valve package assembly; including gate valves, binder test port, strainer, 2 port modulating PICV valve, union, reducers, MAV, bypass pipe with valve, fixings; complete — 20mm diameter | 3930 | Nr. |  | Duplicated item, Refer FCU Connection Assembly | 0 | 2 - Main!A9431
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/41 Item S | S | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — HVAC INSTALLATION — Valve package assembly; including gate valves, binder test port, strainer, 2 port modulating PICV valve, union, reducers, MAV, bypass pipe with valve, fixings; complete — 25mm diameter | 99 | Nr. |  | Duplicated item, Refer FCU Connection Assembly | 0 | 2 - Main!A9433
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/43 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — HVAC INSTALLATION — Plant and equipment including hangers, supports, fixings, pipe connections, wire connections, flexible connections and all ancillary works as necessary — Heat exchanger unit complete with valves, dosing pumpset, sensor, controllers and all ancillary works as necessary — T2-GF-PHEX 01 to 06; plate heat exchanger (6 duty); with cold side flow of 77.6l/s and hot side flow of 77.6l/s, design pressure of 20bar and maximum fluid pressure drop of 40kPa | 1 | Nr. |  | N/A, Since MEP scope start from Secondary side of Heat exchanger as per TA-05, Item no. 5.22 | 0 | 2 - Main!A9509
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/173 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Soft copper pipe tubes to BS EN 1057 tableX; including fittings, perforated covers, hangers, supports, fixings, sleeves, accessories and all ancillary works as necessary — 15mm diameter | 13522 | m |  | Included | 0 | 2 - Main!A15048
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 20mm diameter | 1209 | m |  | Included | 0 | 2 - Main!A15072
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 25mm diameter | 1130 | m |  | Included | 0 | 2 - Main!A15074
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 32mm diameter | 2490 | m |  | Included | 0 | 2 - Main!A15076
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 40mm diameter | 402 | m |  | Included | 0 | 2 - Main!A15078
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 50mm diameter | 1048 | m |  | Included | 0 | 2 - Main!A15080
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item F | F | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, containment pipe, pipe in pipe gas detectors, socket, sensors, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 50mm diameter | 271 | m |  | Included | 0 | 2 - Main!A15084
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item G | G | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, containment pipe, pipe in pipe gas detectors, socket, sensors, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 80mm diameter | 141 | m |  | Included | 0 | 2 - Main!A15086
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item H | H | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 including fittings, containment pipe, pipe in pipe gas detectors, socket, sensors, hangers, supports, clamps, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 100mm diameter | 50 | m |  | Included | 0 | 2 - Main!A15088
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item J | J | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Fire rated duct to LPG pipe — To LPG pipe in various sizes; 2hr. fire rating | 174 | m |  | Included | 0 | 2 - Main!A15092
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/174 Item K | K | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 32mm diameter | 55 | m |  | Included | 0 | 2 - Main!A15096
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 40mm diameter | 19 | m |  | Included | 0 | 2 - Main!A15114
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 50mm diameter | 102 | m |  | Included | 0 | 2 - Main!A15116
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 65mm diameter | 96 | m |  | Included | 0 | 2 - Main!A15118
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 80mm diameter | 26 | m |  | Included | 0 | 2 - Main!A15120
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Seamless carbon steel pipe to ASTM A53 Gr.B schedule 40 to roofdeck; including fittings, 200x300x200mm concrete block, G.I. pipe clamp, unifix assembly, hangers, supports, fixings, sleeves, couplers, accessories and all ancillary works as necessary — 100mm diameter | 2 | m |  | Included | 0 | 2 - Main!A15122
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item F | F | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Gas detectors | 1796 | Nr. |  | Included | 0 | 2 - Main!A15126
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item J | J | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Isolation valve; 32mm diameter | 15 | Nr. |  | Included | 0 | 2 - Main!A15132
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item K | K | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Isolation valve; 50mm diameter | 12 | Nr. |  | Included | 0 | 2 - Main!A15134
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item L | L | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Isolation valve; 65mm diameter | 2 | Nr. |  | Included | 0 | 2 - Main!A15136
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item M | M | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Accessories including all hangers, supports, fixings, pipe connections and ancillary work as necessary — Isolation valve; 80mm diameter | 3 | Nr. |  | Included | 0 | 2 - Main!A15138
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/175 Item P | P | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Kitchen gas pipe assembly; including isolating valve, second stage regulator, solenoid valve, automatic shut-off valve, wirings, connections, fixings, accessories and all ancillary works as necessary — 20mm diameter | 1723 | Nr. |  | Included | 0 | 2 - Main!A15146
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/176 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To ground and podium | 0 | Item |  | Included | 0 | 2 - Main!A15166
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/176 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To tower 1 | 0 | Item |  | Included | 0 | 2 - Main!A15168
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/176 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To tower 2 | 0 | Item |  | Included | 0 | 2 - Main!A15170
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/176 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To tower 3 | 0 | Item |  | Included | 0 | 2 - Main!A15172
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/176 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — LPG INSTALLATION — Allow to gas leak detection system; including gas leak detection control panel, interfacing to gas detectors, sound flashers, wirings and cables, conduits, connection to fire alarm system, fixings, hangers, supports, accessories and all ancillary works as necessary — To tower 4 | 0 | Item |  | Included | 0 | 2 - Main!A15174
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/177 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for all connections to existing services mains | 0 | Item |  | Included within plot | 0 | 2 - Main!A15212
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/177 Item H | H | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for providing spares for Mechanical Engineering Installations | 0 | Item |  | 0 | 0 | 2 - Main!A15226
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/179 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for marking the positions of and cutting or forming holes, mortices, chases or the like and all making good | 0 | Item |  | Included | 0 | 2 - Main!A15286
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/179 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for supplying and fixing all sleeves, frames and built-in fire stoppers for building into concrete structures and masonry walls | 0 | Item |  | Included | 0 | 2 - Main!A15288
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/179 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good | 0 | Item |  | Included | 0 | 2 - Main!A15290
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/179 Item J | J | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for all decorative painting including removing protective coatings or wrappings and cleaning and polishing exposed surfaces for Mechanical installations. | 0 | Item |  | Included | 0 | 2 - Main!A15298
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/180 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work to the Mechanical Engineering Installations where not included above or elsewhere | 0 | Item |  | Included | 0 | 2 - Main!A15316
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/Q/181 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Mechanical Engineering Installations in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A15344
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/11 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 6mm² XLPE/SWA/LSOH + 1C x 6mm² ECC — From SMDB-T2-GF-LV to 20A TP isolator for CHEMI DOZ UNIT - GF | 35 | m |  | Not Applicable | 0 | 2 - Main!A16334
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/12 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 6mm² XLPE/SWA/LSOH + 1C x 6mm² ECC — From SMDB-T2-GF-LV to 20A TP isolator for DOZ CIRCULATION PUMP - GF | 34 | m |  | Not Applicable | 0 | 2 - Main!A16349
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/16 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC — From SMDB-T1-03-LL01 to DB-T1-03-EXT | 82 | m |  | Not Applicable | 0 | 2 - Main!A16578
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/43 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 25mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T3-55-LL01 to DB-T3-55-LL01 | 16 | m |  | Not Applicable | 0 | 2 - Main!A17799
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/44 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 50mm² XLPE/SWA/LSOH + 1C x 25mm² ECC — From SMDB-T1-B2-LL01 to MCC-T1-B2-LL01 | 13 | m |  | Not Applicable | 0 | 2 - Main!A17846
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/45 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 70mm² XLPE/SWA/LSOH + 1C x 35mm² ECC — From 160A MCCB tap-off (SMDB-T3-54-BR01) to SMDB-T3-54-BR01 | 28 | m |  | Not Applicable | 0 | 2 - Main!A17888
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/46 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 70mm² XLPE/SWA/LSOH + 1C x 35mm² ECC — From 160A MCCB tap-off to SMDB-T4-54-BR01 | 28 | m |  | Not Applicable | 0 | 2 - Main!A17907
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/49 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 6mm² XLPE/SWA/FR + 1C x 6mm² ECC — From ESMDB-T2-GF-LV-01 to 32A TP isolator for ISO-TF-GF-UPS1 | 32 | m |  | Not Applicable | 0 | 2 - Main!A18058
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/50 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 6mm² XLPE/SWA/FR + 1C x 6mm² ECC — From ESMDB-T2-GF-LV-01 to 32A TP isolator for ISO-TF-GF-UPS1 (MAINTENANCE BYPASS) | 32 | m |  | Not Applicable | 0 | 2 - Main!A18069
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/50 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 6mm² XLPE/SWA/FR + 1C x 6mm² ECC — From ESMDB-T2-GF-LV-01 to 32A TP isolator for ISO-TF-GF-UPS1 (MAINTENANCE BYPASS) | 32 | m |  | Not Applicable | 0 | 2 - Main!A18071
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/59 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 25mm² XLPE/SWA/FR + 1C x 16mm² ECC — From EMCC-T2-GF-FAN-02 to 20A TP isolator for T2-GF-SPF | 37 | m |  | Not Applicable | 0 | 2 - Main!A18506
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/61 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Fire rated cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — 4C x 50mm² XLPE/SWA/FR + 1C x 25mm² ECC — From EMDB-T3-GF-LV01 to ESMDB-T3-55-FAN | 314 | m |  | Not Applicable | 0 | 2 - Main!A18606
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/65 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator at water feature pump room | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18758
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/65 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-B1-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18760
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/65 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-B1-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18762
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/65 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-B1-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18764
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/65 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-B2-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18766
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/65 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-B2-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18768
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/65 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-B1-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18770
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-B2-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18784
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to DB-T2-GF-SS-01 | 0 | Item |  | Included | 0 | 2 - Main!A18786
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EDB-T2-GF-LL02 | 0 | Item |  | Included | 0 | 2 - Main!A18794
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EMCC-T2-GF-FAN-02 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18796
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18798
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18800
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SP isolator | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18802
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to TPN isolator | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18804
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-GF-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18806
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-GF-LL02 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18808
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to SMDB-T3-01-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18810
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to UDB-T1-GF-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18812
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to UDB-T2-GF-LV01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18814
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item S | S | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to UDB-T4-GF-LV01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18816
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item T | T | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to UDB-T4-GF-SEC-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18818
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item U | U | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to USMDB-T2-BR-GF-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18820
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item V | V | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to USMDB-T2-GF-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18822
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item W | W | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to USMDB-T3-GF-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18824
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/66 Item X | X | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to USMDB-T4-GF-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18826
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T1-50-LIFT2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18839
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T1-59-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18841
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for GEF | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18843
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for HEAT RECOVERY WHEEL | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18845
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for BOOSTER PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18847
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for CBS | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18849
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for FAHU-EXTRACTION FAN | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18851
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for FAHU-SUPPLYFAN | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18853
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for HEATER | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18855
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for JOCKEY PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18857
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18859
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for T1-51F-GEF | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18861
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18863
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for shaft lighting | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18865
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-FAHU | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18867
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-FP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18869
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/67 Item S | S | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-JP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18871
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-TP1 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18890
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-29-TP2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18892
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T1-51-FAHU | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18894
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EMCC-48-T2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18896
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T2-59-LIFT2 | 0 | Item |  | Included | 0 | 2 - Main!A18898
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T2-59-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18900
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for HEAT RECOVERY WHEEL | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18902
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for T2-29F-GEF | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18904
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for BOOSTER PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18906
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for WATER TRANSFER PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18908
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP fire rated isolator for JOCKEY PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18910
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for CBS | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18912
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for FAHU-EXTRACT FAN | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18914
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for FAHU-SUPPLY FAN | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18916
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for HEATER | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18918
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator for CHWP-1 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18920
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/68 Item S | S | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator for CHWP-2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18922
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator for CHWP-3 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18937
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for T2-48F-FPEF | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18939
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP isolator for TRANSFER PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18941
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP fire rated isolator for JOCKEY PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18943
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator for LEVEL 55 - GSM ETISALAT | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18945
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator for LEVEL 56 - GSM DU | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18947
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18949
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP fire rated isolator for T2-59F-GEF | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18951
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A SP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18953
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 80A SP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18955
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for shaft lighting | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18957
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-29-FP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18959
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-29-JP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18961
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-29-TP1 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18963
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-29-TP2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18965
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/69 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-59-FAHU | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18967
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-RF-FAHU1 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18981
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-48-FP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18983
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-48-JP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18985
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-48-TP1 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18987
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T2-48-TP2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18989
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T3-55-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18991
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SPN isolator for GEF | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18993
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SPN isolator for heat recovery wheel | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18995
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TPN isolator for BOOSTER PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18997
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN fire rated isolator for jockey pump | 0 | Item |  | Not Applicable | 0 | 2 - Main!A18999
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for CBS | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19001
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for FAHU-EXTRACTION FAN | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19003
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for FAHU-SUPPLY FAN | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19005
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for HEATER | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19007
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19009
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/70 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP fire rated isolator for T3-55F-GEF | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19011
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A TP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19024
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for shaft lighting | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19026
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-FAHU | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19028
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-FP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19030
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-JP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19032
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-TP1 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19034
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-29-TP2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19036
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T3-55-FAHU | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19038
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EMCC-T3-55-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19040
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T4-53-LL01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19042
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to ESMDB-T4-59-LIFT2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19044
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for HEAT WHEEL | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19046
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for T4-29F-GEF | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19048
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TPN isolator for BOOSTER PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19050
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TPN isolator for WATER TRANSFER PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19052
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for CBS | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19054
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item S | S | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TP isolator for HEAT WHEEL | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19056
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/71 Item T | T | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for FAHU-EXTRACT FAN | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19058
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for FAHU-SUPPLY FAN | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19073
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 32A TPN isolator for JOCKEY PUMP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19075
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 40A TP isolator for CHWP-3 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19077
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19079
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A TP fire rated isolator for T4-59F-GEF | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19081
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 63A SP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19083
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 80A SP isolator for FAHU-RF-01 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19085
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to 20A SP isolator for shaft lighting | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19087
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-29-TP2 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19089
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-L29-FAHU | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19091
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-L29-FP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19093
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-L29-JP | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19095
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-L29-TP1 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19097
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/72 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to MCC-T4-RF-FAHU1 | 0 | Item |  | Not Applicable | 0 | 2 - Main!A19099
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/81 Item T | T | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-01-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19563
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/84 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-B1-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19713
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/84 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-B2-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19715
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/84 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-GF-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19717
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/84 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Sub-main distribution board — SMDB-T3-GF-LL02 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19719
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/87 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T1-50-LIFT2 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19890
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/87 Item S | S | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T1-59-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19894
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/88 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T2-60-LIFT, TCL = 366kW | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19919
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/88 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T2-59-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19923
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/88 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T3-55-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19935
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/88 Item T | T | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T4-53-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19949
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/88 Item V | V | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Equipment; including fixings, supports, accessories and all ancillary works as necessary — Emergency sub-main distribution board — ESMDB-T4-59-LIFT2 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19953
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/89 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible sub-main distribution board — USMDB-T2-BR-GF-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19976
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/89 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible sub-main distribution board — USMDB-T2-GF-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19978
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/89 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible sub-main distribution board — USMDB-T3-GF-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19980
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/89 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible sub-main distribution board — USMDB-T4-GF-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A19982
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/101 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Distribution board — DB-T3-55-LL01, TCL = 15kW | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A20646
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/111 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible distribution board — UDB-T1-GF-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21204
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/111 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible distribution board — UDB-T2-GF-LV01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21206
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/111 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible distribution board — UDB-T4-GF-LV01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21208
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/111 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Uninterruptible distribution board — UDB-T4-GF-SEC-01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21210
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/111 Item T | T | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-FAHU | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21216
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/111 Item U | U | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-FP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21218
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/111 Item V | V | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-JP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21220
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-TP1 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21232
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-29-TP2 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21234
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-51-FAHU | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21236
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-B1-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21238
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T1-B2-LL01, TCL = 60kW | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21240
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-29-FP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21244
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-29-JP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21246
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-29-TP1 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21248
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-29-TP2 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21250
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-59-FAHU | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21252
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-RF-FAHU1 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21254
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-48-FP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21256
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-48-JP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21258
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-48-TP1 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21260
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-48-TP2 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21262
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item U | U | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T2-B2-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21268
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item W | W | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-29-FAHU | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21272
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/112 Item X | X | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-29-FP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21274
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — B4.3: L29: MCC-T3-29-JP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21286
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-29-TP1 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21288
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-29-TP2 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21290
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-55-FAHU | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21292
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T3-B1-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21294
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-29-TP2 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21300
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-L29-FAHU | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21302
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-L29-FP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21304
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-L29-JP | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21306
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-L29-TP1 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21308
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-RF-FAHU1 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21310
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-B1-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21312
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Motor control center — MCC-T4-B2-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21314
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Emergency motor control center — EMCC-48-T2 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21318
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/113 Item W | W | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Emergency motor control center — EMCC-T2-02-FAN1, TCL = 120kW | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21328
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/114 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Emergency motor control center — EMCC-T2-GF-FAN-02 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21346
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/114 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Emergency motor control center — EMCC-T3-55-LL01 | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21356
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/116 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Tap-off unit — 500A MCCB tap-off | 1 | Nr. |  | Not Applicable | 0 | 2 - Main!A21446
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/117 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Isolating switch — 100A TP isolator, weatherproof | 4 | Nr. |  | Not Applicable | 0 | 2 - Main!A21498
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/117 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Isolating switch — SP isolator | 0 | Item |  | Not Applicable | 0 | 2 - Main!A21512
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/117 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Isolating switch — TPN isolator | 0 | Item |  | Not Applicable | 0 | 2 - Main!A21514
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/128 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Luminaires; including fixings, supports, hangers, accessories and all ancillary works as necessary; as specialist lighting specification — Apartment lighting — ID lightings; fixed decorative lights such as pendant lights, chandelier lights, picture lights to FOH areas - Supply by Emaar; Contractor to allow for storage, protection and installation of ID lightings | 1 | Item |  | Included | 0 | 2 - Main!A22007
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/129 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Lighting controls; including fixings, supports, hangers, accessories and all ancillary works as necessary — LED strip driver for 1BR-A unit | 0 | Item |  | Included | 0 | 2 - Main!A22056
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/129 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Lighting controls; including fixings, supports, hangers, accessories and all ancillary works as necessary — LED strip driver for 2BR-C unit | 0 | Item |  | Included | 0 | 2 - Main!A22058
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/141 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Accessories; including fixings, supports, hangers and all ancillary works as necessary — Photocell | 2 | Nr. |  | 0 | 0 | 2 - Main!A22664
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/146 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Accessories; including fixings, supports, hangers and all ancillary works as necessary — FM 200 | 16 | Nr. |  | Included | 0 | 2 - Main!A22879
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/150 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Accessories; including fixings, supports, hangers and all ancillary works as necessary — Emergency lighting installations at Tower 3 Level 29 common areas | 0 | Item |  | Included | 0 | 2 - Main!A23032
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/150 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Accessories; including fixings, supports, hangers and all ancillary works as necessary — Emergency lighting installations at Tower 4 Level 55 common areas | 0 | Item |  | Included | 0 | 2 - Main!A23034
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/163 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Cables and conduits to termination points; including terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — From BMS IP network to DDC points | 40 | Nr. |  | Included | 0 | 2 - Main!A23601
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/163 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Equipment; including active and passive network components, terminations, software, configuration, setup and programming, interface connections, fixings, supports, hangers, accessories and all ancillary works as necessary — Direct digital control, DDC | 40 | Nr. |  | Included | 0 | 2 - Main!A23607
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/163 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To ACB trip status | 0 | Item |  | Included | 0 | 2 - Main!A23615
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To access control panel (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23629
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To BCWS pumps | 0 | Item |  | Included | 0 | 2 - Main!A23631
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To booster pumps | 0 | Item |  | Included | 0 | 2 - Main!A23633
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To CBS panel (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23635
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To CCTV system (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23637
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To chemical dosing unit system | 0 | Item |  | Included | 0 | 2 - Main!A23639
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To chilled water pumps | 0 | Item |  | Included | 0 | 2 - Main!A23641
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To clean agent fire suppression system (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23643
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To common fault alarm | 0 | Item |  | Included | 0 | 2 - Main!A23645
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To co-monitoring panel | 0 | Item |  | Included | 0 | 2 - Main!A23647
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To co-monitoring/sensor | 0 | Item |  | Included | 0 | 2 - Main!A23649
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To domestic water pumps (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23651
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To elevators (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23653
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To extract fan | 0 | Item |  | Included | 0 | 2 - Main!A23655
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To FAHU | 0 | Item |  | Included | 0 | 2 - Main!A23657
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To fire alarm panel (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23659
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item S | S | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To fire pump (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23661
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item T | T | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To FLS fans and dampers (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23663
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item U | U | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To FLS fans/MSFD's (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23665
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item V | V | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To garbage extract fans (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23667
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/164 Item W | W | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To gate barrier (thru FAS) | 0 | Item |  | Included | 0 | 2 - Main!A23669
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To GEF-1 & 2 (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23684
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To generator (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23686
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To integrated panel with ATS | 0 | Item |  | Included | 0 | 2 - Main!A23688
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To irrigation water pumps (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23690
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To jet fan (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23692
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To lighting control system (control and monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23694
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To LPG detecting panel (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23696
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To LPG tank high level alarm (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23698
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item J | J | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To LV/EMU (current/voltage) (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23700
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item K | K | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To motor control centres | 0 | Item |  | Included | 0 | 2 - Main!A23702
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To MFSD (smoke control) (thru FAS) | 0 | Item |  | Included | 0 | 2 - Main!A23704
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To PMU's | 0 | Item |  | Included | 0 | 2 - Main!A23706
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To pool plant equipment (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23708
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To pressurization unit system | 0 | Item |  | Included | 0 | 2 - Main!A23710
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item Q | Q | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To sump pumps | 0 | Item |  | Included | 0 | 2 - Main!A23712
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item R | R | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To supply fans | 0 | Item |  | Included | 0 | 2 - Main!A23714
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item S | S | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To thermostat (common area) | 0 | Item |  | Included | 0 | 2 - Main!A23716
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item T | T | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To UPS for security system (monitoring) | 0 | Item |  | Included | 0 | 2 - Main!A23718
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item U | U | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To water tank level (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23720
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/165 Item V | V | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — BUILDING MANAGEMENT SYSTEM — Building Management Systems (BMS) to interface with other systems and all associated automatic controls and monitoring system; including cabling, containment, BMS devices, terminations, fixings, supports, fittings, accessories and all ancillary works as necessary; complete — To water transfer pumps (monitoring only) | 0 | Item |  | Included | 0 | 2 - Main!A23722
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/166 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere | 0 | Item |  | Included | 0 | 2 - Main!A23737
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/166 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for all identification including painting, marking and labeling | 0 | Item |  | Included | 0 | 2 - Main!A23739
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/166 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installation | 0 | Item |  | Included | 0 | 2 - Main!A23743
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/166 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for providing spares for the Electrical Engineering Installation | 0 | Item |  | 0 | 0 | 2 - Main!A23745
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/166 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like | 0 | Item |  | Included | 0 | 2 - Main!A23747
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/167 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades | 0 | Item |  | Included | 0 | 2 - Main!A23762
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/167 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for liaison with obtaining approvals and attendance on approved Authorities, other statutory bodies and service providers as required | 0 | Item |  | Included | 0 | 2 - Main!A23764
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/167 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for marking the positions of and cutting or forming holes, mortices, chases or the like and all making good | 0 | Item |  | Included | 0 | 2 - Main!A23766
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/167 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for supplying and fixing all sleeves, frames and built-in fire stoppers for building into concrete structures and masonry walls | 0 | Item |  | Included | 0 | 2 - Main!A23768
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/167 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good | 0 | Item |  | Included | 0 | 2 - Main!A23770
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/167 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for fire stopping all cables, conduit, trucking, cable tray and the like at penetrations through fire walls and other structures and making good | 0 | Item |  | Included | 0 | 2 - Main!A23772
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/167 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good | 0 | Item |  | Included | 0 | 2 - Main!A23774
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/167 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for all protective painting including removing protective coatings or wrappings and cleaning exposed surfaces for Electrical installations. | 0 | Item |  | Included | 0 | 2 - Main!A23776
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/168 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for all decorative painting including removing protective coatings or wrappings and cleaning exposed surfaces for Electrical installations. | 0 | Item |  | Included | 0 | 2 - Main!A23792
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/168 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Electrical Engineering Installations | 0 | Item |  | Included | 0 | 2 - Main!A23794
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/168 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Work Incidental to Electrical Engineering Installations — Allow for all incidental work to the Electrical Engineering Installations where not included above or elsewhere | 0 | Item |  | Included | 0 | 2 - Main!A23796
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 2/R/169 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Electrical Engineering Installations in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 2 - Main!A23821
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/B/4 Item N | N | Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for the provision of water only for maintenance purpose during defect liability period | 0 | Item |  | Included | 0 | 3 - Ext!A156
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/B/5 Item A | A | Bill 3 — SECTION B - SITE WORKS (3/B) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Site Works in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A173
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/C/3 Item B | B | Bill 3 — SECTION C - CONCRETE WORKS (3/C) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Concrete Works in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A414
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/E/2 Item A | A | Bill 3 — SECTION E - METALWORK (3/E) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Metalwork in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A613
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/G/2 Item A | A | Bill 3 — SECTION G - THERMAL AND MOISTURE PROTECTION (3/G) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Thermal and Moisture Protection in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A762
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/J/8 Item A | A | Bill 3 — SECTION J - FINISHES (3/J) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Finishes in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A1150
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/K/2 Item A | A | Bill 3 — SECTION K - ACCESSORIES (3/K) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Accessories in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A1435
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/L/2 Item A | A | Bill 3 — SECTION L - EQUIPMENT (3/L) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Equipment in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A1598
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/M/1 Item B | B | Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Lounge table | 65 | Nr. |  | 0 | 0 | 3 - Ext!A1713
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/M/1 Item C | C | Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Outdoor chaise | 130 | Nr. |  | 0 | 0 | 3 - Ext!A1715
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/M/1 Item D | D | Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Pool umbrella | 42 | Nr. |  | 0 | 0 | 3 - Ext!A1717
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/M/1 Item E | E | Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Lifeguard station | 5 | Nr. |  | 0 | 0 | 3 - Ext!A1719
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/M/1 Item F | F | Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Raised cabana | 35 | Nr. |  | 0 | 0 | 3 - Ext!A1721
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/M/1 Item G | G | Bill 3 — SECTION M - FURNISHING (3/M) — SITE FURNITURE — Supply and installation of site furniture; including necessary fixings and all other associated works — Code: FE-02-G; Waste and recycling aluminium bins; size 775 x 260 dia x 985mm high | 11 | Nr. |  | 0 | 0 | 3 - Ext!A1723
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/M/2 Item E | E | Bill 3 — SECTION M - FURNISHING (3/M) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Furnishing in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A1766
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item A | A | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 450mm dia Sand filter to swimming pool 03 | 2 | Nr. |  | Included | 0 | 3 - Ext!A1863
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item B | B | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 500mm dia Sand filter | 8 | Nr. |  | Included | 0 | 3 - Ext!A1865
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item C | C | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 550mm dia Sand filter to swimming pool 04 & 05 | 4 | Nr. |  | Included | 0 | 3 - Ext!A1867
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item D | D | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 1000mm dia Sand filter to swimming pool 02 | 2 | Nr. |  | Included | 0 | 3 - Ext!A1869
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item E | E | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 1200mm dia Sand filter to swimming pool 01 + kids pool | 2 | Nr. |  | Included | 0 | 3 - Ext!A1871
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item F | F | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 0.75 HP (2D + 1S) | 4 | Nr. |  | Included | 0 | 3 - Ext!A1873
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item G | G | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 1 Hp/Ph (2D + 1S) to swimming pool 03 | 2 | Nr. |  | Included | 0 | 3 - Ext!A1875
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item J | J | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 3Hp / 3Ph (2D + 1S) to swimming pool 02 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1879
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item K | K | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 3.5 Hp/3Ph to swimming pool 04 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1881
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item L | L | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 5.5Hp / 3Ph (2D + 1S) to swimming pool 01 + kids pool | 1 | Nr. |  | Included | 0 | 3 - Ext!A1883
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item M | M | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Small Tank to swimming pool 02, 03, 04 & 05 | 6 | Nr. |  | Included | 0 | 3 - Ext!A1885
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item N | N | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Big Tank to swimming pool 03 & 04 | 4 | Nr. |  | Included | 0 | 3 - Ext!A1887
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item P | P | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Balancing tank 10m3 to swimming pool 04 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1889
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item Q | Q | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Balancing tank (2m x 3m x 2m) to swimming pool 05 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1891
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item R | R | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Balancing tank (4m x 2m x 2m) to swimming pool 01 + kids pool | 1 | Nr. |  | Included | 0 | 3 - Ext!A1893
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item S | S | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — UV Disinfection System to swimming pool 01, 02, 03, 04 & 05 | 5 | Nr. |  | Included | 0 | 3 - Ext!A1895
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item T | T | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank 100 Ltr including stirrer to swimming pool 03 & penthouse pool | 5 | Nr. |  | Included | 0 | 3 - Ext!A1897
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/1 Item U | U | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank 200 Ltr, flow 80 m3/hr including manual mixer to swimming pool 02 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1899
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item A | A | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank 250 Ltr, flow 112 m3/hr including manual mixer to swimming pool 01 + kids pool | 1 | Nr. |  | Included | 0 | 3 - Ext!A1912
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item B | B | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank 200 ltr, flow 20 m3/hr including manual mixer swimming pool 04 & 05 | 2 | Nr. |  | Included | 0 | 3 - Ext!A1914
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item C | C | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Automatic chemical dosing system for swimming pool 01, 02, 03, 04 & 05 and penthouse pool | 9 | Nr. |  | Included | 0 | 3 - Ext!A1916
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item D | D | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 100 Ltr including stirrer to swimming pool 03 & penthouse pool | 5 | Nr. |  | Included | 0 | 3 - Ext!A1918
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item E | E | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 200 ltr, flow 20 m3/hr including stirrer to swimming pool 04 & 05 | 2 | Nr. |  | Included | 0 | 3 - Ext!A1920
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item F | F | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 200 Ltr, flow 80 m3/hr including stirrer to swimming pool 02 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1922
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item G | G | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 250 Ltr, flow 112 m3/hr including stirrer to swimming pool 01 + kids pool | 1 | Nr. |  | Included | 0 | 3 - Ext!A1924
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item H | H | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 35kW/25kW to swimming pool 03 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1926
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item J | J | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 45kW/32kW to swimming pool 05 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1928
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item K | K | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 160kW/115kW to swimming pool 04 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1930
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item L | L | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 250kW/180kW to swimming pool 02 | 1 | Nr. |  | Included | 0 | 3 - Ext!A1932
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item M | M | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat cool pump, heating/cooling capacity 135kW/97kW to swimming pool 01 + kids pool | 2 | Nr. |  | Included | 0 | 3 - Ext!A1934
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item N | N | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Water meter to swimming pool 01, 02, 03, 04 & 05 and penthouse pool | 18 | Nr. |  | Included | 0 | 3 - Ext!A1936
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item P | P | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Electrical heater 60kW | 4 | Nr. |  | Included | 0 | 3 - Ext!A1938
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item Q | Q | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Heat Exchanger, capacity: 40kW | 4 | Nr. |  | Included | 0 | 3 - Ext!A1940
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item R | R | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Pressure breaking chamber (600 x 800 x 600mm) | 4 | Nr. |  | Included | 0 | 3 - Ext!A1942
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item S | S | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 25mm (1 inch) Ball valve | 25 | Nr. |  | Included | 0 | 3 - Ext!A1946
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/2 Item T | T | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 40mm (1 1/2 inch) Ball valve | 26 | Nr. |  | Included | 0 | 3 - Ext!A1948
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item A | A | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2") Ball valve | 80 | Nr. |  | Included | 0 | 3 - Ext!A1958
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item B | B | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 60mm (2 1/2 inch) Ball valve | 22 | Nr. |  | Included | 0 | 3 - Ext!A1960
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item C | C | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 75mm (3 inch) ball valve | 20 | Nr. |  | Included | 0 | 3 - Ext!A1962
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item D | D | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 80mm (3") Ball valve | 10 | Nr. |  | Included | 0 | 3 - Ext!A1964
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item E | E | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 100mm (4") Ball valve | 2 | Nr. |  | Included | 0 | 3 - Ext!A1966
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item F | F | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 25mm (1 inch) NRV | 9 | Nr. |  | Included | 0 | 3 - Ext!A1968
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item G | G | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 40mm (2") NRV | 1 | Nr. |  | Included | 0 | 3 - Ext!A1970
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item H | H | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2") NRV | 9 | Nr. |  | Included | 0 | 3 - Ext!A1972
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item J | J | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 60mm (2 1/2 inch) NRV | 12 | Nr. |  | Included | 0 | 3 - Ext!A1974
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item K | K | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 75mm (3 inch) NRV | 2 | Nr. |  | Included | 0 | 3 - Ext!A1976
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item L | L | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 80mm (3") NRV | 6 | Nr. |  | Included | 0 | 3 - Ext!A1978
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item M | M | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 100mm (4") NRV | 1 | Nr. |  | Included | 0 | 3 - Ext!A1980
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item N | N | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 150mm (6") NRV | 6 | Nr. |  | Included | 0 | 3 - Ext!A1982
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item P | P | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 25mm (1 inch) Butterfly valve | 8 | Nr. |  | Included | 0 | 3 - Ext!A1984
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item Q | Q | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2") Butterfly valve | 7 | Nr. |  | Included | 0 | 3 - Ext!A1986
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item R | R | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 63mm (2 1/2") Butterfly valve | 6 | Nr. |  | Included | 0 | 3 - Ext!A1988
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item S | S | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 75mm (2") Butterfly valve | 9 | Nr. |  | Included | 0 | 3 - Ext!A1990
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item T | T | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 80mm (3") Butterfly valve | 10 | Nr. |  | Included | 0 | 3 - Ext!A1992
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item U | U | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 100mm (4") Butterfly valve | 18 | Nr. |  | Included | 0 | 3 - Ext!A1994
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item V | V | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 150mm (6") Butterfly valve | 16 | Nr. |  | Included | 0 | 3 - Ext!A1996
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item W | W | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2") solenoid valve | 1 | Nr. |  | Included | 0 | 3 - Ext!A1998
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item X | X | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Pipe Accessories complete with all ancillary work as necessary — 50mm (2 inch) Bypass valve | 4 | Nr. |  | Included | 0 | 3 - Ext!A2000
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item Y | Y | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 60mm (2 1/2 inch) discharge header, flow 22m3/hr | 2 | Nr. |  | Included | 0 | 3 - Ext!A2004
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/3 Item Z | Z | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 75mm (3 inch) discharge header, flow 16 m3/hr to SP 03 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2006
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item A | A | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") fabricated discharge header, flow 20m3/hr to SP 04 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2016
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item B | B | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") Discharge header, flow 20m3/hr to SP 05 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2018
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item C | C | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 150mm (6") fabricated discharge header, flow 112 m3/hr to SP 01 + kids pool | 1 | Nr. |  | Included | 0 | 3 - Ext!A2020
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item D | D | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 150mm (6") fabricated discharge header, flow 80m3/hr to SP 02 |  |  |  | 0 | 0 | 3 - Ext!A2022
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item E | E | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 7" Suction header, flow 20m3/hr to SP 04 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2024
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item F | F | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") Suction header, flow 20m3/hr to SP 05 | 3 | Nr. |  | Included | 0 | 3 - Ext!A2026
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item G | G | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 150mm (6") fabricated suction header, flow 80m3/hr to SP 02 |  |  |  | 0 | 0 | 3 - Ext!A2028
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item H | H | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 200 x 200mm frame and grate anti-vortex drain | 15 | Nr. |  | Included | 0 | 3 - Ext!A2030
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item J | J | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — 300 x 300mm frame and grate anti-vortex drain | 8 | Nr. |  | Included | 0 | 3 - Ext!A2032
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item K | K | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Acid injection point | 7 | Nr. |  | Included | 0 | 3 - Ext!A2034
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item L | L | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Chlorine injection point | 7 | Nr. |  | Included | 0 | 3 - Ext!A2036
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item M | M | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Drain fittings | 13 | Nr. |  | Included | 0 | 3 - Ext!A2038
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item N | N | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Main drain point | 2 | Nr. |  | Included | 0 | 3 - Ext!A2040
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item P | P | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Floor Drain | 4 | Nr. |  | Included | 0 | 3 - Ext!A2042
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item Q | Q | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Filtration inlet (wall) | 83 | Nr. |  | Included | 0 | 3 - Ext!A2044
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item R | R | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Skimmer | 26 | Nr. |  | Included | 0 | 3 - Ext!A2046
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item S | S | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Vacuum point | 23 | Nr. |  | Included | 0 | 3 - Ext!A2048
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item T | T | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Wire inlet fitting (wall) | 2 | Nr. |  | Included | 0 | 3 - Ext!A2050
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item U | U | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Wall inlet | 6 | Nr. |  | Included | 0 | 3 - Ext!A2052
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item V | V | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Overflow fitting | 16 | Nr. |  | Included | 0 | 3 - Ext!A2054
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item W | W | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Overflow drain | 8 | Nr. |  | Included | 0 | 3 - Ext!A2056
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item X | X | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Water level regulator | 4 | Nr. |  | Included | 0 | 3 - Ext!A2058
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/4 Item Y | Y | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Swimming pool accessories complete, fittings, all hangers, supports and ancillary work as necessary — Infinity channel drain | 8 | Nr. |  | Included | 0 | 3 - Ext!A2060
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item A | A | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 1 + Kids Pool | 290 | m2 |  | Included | 0 | 3 - Ext!A2073
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item B | B | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 2 | 414 | m2 |  | Included | 0 | 3 - Ext!A2075
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item C | C | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 3 (Kids Pool) | 48 | m2 |  | Included | 0 | 3 - Ext!A2077
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item D | D | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 4 | 179 | m2 |  | Included | 0 | 3 - Ext!A2079
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item E | E | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 5 (Kids Pool) | 64 | m2 |  | Included | 0 | 3 - Ext!A2081
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item F | F | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Allow for Swimming pool water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Penthouse Pool | 286 | m2 |  | Included | 0 | 3 - Ext!A2083
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item G | G | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 1 + Kids Pool | 290 | m2 |  | Included | 0 | 3 - Ext!A2089
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item H | H | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 2 | 414 | m2 |  | Included | 0 | 3 - Ext!A2091
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item J | J | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 3 (Kids Pool) | 48 | m2 |  | Included | 0 | 3 - Ext!A2093
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item K | K | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 4 | 179 | m2 |  | Included | 0 | 3 - Ext!A2095
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item L | L | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 5 (Kids Pool) | 64 | m2 |  | Included | 0 | 3 - Ext!A2097
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/5 Item M | M | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — SWIMMING POOL — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Penthouse Pool | 286 | m2 |  | Included | 0 | 3 - Ext!A2099
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item A | A | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 450mm dia Sand filter to WF 02, 03, PH | 6 | Nr. |  | Included | 0 | 3 - Ext!A2126
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item B | B | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — 550mm dia Sand filter to WF 01 | 2 | Nr. |  | Included | 0 | 3 - Ext!A2128
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item C | C | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Small tank to WF 02, 03 | 4 | Nr. |  | Included | 0 | 3 - Ext!A2130
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item D | D | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank - 100 Ltr, flow 10m3/hr including manual mixer to WF 01 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2132
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item E | E | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Acid tank - 100 Ltr, flow 16m3/hr including manual mixer to WF 02, 03 | 2 | Nr. |  | Included | 0 | 3 - Ext!A2134
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item F | F | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Automatic chemical dosing system to WF 01, 02, 03 | 3 | Nr. |  | Included | 0 | 3 - Ext!A2136
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item G | G | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — UV disinfection system to WF 02, 03, PH | 4 | Nr. |  | Included | 0 | 3 - Ext!A2138
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item H | H | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 100 Ltr, flow 10m3/hr including stirrer to WF 01 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2140
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item J | J | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Chlorine tank 100 Ltr, flow 16m3/hr including stirrer to WF 02, 03 | 2 | Nr. |  | Included | 0 | 3 - Ext!A2142
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item K | K | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 1Hp /1 Ph (2D + 1S) for WF-01 to WF 01 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2144
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item L | L | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Filtration pump 1.5Hp/1 Ph (2D + 1S) to WF 02, 03, PH | 4 | Nr. |  | Included | 0 | 3 - Ext!A2146
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item M | M | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature equipment complete, fittings, including all hangers, electrical connection, supports and ancillary work as necessary — Water meter to WF 01, 02, 03 | 6 | Nr. |  | Included | 0 | 3 - Ext!A2148
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item N | N | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 25mm (1 inch) Ball valve | 6 | Nr. |  | Included | 0 | 3 - Ext!A2152
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item P | P | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 40mm (1 1/2") Ball valve | 14 | Nr. |  | Included | 0 | 3 - Ext!A2154
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item Q | Q | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 50mm (2" ) Ball valve | 28 | Nr. |  | Included | 0 | 3 - Ext!A2156
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item R | R | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 80mm (3") Ball Valve | 6 | Nr. |  | Included | 0 | 3 - Ext!A2158
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item S | S | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 50mm (2" ) NRV | 9 | Nr. |  | Included | 0 | 3 - Ext!A2160
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item T | T | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — 80mm (3" ) NRV | 6 | Nr. |  | Included | 0 | 3 - Ext!A2162
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/6 Item U | U | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Pipe accessories complete with all ancillary work as necessary — Allow for pipe accessories for penthouse water feature | 50 | m2 |  | Included | 0 | 3 - Ext!A2164
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item A | A | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 50mm (2" ) discharge header, flow 10m3/hr to WF 01 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2178
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item B | B | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") discharge header, flow 16m3/hr to WF 02, 03 | 2 | Nr. |  | Included | 0 | 3 - Ext!A2180
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item C | C | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 50mm (2") suction header, flow 10m3/hr to WF 01 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2182
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item D | D | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 50mm (3") suction header, flow 16m3/hr to WF 03 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2184
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item E | E | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 80mm (3") suction header, flow 16m3/hr to WF 02 | 1 | Nr. |  | Included | 0 | 3 - Ext!A2186
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item F | F | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — 200x200mm frame & grate anti-vortex drain to WF 01, 02, 03 | 7 | Nr. |  | Included | 0 | 3 - Ext!A2188
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item G | G | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Floor Drain | 7 | Nr. |  | Included | 0 | 3 - Ext!A2190
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item H | H | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Filtration inlet (wall) | 26 | Nr. |  | Included | 0 | 3 - Ext!A2192
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item J | J | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Skimmer fitting | 12 | Nr. |  | Included | 0 | 3 - Ext!A2194
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item K | K | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Vacuum point | 6 | Nr. |  | Included | 0 | 3 - Ext!A2196
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item L | L | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Acid injection point | 3 | Nr. |  | Included | 0 | 3 - Ext!A2198
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item M | M | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Chlorine injection point | 2 | Nr. |  | Included | 0 | 3 - Ext!A2200
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item N | N | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Water feature accessories complete, fittings, all hangers, supports and ancillary work as necessary — Allow for water feature accessories for penthouse water feature | 50 | m2 |  | Included | 0 | 3 - Ext!A2202
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item P | P | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 1 + Kids Pool | 290 | m2 |  | Included | 0 | 3 - Ext!A2206
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item Q | Q | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 2 | 414 | m2 |  | Included | 0 | 3 - Ext!A2208
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item R | R | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 3 (Kids Pool) | 48 | m2 |  | Included | 0 | 3 - Ext!A2210
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item S | S | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 4 | 179 | m2 |  | Included | 0 | 3 - Ext!A2212
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item T | T | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Swimming Pool 5 (Kids Pool) | 64 | m2 |  | Included | 0 | 3 - Ext!A2214
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item U | U | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Penthouse Pool | 286 | m2 |  | Included | 0 | 3 - Ext!A2216
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item V | V | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Water Feature 01 at Ground Floor | 51 | m2 |  | Included | 0 | 3 - Ext!A2218
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item W | W | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Water Feature 02 at Podium | 99 | m2 |  | Included | 0 | 3 - Ext!A2220
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item X | X | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Water Feature 03 at Podium | 154 | m2 |  | Included | 0 | 3 - Ext!A2222
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/7 Item Y | Y | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Allow for water supply and drainage system including pipes, fittings, fixings, accessories and all ancillary works as necessary — Penthouse water feature | 50 | m2 |  | Included | 0 | 3 - Ext!A2224
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item A | A | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 1 + Kids Pool | 290 | m2 |  | Included | 0 | 3 - Ext!A2238
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item B | B | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 2 | 414 | m2 |  | Included | 0 | 3 - Ext!A2240
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item C | C | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 3 (Kids Pool) | 48 | m2 |  | Included | 0 | 3 - Ext!A2242
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item D | D | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 4 | 179 | m2 |  | Included | 0 | 3 - Ext!A2244
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item E | E | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Swimming Pool 5 (Kids Pool) | 64 | m2 |  | Included | 0 | 3 - Ext!A2246
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item F | F | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Penthouse Pool | 286 | m2 |  | Included | 0 | 3 - Ext!A2248
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item G | G | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Water Feature 01 at Ground Floor | 51 | m2 |  | Included | 0 | 3 - Ext!A2250
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item H | H | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Water Feature 02 at Podium | 99 | m2 |  | Included | 0 | 3 - Ext!A2252
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item J | J | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Water Feature 03 at Podium | 154 | m2 |  | Included | 0 | 3 - Ext!A2254
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item K | K | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — WATER FEATURES — Electrical Installation — Allow for Electrical works including distribution board, control panel, cables, conduits, terminations, fixings, supports, accessories, control panels and all works as necessary. — Penthouse water feature | 50 | m2 |  | Included | 0 | 3 - Ext!A2256
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item L | L | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Final sub-circuits and ancillary installations complete; including cabling, wiring, containment and terminations as necessary — Light points | 171 | Nr. |  | Included | 0 | 3 - Ext!A2262
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item M | M | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 4.1; Recessed elliptical beam pool light; 3000 K | 49 | Nr. |  | Included | 0 | 3 - Ext!A2266
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item N | N | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 4.2; Recessed elliptical beam pool step light; 3000 K | 91 | Nr. |  | Included | 0 | 3 - Ext!A2268
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item P | P | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 4.3; Recessed diffused pool marker light; 4000K | 15 | Nr. |  | Included | 0 | 3 - Ext!A2270
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/8 Item Q | Q | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 8.2; Surface mounted floor washer; 3000 K | 16 | Nr. |  | Included | 0 | 3 - Ext!A2272
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/N/9 Item A | A | Bill 3 — SECTION N - SPECIAL CONSTRUCTION (3/N) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Special Construction in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A2284
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item B | B | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for all identification including painting, marking and labelling | 0 | Item |  | Included | 0 | 3 - Ext!A2754
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item C | C | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations | 0 | Item |  | Included | 0 | 3 - Ext!A2756
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item D | D | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installation | 0 | Item |  | Included | 0 | 3 - Ext!A2758
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item E | E | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for providing spares for the Mechanical Engineering Installation | 0 | Item |  | 0 | 0 | 3 - Ext!A2760
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item F | F | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like | 0 | Item |  | Included | 0 | 3 - Ext!A2762
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item G | G | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades | 0 | Item |  | Included | 0 | 3 - Ext!A2766
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item H | H | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for liaison with obtaining approvals and attendance on approved Authorities, other statutory bodies and service providers as required | 0 | Item |  | Included | 0 | 3 - Ext!A2768
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item K | K | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good | 0 | Item |  | Included | 0 | 3 - Ext!A2772
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item L | L | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Mechanical Engineering Installations | 0 | Item |  | Included | 0 | 3 - Ext!A2774
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/8 Item M | M | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work to the Mechanical Engineering Installations where not included above or elsewhere | 0 | Item |  | Included | 0 | 3 - Ext!A2776
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/Q/9 Item A | A | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Mechanical Engineering Installations in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A2790
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/1 Item A | A | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Sub-main cables; including fixings, supports, terminations, accessories and all ancillary works as necessary | 22893 | m2 |  | 0 | 0 | 3 - Ext!A2899
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/1 Item B | B | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Equipment (DB, kwh meter, containment, ducts, etc); including fixings, supports, hangers, concrete base, plinths, earth works, accessories and all ancillary works as necessary | 25649 | m2 |  | 0 | 0 | 3 - Ext!A2901
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/1 Item C | C | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Excavation of trenches; including earthwork support, disposal, compaction, backfilling, marking tape, accessories and all ancillary works as necessary | 15341 | m2 |  | 0 | 0 | 3 - Ext!A2903
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/1 Item D | D | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Connection to supply mains; including cables, conduits, fixings, supports, terminations, accessories and all ancillary works as necessary | 5760 | m2 |  | 0 | 0 | 3 - Ext!A2905
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/1 Item E | E | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Allow for Earthing system; including earthworks, fixings, bondings, connections, joints, earthing cables, earth rods, earth pits, accessories and all ancillary works as necessary | 11172 | m2 |  | 0 | 0 | 3 - Ext!A2907
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/1 Item F | F | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — ELECTRICAL ENGINEERING INSTALLATION — Small power including cables, conduits to termination points and accessories; including terminations, fixings, supports, hangers, accessories and all ancillary works as necessary | 928 | m2 |  | 0 | 0 | 3 - Ext!A2909
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/1 Item K | K | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — uPVC duct — 2x160mm diameter uPVC duct sleeve | 109 | m |  | Included | 0 | 3 - Ext!A2927
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/3 Item C | C | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — LTL 1.1n - Tree Spike light, Narrow beam, 3000K | 0 | Nr. |  | 0 | 0 | 3 - Ext!A3004
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/3 Item K | K | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — LIGHTING INSTALLATION — Light fittings; including fixings, supports, hangers and all ancillary works as necessary — TLTL 8.2 -Asymmetric drive over floor washer, 3000K | 16 | Nr. |  | 0 | 0 | 3 - Ext!A3018
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/3 Item L | L | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for earthing and bonding as specified; in particular all metal containments shall be | 0 | Item |  | Included | 0 | 3 - Ext!A3022
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/3 Item M | M | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere | 0 | Item |  | Included | 0 | 3 - Ext!A3024
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/3 Item N | N | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for all identification including painting, marking and labeling | 0 | Item |  | Included | 0 | 3 - Ext!A3026
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/3 Item Q | Q | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installation | 0 | Item |  | Included | 0 | 3 - Ext!A3030
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item A | A | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for providing spares for the Electrical Engineering Installation | 0 | Item |  | 0 | 0 | 3 - Ext!A3040
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item B | B | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like | 0 | Item |  | Included | 0 | 3 - Ext!A3042
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item C | C | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades | 0 | Item |  | Included | 0 | 3 - Ext!A3046
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item D | D | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for liaison with obtaining approvals and attendance on DEWA, other statutory bodies and service providers as required | 0 | Item |  | Included | 0 | 3 - Ext!A3048
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item E | E | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for marking the positions of and cutting or forming holes, mortices, chases or the like and all making good | 0 | Item |  | Included | 0 | 3 - Ext!A3050
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item F | F | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for supplying and fixing all sleeves, frames and built-in fire stoppers for building into concrete structures and masonry walls | 0 | Item |  | Included | 0 | 3 - Ext!A3052
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item G | G | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for supplying and fixing all brackets, clamps and other fixing devices including building in or cutting and pinning and all making good | 0 | Item |  | Included | 0 | 3 - Ext!A3054
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item H | H | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for fire stopping all cables, conduit, trucking, cable tray and the like at penetrations through fire walls and other structures and making good | 0 | Item |  | Included | 0 | 3 - Ext!A3056
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item J | J | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good | 0 | Item |  | Included | 0 | 3 - Ext!A3058
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item K | K | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Electrical Engineering Installation | 0 | Item |  | Included | 0 | 3 - Ext!A3060
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/4 Item L | L | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Work Incidental to Electrical Engineering Installations — Allow for all incidental work to the Electrical Engineering Installation where not included above or elsewhere | 0 | Item |  | Included | 0 | 3 - Ext!A3062
Candidate — not yet raised | Excluded / unpriced | Excluded, unpriced items | Tenderer should price the below items marked as "excluded, Not Applicable, by others, unpriced etc". Or provide justifications for not pricing. |  |  |  | 3/R/5 Item A | A | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — GENERALLY — Allow for any other works which are not included above and which are required to complete the Electrical Engineering Installations in accordance with the Specification and the Drawings (Tenderer to list below): | 0 | Item |  | 0 | 0 | 3 - Ext!A3079
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/2-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 1 As per Emaar standard CoC |  | Item |  | 1859450 | 1859450 | GR1!A46
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/2-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 2 Advance Payment Guarantee |  | Item |  | 4441500 | 4441500 | GR1!A48
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/2-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 3 Performance Bond |  | Item |  | 5710500 | 5710500 | GR1!A50
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/2-E | E | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A1.1- Schedule of Clauses — 5 Workmen's Compensation Insurance |  | Item |  | 2579252 | 2579252 | GR1!A54
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/4-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 1 Access for and Possession or use of the Site |  | Item |  | 326000 | 326000 | GR1!A139
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/4-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 2 Limitations of working space |  | Item |  | 875150 | 875150 | GR1!A141
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/4-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A1 - Conditions of Contract — The Contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately — A3 - Restrictions — 3 Limitations of working hours |  | Item |  | 2579252 | 2579252 | GR1!A143
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/5-D | D | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — 2 Supervision |  | Item |  | 127607506 | 127607506 | GR1!A199
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/5-E | E | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — 3 Security |  | Item |  | 1677101 | 1677101 | GR1!A201
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/5-F | F | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A4 - Contractor's Administrative Arrangement — A4.1- An item shall be given for contractor's administrative arrangements, which shall include: — 1 Office for the Contract administrators — 4 Safety, health and welfare of workpeople |  | Item |  | 14390609 | 14390609 | GR1!A203
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 1 Small plant and tools — i. Establishment (Fixed Charges) |  | Item |  | 255272 | 255272 | GR1!A243
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 1 Small plant and tools — ii. Maintenance (Time Related Charges) |  | Item |  | 2169815 | 2169815 | GR1!A245
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 1 Small plant and tools — iii. Removal (Fixed Charges) |  | Item |  | 127636 | 127636 | GR1!A247
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-D | D | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 2 Scaffoldings — i. Establishment (Fixed Charges) |  | Item |  | 254997 | 254997 | GR1!A251
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-E | E | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 2 Scaffoldings — ii. Maintenance (Time Related Charges) |  | Item |  | 4589946 | 4589946 | GR1!A253
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-F | F | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 2 Scaffoldings — iii. Removal (Fixed Charges) |  | Item |  | 254997 | 254997 | GR1!A255
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-G | G | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 3 Cranes and lifting plant — i. Establishment (Fixed Charges) |  | Item |  | 1903672 | 1903672 | GR1!A259
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-H | H | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 3 Cranes and lifting plant — ii. Maintenance (Time Related Charges) |  | Item |  | 16561946 | 16561946 | GR1!A261
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-J | J | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 3 Cranes and lifting plant — iii. Removal (Fixed Charges) |  | Item |  | 571102 | 571102 | GR1!A263
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-K | K | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 4 Plant required for specific trades — i. Establishment (Fixed Charges) |  | Item |  | 954406 | 954406 | GR1!A267
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-L | L | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 4 Plant required for specific trades — ii. Maintenance (Time Related Charges) |  | Item |  | 8112451 | 8112451 | GR1!A269
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-M | M | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 4 Plant required for specific trades — iii. Removal (Fixed Charges) |  | Item |  | 477203 | 477203 | GR1!A271
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-N | N | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 5 Site Transport — i. Establishment (Fixed Charges) |  | Item |  | 216157 | 216157 | GR1!A275
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-P | P | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 5 Site Transport — ii. Maintenance (Time Related Charges) |  | Item |  | 3890822 | 3890822 | GR1!A277
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-Q | Q | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 5 Site Transport — iii. Removal (Fixed Charges) |  | Item |  | 216157 | 216157 | GR1!A279
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/6-R | R | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — 5 Site Transport — 6 Other plant not listed above but necessary for the completion of the Works |  | Item |  | 3378750 | 3378750 | GR1!A281
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — A6 - Employer's Facilities — Particulars shall be given of any facilities required for the Employer or the Employer's representatives, which shall include: — 1 - Temporary fully functional site facilities — i. Establishment (Fixed Charges) |  | Item |  | 356150 | 356150 | GR1!A294
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — A6 - Employer's Facilities — Particulars shall be given of any facilities required for the Employer or the Employer's representatives, which shall include: — 1 - Temporary fully functional site facilities — ii. Maintenance (Time Related Charges) |  | Item |  | 336125 | 336125 | GR1!A296
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A5 - Constructional Plant — A5.1 An item shall be given for constructional plant, which shall include: — A6 - Employer's Facilities — Particulars shall be given of any facilities required for the Employer or the Employer's representatives, which shall include: — 1 - Temporary fully functional site facilities — iii. Removal (Fixed Charges) |  | Item |  | 7500 | 7500 | GR1!A298
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-D | D | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Telephones, including costs of calls — i. Establishment (Fixed Charges) |  | Item |  | 228000 | 228000 | GR1!A302
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-E | E | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Telephones, including costs of calls — ii. Maintenance (Time Related Charges) |  | Item |  | 410600 | 410600 | GR1!A304
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-F | F | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Telephones, including costs of calls — iii. Removal (Fixed Charges) |  | Item |  | 15750 | 15750 | GR1!A306
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-G | G | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Telephones, including costs of calls — 3 - Attendance of staff (for example, drivers, laboratory assistants) |  | Item |  | 575000 | 575000 | GR1!A308
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-H | H | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 - Equipment (for example surveying equipment, laboratory equipment) — i. Establishment (Fixed Charges) |  | Item |  | 35130 | 35130 | GR1!A312
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-J | J | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 - Equipment (for example surveying equipment, laboratory equipment) — ii. Maintenance (Time Related Charges) |  | Item |  | 76200 | 76200 | GR1!A314
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-K | K | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 - Equipment (for example surveying equipment, laboratory equipment) — iii. Removal (Fixed Charges) |  | Item |  | 2500 | 2500 | GR1!A316
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/7-L | L | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 - Equipment (for example surveying equipment, laboratory equipment) — 5 - Special requirements for programmes or progress charts |  | Item |  | 147000 | 147000 | GR1!A318
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/8-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Any other facilities (for example, progress photographs). — i. Establishment (Fixed Charges) |  | Item |  | 6500 | 6500 | GR1!A339
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/8-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Any other facilities (for example, progress photographs). — ii. Maintenance (Time Related Charges) |  | Item |  | 63000 | 63000 | GR1!A341
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/8-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Any other facilities (for example, progress photographs). — iii. Removal (Fixed Charges) |  | Item |  | 2500 | 2500 | GR1!A343
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/8-D | D | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — Signboard — Existing signboard to be taken over from Enabling Works contractor and Main Works contractor to update the names, maintain as required, remove after completion of the Works |  | Item |  | 25000 | 25000 | GR1!A348
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/9-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A7 - Contractor's Facilities — A7.1 An item shall be given for facilities required by the contractor, which shall include: — 1 - Contractor's Facilities, including offices, toilets, laboratories, compounds, stores, mess rooms — i. Establishment (Fixed Charges) |  | Item |  | 2292840 | 2292840 | GR1!A389
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/9-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A7 - Contractor's Facilities — A7.1 An item shall be given for facilities required by the contractor, which shall include: — 1 - Contractor's Facilities, including offices, toilets, laboratories, compounds, stores, mess rooms — ii. Maintenance (Time Related Charges) |  | Item |  | 5197105 | 5197105 | GR1!A391
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/9-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A7 - Contractor's Facilities — A7.1 An item shall be given for facilities required by the contractor, which shall include: — 1 - Contractor's Facilities, including offices, toilets, laboratories, compounds, stores, mess rooms — iii. Removal (Fixed Charges) |  | Item |  | 152856 | 152856 | GR1!A393
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/9-D | D | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Temporary fencing, hoardings — i. Existing temporary site perimeter hoarding to be taken over from Enabling Works contractor and Main Works contractor to move / remove / adjust, maintain as required |  | Item |  | 35750 | 35750 | GR1!A397
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/9-E | E | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Temporary fencing, hoardings — ii. Maintenance (Time Related Charges) |  | Item |  | 147000 | 147000 | GR1!A399
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/9-F | F | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 2 - Temporary fencing, hoardings — ii. Final Removal (Fixed Charges) |  | Item |  | 8500 | 8500 | GR1!A401
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/9-K | K | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 Temporary roads, hard standings and crossings — i. Establishment (Fixed Charges) |  | Item |  | 48250 | 48250 | GR1!A413
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/9-L | L | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 Temporary roads, hard standings and crossings — ii. Maintenance (Time Related Charges) |  | Item |  | 475100 | 475100 | GR1!A415
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/9-M | M | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 4 Temporary roads, hard standings and crossings — iii. Removal (Fixed Charges) |  | Item |  | 7800 | 7800 | GR1!A417
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/10-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 5 Water for the Works — i. Establishment (Fixed Charges) |  | Item |  | 870813 | 870813 | GR1!A433
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/10-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 5 Water for the Works — ii. Maintenance (Time Related Charges) |  | Item |  | 4644336 | 4644336 | GR1!A435
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/10-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 5 Water for the Works — iii. Removal (Fixed Charges) |  | Item |  | 290271 | 290271 | GR1!A437
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/10-D | D | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Lighting and power for the Works — i. Establishment (Fixed Charges) |  | Item |  | 3367938 | 3367938 | GR1!A441
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/10-E | E | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Lighting and power for the Works — ii. Maintenance (Time Related Charges) |  | Item |  | 29637854 | 29637854 | GR1!A443
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/10-F | F | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 6 Lighting and power for the Works — iii. Removal (Fixed Charges) |  | Item |  | 673588 | 673588 | GR1!A445
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/10-G | G | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 7 Temporary telephones, electronic mail and facsimile — i. Establishment (Fixed Charges) |  | Item |  | 105600 | 105600 | GR1!A449
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/10-H | H | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 7 Temporary telephones, electronic mail and facsimile — ii. Maintenance (Time Related Charges) |  | Item |  | 376150 | 376150 | GR1!A451
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/10-J | J | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — 7 Temporary telephones, electronic mail and facsimile — iii. Removal (Fixed Charges) |  | Item |  | 5600 | 5600 | GR1!A453
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/11-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A8 - Temporary Works — A8.1 An item shall be given for temporary works including design, which shall include: — 1 Traffic diversion |  | Item |  | 813450 | 813450 | GR1!A484
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/11-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A8 - Temporary Works — A8.1 An item shall be given for temporary works including design, which shall include: — 2 Access roads |  | Item |  | 474513 | 474513 | GR1!A486
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/12-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 1 - Testing of materials |  | Item |  | 488070 | 488070 | GR1!A535
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/12-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 2 - Testing of the Works |  | Item |  | 1762475 | 1762475 | GR1!A537
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/12-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 3 - Protecting the Works from inclement weather |  | Item |  | 623645 | 623645 | GR1!A539
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/12-D | D | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 4 - Removing rubbish, protective casings and coverings and cleaning the Works at completion |  | Item |  | 813450 | 813450 | GR1!A541
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/12-F | F | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9 - Sundry Items — A9.1 An item shall be given for temporary works, which shall include: — 6 - Maintenance of public and private roads |  | Item |  | 216920 | 216920 | GR1!A545
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/12-K | K | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 1 - Coordination with the Works by Others |  | Item |  | 325380 | 325380 | GR1!A555
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/12-L | L | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 2 - Surveys, Setting-out and Levels |  | Item |  | 515185 | 515185 | GR1!A557
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/12-M | M | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 3 - Dust Control, Pest Control and Lightning Protection |  | Item |  | 623645 | 623645 | GR1!A559
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/12-P | P | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 5 - Packing, marking, storage, handling and unpacking |  | Item |  | 113883 | 113883 | GR1!A563
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/13-B | B | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 7 - Shop Drawings |  | Item |  | 406725 | 406725 | GR1!A579
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/13-C | C | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 8 - Submittal program, drawings and revisions |  | Item |  | 176248 | 176248 | GR1!A581
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/13-D | D | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 9 - Method Statements |  | Item |  | 162690 | 162690 | GR1!A583
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/13-E | E | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 10 - Operation and Maintenance Manuals |  | Item |  | 140998 | 140998 | GR1!A585
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/13-F | F | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 11 - Building Information Modelling (BIM) System |  | Item |  | 3308030 | 3308030 | GR1!A587
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/13-G | G | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 12 - Project Management System - Unifier |  | Item |  | 437500 | 437500 | GR1!A589
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/13-M | M | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 17 - Final Cleaning for Project Handover |  | Item |  | 1382865 | 1382865 | GR1!A599
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/13-N | N | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 18 - Provision of Handover Documentation |  | Item |  | 149133 | 149133 | GR1!A601
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/13-R | R | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 21 - Design of the Works to the extent provided for in the Contract |  | Item |  | 433840 | 433840 | GR1!A607
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | GR1/14-A | A | GENERAL REQUIREMENTS FOR THE WHOLE OF THE WORKS — A9.2 Particulars shall be given where the nature or extent of the sundry items is not at the discretion of the Contractor. — 23 - All mock-ups, prototypes and samples required by the Specification, the Drawings and the Schedule of Project Requirements |  | Item |  | 325400 | 325400 | GR1!A624
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/B/1 Item D | D | Bill 2 — SECTION B - SITE WORKS (2/B) — SITE PREPARATION — Dewatering; including design, maintenance, consumables, accessories and all ancillary works as necessary; complete — Maintenance of de-watering system | 0 | Item | 3049200 | 3049200 | 3049200 | 2 - Main!A21
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/B/1 Item E | E | Bill 2 — SECTION B - SITE WORKS (2/B) — SITE PREPARATION — Dewatering; including design, maintenance, consumables, accessories and all ancillary works as necessary; complete — Allow for removal of the dewatering system and closing of raft suction pipe opening, etc.. | 0 | Item | 246400 | 246400 | 246400 | 2 - Main!A23
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/J/9 Item F | F | Bill 2 — SECTION J - FINISHES (2/J) — CEILING FINISHES — Calcium silicate board ceiling system; 13mm thick; non-combustible board panels supported by metal frame system; including insulation, finishes, suspended metal support framing system, brackets, fastenings, accessories and all necessary fixings and accessories — Extra over for access panel | 0 | Item | 29155 | 29155 | 29155 | 2 - Main!A4866
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/J/11 Item B | B | Bill 2 — SECTION J - FINISHES (2/J) — SUSPENDED CEILING — Monolithic gypsum board ceiling; including ceiling suspension system, shadows gaps, trims, corner protection profile, accessories and all ancillary works as necessary — Extra over for access panel; size 450 x 450mm | 0 | Item | 309 | 309 | 309 | 2 - Main!A4948
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/J/12 Item J | J | Bill 2 — SECTION J - FINISHES (2/J) — SUSPENDED CEILING — Monolithic gypsum board ceiling; moisture resistant; including ceiling suspension system, shadows gaps, trims, corner protection profile, accessories and all ancillary works as necessary — Extra over for access panel; size 450 x 450mm | 0 | Item | 167 | 167 | 167 | 2 - Main!A5005
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/L/5 Item H | H | Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — Allow to panel transport trolley including accessories and all ancillary works as necessary | 0 | Item | 14102 | 14102 | 14102 | 2 - Main!A6674
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/4 Item K | K | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Sanitary fixtures; fixed to tiled or plastered concrete or blockwork; including all waste and overflow outlets, connections, supports and sealing around with silicone-based sealants and all ancillary works as necessary — Sundries — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations | 0 | Item |  | 241378 | 241378 | 2 - Main!A7781
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/5 Item H | H | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SANITARY FIXTURES & FITTINGS — Builders work in connection (BWIC) with Mechanical Engineering Installations — Allow for all BWIC with Mechanical Engineering Installations where not included above or elsewhere | 0 | Item |  | 444555 | 444555 | 2 - Main!A7826
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/177 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for earthing and bonding as specified; in particular all ductwork systems shall be provided with earth continuity protection at all joints | 0 | Item |  | 104875 | 104875 | 2 - Main!A15214
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/177 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for all supports, fixings, anchors, insulating blocks and anti-vibration devices where not included above or elsewhere | 0 | Item |  | 104875 | 104875 | 2 - Main!A15216
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/177 Item D | D | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for all identification including painting, marking and labeling, including labeling all valves | 0 | Item |  | 104875 | 104875 | 2 - Main!A15218
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/177 Item E | E | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for flushing, cleaning, sterilization and chlorination of the completed installations as necessary | 0 | Item |  | 31462 | 31462 | 2 - Main!A15220
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/177 Item F | F | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations | 0 | Item |  | 4553660 | 4553660 | 2 - Main!A15222
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/177 Item G | G | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for providing in suitable quantities all special tools, operating handles and keys or other equipment necessary for installation, maintenance or operation of the completed installations | 0 | Item |  | 104875 | 104875 | 2 - Main!A15224
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/177 Item J | J | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for providing comprehensive equipment documentation including operating instructions and maintenance manuals, record documents, warranties, guarantees, drawings and the like | 0 | Item |  | 178287 | 178287 | 2 - Main!A15228
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/178 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — SUNDRIES — Allow for vibration and noise control where not included above or elsewhere | 0 | Item |  | 83902 | 83902 | 2 - Main!A15249
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/179 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for planning and coordinating with relevant statutory authorities and with all other trades | 0 | Item |  | 20976 | 20976 | 2 - Main!A15282
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/179 Item B | B | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for liaison with obtaining approvals and attendance on DEWA, other statutory bodies and service providers as required | 0 | Item |  | 20976 | 20976 | 2 - Main!A15284
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/179 Item F | F | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for fire stopping all pipes, ducts and the like at penetrations through fire walls and other structures and making good | 0 | Item |  | 104875 | 104875 | 2 - Main!A15292
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/179 Item G | G | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good | 0 | Item |  | 83902 | 83902 | 2 - Main!A15294
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/179 Item H | H | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for all protective painting including removing protective coatings or wrappings and cleaning exposed surfaces for Mechanical installations. | 0 | Item |  | 83902 | 83902 | 2 - Main!A15296
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/180 Item A | A | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Work Incidental to Mechanical Engineering Installations — Allow for training the Employer's Staff to operate and maintain the Mechanical Engineering Installations | 0 | Item |  | 20976 | 20976 | 2 - Main!A15314
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/Q/180 Item C | C | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — WORK INCIDENTAL AND BWIC — Builders work in connection (BWIC) with Mechanical Engineering Installations — Allow for all BWIC with Mechanical Engineering Installations where not included above or elsewhere | 0 | Item |  | 4880115 | 4880115 | 2 - Main!A15320
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/13 Item S | S | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC — From SMDB-T2-GF-LV to DB-T2-GF-WF1 | 0 | Item | 2863 | 2863 | 2863 | 2 - Main!A16430
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/37 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T1-GF-LV01 to 40A TP isolator for signage (ISO-T1-GF-SIGNAGE) | 0 | Item | 5627 | 5627 | 5627 | 2 - Main!A17548
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/37 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T1-GF-LV01 to 40A TP isolator for signage (ISO-T3-GF-SIGNAGE) | 0 | Item | 5627 | 5627 | 5627 | 2 - Main!A17550
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/39 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T4-02-LL01 to DB-T4-02-GYM | 0 | Item | 845 | 845 | 845 | 2 - Main!A17622
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/66 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to DB-T3-GF-LL02 | 0 | Item |  | 515 | 515 | 2 - Main!A18788
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/66 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to DB-T2-03-KDCB | 0 | Item |  | 6845 | 6845 | 2 - Main!A18790
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/66 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Cables; including fixings, supports, terminations, accessories and all ancillary works as necessary — From power supply to EDB-T2-GF-ETS | 0 | Item |  | 2556 | 2556 | 2 - Main!A18792
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/118 Item U | U | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Containment; including fixings, supports, hangers, fittings, accessories and all ancillary works as necessary — PVC pipe — Cable containment to Retail DB | 0 | Item | 24876 | 24876 | 24876 | 2 - Main!A21586
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/141 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To BMS system | 0 | Item | 16025 | 16025 | 16025 | 2 - Main!A22672
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/141 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Aircraft warning lighting at Tower 3 | 0 | Item | 10685 | 10685 | 10685 | 2 - Main!A22674
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/141 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Aircraft warning lighting at Tower 4 | 0 | Item | 10685 | 10685 | 10685 | 2 - Main!A22676
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/148 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To BMS | 0 | Item |  | 20031 | 20031 | 2 - Main!A22949
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/148 Item B | B | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To access control panel, ACP | 0 | Item |  | 16025 | 16025 | 2 - Main!A22951
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/148 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To gas leak detection panel | 0 | Item |  | 16025 | 16025 | 2 - Main!A22953
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/148 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Fire alarm installations at Tower 3 Level 29 common areas | 0 | Item |  | 13354 | 13354 | 2 - Main!A22955
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/148 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Fire alarm interfacing works complete; including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Fire alarm installations at Tower 4 Level 55 common areas | 0 | Item |  | 13354 | 13354 | 2 - Main!A22957
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/150 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — Graphic workstation with touch screen at Tower 4 FCC room | 0 | Item | 26709 | 26709 | 26709 | 2 - Main!A23044
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/150 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — Master PC at Security room | 0 | Item | 33385 | 33385 | 33385 | 2 - Main!A23046
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/161 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To ACS system | 0 | Item | 25227 | 25227 | 25227 | 2 - Main!A23542
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/161 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To ANPR system | 0 | Item | 25227 | 25227 | 25227 | 2 - Main!A23544
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/161 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To intercom system | 0 | Item | 25227 | 25227 | 25227 | 2 - Main!A23546
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/161 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To key management system | 0 | Item | 25227 | 25227 | 25227 | 2 - Main!A23548
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/162 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To video management system | 0 | Item | 163592 | 163592 | 163592 | 2 - Main!A23561
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/166 Item C | C | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations | 0 | Item |  | 5151382 | 5151382 | 2 - Main!A23741
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 2/R/168 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Builders work in connection (BWIC) with Electrical Engineering Installations — Allow for all BWIC with Electrical Engineering Installations where not included above or elsewhere | 0 | Item | 5601893 | 5601893 | 5601893 | 2 - Main!A23800
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 3/B/4 Item L | L | Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for planting edging | 0 | Item | 66444 | 66444 | 66444 | 3 - Ext!A152
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 3/B/4 Item M | M | Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for maintenance of soft landscaping works during defect liability period for a period of one year after the date of Taking over Certificate and for complying with all the requirements | 0 | Item | 244080 | 244080 | 244080 | 3 - Ext!A154
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 3/Q/7 Item A | A | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — IRRIGATION INSTALLATION — Irrigation controller; including foundation, 100mm diameter conduit for valve cables, 40mm diameter conduit for ground cable, copper earthing, electrical connection, supports and ancillary work as necessary — Allow for connection of irrigation pipe with existing infrastructure network including ancillary work as necessary | 0 | Item | 84750 | 84750 | 84750 | 3 - Ext!A2698
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 3/Q/8 Item A | A | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere | 0 | Item | 42375 | 42375 | 42375 | 3 - Ext!A2752
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 3/Q/8 Item J | J | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good | 0 | Item | 73569 | 73569 | 73569 | 3 - Ext!A2770
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 3/Q/8 Item N | N | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Builders work in connection (BWIC) with Mechanical Engineering Installations — Allow for all BWIC with Mechanical Engineering Installations where not included above or elsewhere | 0 | Item | 76998 | 76998 | 76998 | 3 - Ext!A2780
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 3/R/2 Item A | A | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — Tie-in Connection — Tie-in connection to existing electrical line | 0 | item | 107365 | 107365 | 107365 | 3 - Ext!A2944
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 3/R/2 Item M | M | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — External Communication Services — Electrical point — External Communication Services — Allow for ICT installation (Data connection); including cables, conduits, terminations, fixings, supports, hangers, data outlets, accessories and all ancillary works as necessary | 0 | Item | 127075 | 127075 | 127075 | 3 - Ext!A2986
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | 3/R/3 Item P | P | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant Specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations | 0 | Item | 59885.95 | 59885.95 | 59885.95 | 3 - Ext!A3028
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | Bill 4/1-A | A | PROVISIONAL SUMS — Items of Works to be Tendered — The Employer shall ascertain and determine by measurement the value of work done and/or Plant provided to which the following Provisional Sums relate in accordance with the Conditions of Contract — Workforce Productivity System — Workforce productivity monitoring system (AED1,000,000) |  | Item |  | 1000000 | 1000000 | Bill 4!A12
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | Bill 4/1-B | B | PROVISIONAL SUMS — Items of Works to be Tendered — The Employer shall ascertain and determine by measurement the value of work done and/or Plant provided to which the following Provisional Sums relate in accordance with the Conditions of Contract — Workforce Productivity System — Main Contractor's OH&P of 10% |  | Item |  | 100000 | 100000 | Bill 4!A14
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | Bill 4/1-C | C | PROVISIONAL SUMS — Items of Works to be Tendered — The Employer shall ascertain and determine by measurement the value of work done and/or Plant provided to which the following Provisional Sums relate in accordance with the Conditions of Contract — RTA ROW Access — Design and build of the RTA ROW accesses in the adjacent DM-owned plot as per SOPR, Clause 1.6 b |  | Item |  | 3500000 | 3500000 | Bill 4!A18
Candidate — not yet raised | Not priced individually | Items not priced individually | BOQ line items should be priced individually. The below items carry a composite or lump-sum price; please provide the individual rate and amount against each line. |  |  |  | Bill 4/1-D | D | PROVISIONAL SUMS — Items of Works to be Tendered — The Employer shall ascertain and determine by measurement the value of work done and/or Plant provided to which the following Provisional Sums relate in accordance with the Conditions of Contract — RTA ROW Access — Main Contractor's OH&P of 10% |  | Item |  | 350000 | 350000 | Bill 4!A20
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/B/1 Item D | D | Bill 2 — SECTION B - SITE WORKS (2/B) — SITE PREPARATION — Dewatering; including design, maintenance, consumables, accessories and all ancillary works as necessary; complete — Maintenance of de-watering system | 0 | Item | 3049200 | 3049200 | 3049200 | 2 - Main!A21
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/B/1 Item E | E | Bill 2 — SECTION B - SITE WORKS (2/B) — SITE PREPARATION — Dewatering; including design, maintenance, consumables, accessories and all ancillary works as necessary; complete — Allow for removal of the dewatering system and closing of raft suction pipe opening, etc.. | 0 | Item | 246400 | 246400 | 246400 | 2 - Main!A23
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/J/9 Item F | F | Bill 2 — SECTION J - FINISHES (2/J) — CEILING FINISHES — Calcium silicate board ceiling system; 13mm thick; non-combustible board panels supported by metal frame system; including insulation, finishes, suspended metal support framing system, brackets, fastenings, accessories and all necessary fixings and accessories — Extra over for access panel | 0 | Item | 29155 | 29155 | 29155 | 2 - Main!A4866
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/J/11 Item B | B | Bill 2 — SECTION J - FINISHES (2/J) — SUSPENDED CEILING — Monolithic gypsum board ceiling; including ceiling suspension system, shadows gaps, trims, corner protection profile, accessories and all ancillary works as necessary — Extra over for access panel; size 450 x 450mm | 0 | Item | 309 | 309 | 309 | 2 - Main!A4948
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/J/12 Item J | J | Bill 2 — SECTION J - FINISHES (2/J) — SUSPENDED CEILING — Monolithic gypsum board ceiling; moisture resistant; including ceiling suspension system, shadows gaps, trims, corner protection profile, accessories and all ancillary works as necessary — Extra over for access panel; size 450 x 450mm | 0 | Item | 167 | 167 | 167 | 2 - Main!A5005
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/L/5 Item H | H | Bill 2 — SECTION L - EQUIPMENT (2/L) — BUILDING MANAGEMENT UNIT (BMU) — Allow to detent pin BMU restraints; including painted restraint socket, fixings, brackets, accessories and all ancillary works as necessary — Allow to panel transport trolley including accessories and all ancillary works as necessary | 0 | Item | 14102 | 14102 | 14102 | 2 - Main!A6674
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/13 Item S | S | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC — From SMDB-T2-GF-LV to DB-T2-GF-WF1 | 0 | Item | 2863 | 2863 | 2863 | 2 - Main!A16430
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/37 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T1-GF-LV01 to 40A TP isolator for signage (ISO-T1-GF-SIGNAGE) | 0 | Item | 5627 | 5627 | 5627 | 2 - Main!A17548
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/37 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T1-GF-LV01 to 40A TP isolator for signage (ISO-T3-GF-SIGNAGE) | 0 | Item | 5627 | 5627 | 5627 | 2 - Main!A17550
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/39 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC — From SMDB-T4-02-LL01 to DB-T4-02-GYM | 0 | Item | 845 | 845 | 845 | 2 - Main!A17622
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/118 Item U | U | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — POWER INSTALLATION — Containment; including fixings, supports, hangers, fittings, accessories and all ancillary works as necessary — PVC pipe — Cable containment to Retail DB | 0 | Item | 24876 | 24876 | 24876 | 2 - Main!A21586
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/141 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — To BMS system | 0 | Item | 16025 | 16025 | 16025 | 2 - Main!A22672
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/141 Item E | E | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Aircraft warning lighting at Tower 3 | 0 | Item | 10685 | 10685 | 10685 | 2 - Main!A22674
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/141 Item F | F | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — LIGHTING INSTALLATION — Aircraft warning lighting interfacing works; complete including cables, conduits, terminations, fixings, supports, hangers, accessories and all ancillary works as necessary — Aircraft warning lighting at Tower 4 | 0 | Item | 10685 | 10685 | 10685 | 2 - Main!A22676
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/150 Item G | G | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — Graphic workstation with touch screen at Tower 4 FCC room | 0 | Item | 26709 | 26709 | 26709 | 2 - Main!A23044
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/150 Item H | H | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — FIRE ALARM AND EMERGENCY LIGHTING INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — Master PC at Security room | 0 | Item | 33385 | 33385 | 33385 | 2 - Main!A23046
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/161 Item L | L | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To ACS system | 0 | Item | 25227 | 25227 | 25227 | 2 - Main!A23542
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/161 Item M | M | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To ANPR system | 0 | Item | 25227 | 25227 | 25227 | 2 - Main!A23544
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/161 Item N | N | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To intercom system | 0 | Item | 25227 | 25227 | 25227 | 2 - Main!A23546
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/161 Item P | P | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To key management system | 0 | Item | 25227 | 25227 | 25227 | 2 - Main!A23548
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/162 Item A | A | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — SECURITY INSTALLATION — Workstation; including computers, monitors, printers, software, accessories and all ancillary works as necessary — To video management system | 0 | Item | 163592 | 163592 | 163592 | 2 - Main!A23561
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 2/R/168 Item D | D | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — WORK INCIDENTAL AND BWIC — Builders work in connection (BWIC) with Electrical Engineering Installations — Allow for all BWIC with Electrical Engineering Installations where not included above or elsewhere | 0 | Item | 5601893 | 5601893 | 5601893 | 2 - Main!A23800
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 3/B/4 Item L | L | Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for planting edging | 0 | Item | 66444 | 66444 | 66444 | 3 - Ext!A152
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 3/B/4 Item M | M | Bill 3 — SECTION B - SITE WORKS (3/B) — SUNDRIES — Allow for maintenance of soft landscaping works during defect liability period for a period of one year after the date of Taking over Certificate and for complying with all the requirements | 0 | Item | 244080 | 244080 | 244080 | 3 - Ext!A154
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 3/Q/7 Item A | A | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — IRRIGATION INSTALLATION — Irrigation controller; including foundation, 100mm diameter conduit for valve cables, 40mm diameter conduit for ground cable, copper earthing, electrical connection, supports and ancillary work as necessary — Allow for connection of irrigation pipe with existing infrastructure network including ancillary work as necessary | 0 | Item | 84750 | 84750 | 84750 | 3 - Ext!A2698
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 3/Q/8 Item A | A | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Allow for all supports, fixings, anchors and insulating blocks where not included above or elsewhere | 0 | Item | 42375 | 42375 | 42375 | 3 - Ext!A2752
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 3/Q/8 Item J | J | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Work Incidental to Mechanical Engineering Installations — Allow for all incidental work including factory finishing, fixing to all backgrounds by appropriate means and all making good | 0 | Item | 73569 | 73569 | 73569 | 3 - Ext!A2770
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 3/Q/8 Item N | N | Bill 3 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (3/Q) — SUNDRIES — Builders work in connection (BWIC) with Mechanical Engineering Installations — Allow for all BWIC with Mechanical Engineering Installations where not included above or elsewhere | 0 | Item | 76998 | 76998 | 76998 | 3 - Ext!A2780
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 3/R/2 Item A | A | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — Tie-in Connection — Tie-in connection to existing electrical line | 0 | item | 107365 | 107365 | 107365 | 3 - Ext!A2944
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 3/R/2 Item M | M | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUB - MAIN INSTALLATION — External Communication Services — Electrical point — External Communication Services — Allow for ICT installation (Data connection); including cables, conduits, terminations, fixings, supports, hangers, data outlets, accessories and all ancillary works as necessary | 0 | Item | 127075 | 127075 | 127075 | 3 - Ext!A2986
Candidate — not yet raised | Amount repeats the rate | Amount repeated in the Rate column with no quantity | The below items print the same figure in both the Rate and Amount columns with the quantity left at zero. Please confirm the quantity and the rate intended, or confirm the line is a lump sum. |  |  |  | 3/R/3 Item P | P | Bill 3 — SECTION R - ELECTRICAL INSTALLATIONS (3/R) — SUNDRIES — Allow for inspection, testing and commissioning including all off-site and factory testing; inspections to demonstrate compliance with relevant Specifications and standards; operating the completed installations; submitting all relevant test record sheets at the completion of the installations | 0 | Item | 59885.95 | 59885.95 | 59885.95 | 3 - Ext!A3028
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/Q/181 Item ADD | ADD | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Water Heater, WH-04 | 120 | Nr | 1760 | 211200 | 211200 | 2 - Main!A15348
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/Q/181 Item ADD | ADD | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Water Heater, EWH120 | 34 | Nr | 3266 | 111044 | 111044 | 2 - Main!A15349
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/Q/181 Item ADD | ADD | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Aluminium cladding for Chilled water pipe | 1 | Item | 1052379 | 1052379 | 1052379 | 2 - Main!A15350
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/Q/181 Item ADD | ADD | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Aluminium Cladding (GI + Fire rated) | 1 | Item | 4851207 | 4851207 | 4851207 | 2 - Main!A15351
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/Q/181 Item ADD | ADD | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Acoustic Lining | 1 | Item | 1542368 | 1542368 | 1542368 | 2 - Main!A15352
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/Q/181 Item ADD | ADD | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Pre insulated duct work as per TQ Response | 36475 | m2 | 181 | 6601975 | 6601975 | 2 - Main!A15353
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/Q/181 Item ADD | ADD | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Flow Meter 600mm | 1 | Nr | 100130 | 100130 | 100130 | 2 - Main!A15354
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/Q/181 Item ADD | ADD | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Flow Meter 200mm | 1 | Nr | 23482 | 23482 | 23482 | 2 - Main!A15355
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/Q/181 Item ADD | ADD | Bill 2 — SECTION Q - MECHANICAL ENGINEERING INSTALLATIONS (2/Q) — GENERALLY — Secondary side valve Assembly for Main Heat exchanger | 6 | Nr | 84704 | 508224 | 508224 | 2 - Main!A15356
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Energy metering & monitoring system | 1 | Item | 1645985 | 1645985 | 1645985 | 2 - Main!A23823
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Lift related Electrical Works | 1 | Item | 358958 | 358958 | 358958 | 2 - Main!A23824
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Garbage & Linen Chute - Electrical Related Works | 1 | Item | 254262 | 254262 | 254262 | 2 - Main!A23825
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — LPG System Related Electrical Works | 1 | Item | 600935 | 600935 | 600935 | 2 - Main!A23826
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Control Panels for mechanical Equipments | 1 | Item | 1148879 | 1148879 | 1148879 | 2 - Main!A23827
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-01-FAHU-T1 | 1 | Nr | 35416 | 35416 | 35416 | 2 - Main!A23830
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-01-FAHU-T3 | 1 | Nr | 39502 | 39502 | 39502 | 2 - Main!A23831
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T1-51-FAHU | 1 | Nr | 39502 | 39502 | 39502 | 2 - Main!A23832
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T3-55-FAHU | 1 | Nr | 49718 | 49718 | 49718 | 2 - Main!A23833
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T2-01-FAHU | 1 | Nr | 39502 | 39502 | 39502 | 2 - Main!A23834
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T2-29-FAHU | 1 | Nr | 38821 | 38821 | 38821 | 2 - Main!A23835
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T2-59-FAHU | 1 | Nr | 49718 | 49718 | 49718 | 2 - Main!A23836
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T4-01-FAHU | 1 | Nr | 36096 | 36096 | 36096 | 2 - Main!A23837
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T4-29-FAHU | 1 | Nr | 38821 | 38821 | 38821 | 2 - Main!A23838
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — CP-T4-55-FAHU | 1 | Nr | 46313 | 46313 | 46313 | 2 - Main!A23839
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 16mm² XLPE/SWA/PVC/CU +1C x 16mm² ECC | 94 | m | 68 | 6392 | 6392 | 2 - Main!A23841
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 2 x 4C x 150mm² XLPE/SWA/PVC/CU + 2 x 1C x 70mm² ECC | 114 | m | 959 | 109326 | 109326 | 2 - Main!A23842
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 2C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC | 30 | m | 30 | 900 | 900 | 2 - Main!A23844
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 6mm² XLPE/SWA/LSOH + 1C x 6mm² ECC | 614 | m | 30 | 18420 | 18420 | 2 - Main!A23845
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 10mm² XLPE/SWA/LSOH + 1C x 10mm² ECC | 528 | m | 49 | 25872 | 25872 | 2 - Main!A23846
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 16mm² XLPE/SWA/LSOH + 1C x 16mm² ECC | 225 | m | 71 | 15975 | 15975 | 2 - Main!A23847
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 25mm² XLPE/SWA/LSOH + 1C x 16mm² ECC | 542 | m | 97 | 52574 | 52574 | 2 - Main!A23848
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 35mm² XLPE/SWA/LSOH + 1C x 16mm² ECC | 60 | m | 131 | 7860 | 7860 | 2 - Main!A23849
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 70mm² XLPE/SWA/LSOH + 1C x 35mm² ECC | 30 | m | 228 | 6840 | 6840 | 2 - Main!A23850
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 6mm² XLPE/SWA/FR + 1C x6mm² ECC | 88 | m | 51 | 4488 | 4488 | 2 - Main!A23866
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 10mm² XLPE/SWA/FR + 1C x10mm² ECC | 175 | m | 68 | 11900 | 11900 | 2 - Main!A23867
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 16mm² XLPE/SWA/FR + 1C x 16mm² ECC | 80 | m | 93 | 7440 | 7440 | 2 - Main!A23868
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 35mm² XLPE/SWA/FR + 1C x 16mm² ECC | 36 | m | 169 | 6084 | 6084 | 2 - Main!A23869
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 4C x 50mm² XLPE/SWA/FR + 1C x 25mm² ECC | 296 | m | 208 | 61568 | 61568 | 2 - Main!A23870
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 800A MCCB tap-off | 1 | Nr | 10592 | 10592 | 10592 | 2 - Main!A23872
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Fixed outdoor wall: Monitoring | 5 | Nr | 3414 | 17070 | 17070 | 2 - Main!A23873
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 40A TPN isolator, fire rated | 1 | Nr | 747 | 747 | 747 | 2 - Main!A23874
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 63A TPN isolator, fire rated | 38 | Nr | 2241 | 85158 | 85158 | 2 - Main!A23875
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 80A TPN isolator, fire rated | 15 | Nr | 2604 | 39060 | 39060 | 2 - Main!A23876
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 100A TPN isolator, fire rated | 4 | Nr | 2976 | 11904 | 11904 | 2 - Main!A23877
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 125A TPN isolator, fire rated | 24 | Nr | 3253 | 78072 | 78072 | 2 - Main!A23878
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — To key management system | 1 | Item | 173604 | 173604 | 173604 | 2 - Main!A23880
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 150mm wide cable tray for Fire Alarm System | 18338 | m | 26 | 476788 | 476788 | 2 - Main!A23882
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 100mm x 50mm cable trunking for Emergency Lighting System | 18338 | m | 30 | 550140 | 550140 | 2 - Main!A23883
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 150mm wide cable tray for BMS System | 18338 | m | 26 | 476788 | 476788 | 2 - Main!A23884
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 150mm wide cable tray for Earthing System | 1153 | m | 26 | 29978 | 29978 | 2 - Main!A23885
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — 100mm x 50mm dual compartment GI trunking for Light/Power | 11130 | m | 60 | 667800 | 667800 | 2 - Main!A23886
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Outdoor speaker landscape with ground stack,ref T5 | 18 | Nr | 416 | 7488 | 7488 | 2 - Main!A23888
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Outdoor speaker landscape with ground stack,ref T5 | 18 | Nr | 3888 | 69984 | 69984 | 2 - Main!A23889
Candidate — not yet raised | Zone split does not add up | Rows whose zone split does not add to the row total | On the below rows the per-zone amounts do not add to the total the same row prints — and your workbook's own check column reports the same. Please correct the rows or confirm the figures intended. |  |  |  | 2/R/169 Item ADD | ADD | Bill 2 — SECTION R - ELECTRICAL INSTALLATIONS (2/R) — GENERALLY — Allow for coordination of Transformer installation & Termination | 1 | Item | 122331 | 122331 | 122331 | 2 - Main!A23891
Candidate — not yet raised | No item reference | Priced lines carrying no item reference | The below priced lines carry no printed item reference. Please add the reference, or confirm the line is not a measured item. |  |  |  | 2/L/2 Item |  | Bill 2 — SECTION L - EQUIPMENT (2/L) — GYM EQUIPMENT — Supply and installation by Others: Contractor to allow for Co-ordination, attendance and builders work | 1 | Item | 50850 | 50850 | 50850 | 2 - Main!A6515
Candidate — not yet raised | Duplicate item code | Duplicated item references | The below item references appear more than once within the same sequence. Please confirm the numbering. |  |  |  | 2/E/11 Item ADD | ADD | Bill 2 — SECTION E - METALWORK (2/E) — GENERALLY — Primary Structural Steel (Non Fire Rated) to inaccessible areas on façade (Dummy Balconies) and Canopies Provisional Qty | 552.04 | t | 19218 | 10609104.719999999 | 10609104.72 | 2 - Main!A1692
Candidate — not yet raised | Duplicate item code | Duplicated item references | The below item references appear more than once within the same sequence. Please confirm the numbering. |  |  |  | 2/E/11 Item A | A | Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; UB 533 x 210 x 82 | -5.69 | t | 21769 | -123865.61000000003 | -123865.61 | 2 - Main!A1715
Candidate — not yet raised | Duplicate item code | Duplicated item references | The below item references appear more than once within the same sequence. Please confirm the numbering. |  |  |  | 2/E/11 Item B | B | Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; UC 203 x 203 x 60 | 4.6 | t | 21769 | 100137.40000000001 | 100137.4 | 2 - Main!A1716
Candidate — not yet raised | Duplicate item code | Duplicated item references | The below item references appear more than once within the same sequence. Please confirm the numbering. |  |  |  | 2/E/11 Item C | C | Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; CHS 219 x 6.3 | -0.28 | t | 21769 | -6095.320000000005 | -6095.32 | 2 - Main!A1717
Candidate — not yet raised | Duplicate item code | Duplicated item references | The below item references appear more than once within the same sequence. Please confirm the numbering. |  |  |  | 2/E/11 Item D | D | Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; SHS 150 x 150 x 6.3 | -0.44 | t | 21769 | -9578.360000000004 | -9578.36 | 2 - Main!A1718
Candidate — not yet raised | Duplicate item code | Duplicated item references | The below item references appear more than once within the same sequence. Please confirm the numbering. |  |  |  | 2/E/11 Item E | E | Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Structural steel frame; with grade S275/355; conforming to BS 5950 and BS EN 10025; including teflon, stiffeners, fixings, supports, surface treatment, protective coatings, accessories and all ancillary works as necessary — Columns; SHS 120 x 120 x 6.3 | -0.03 | t | 21769 | -653.0699999999981 | -653.07 | 2 - Main!A1719
Candidate — not yet raised | Duplicate item code | Duplicated item references | The below item references appear more than once within the same sequence. Please confirm the numbering. |  |  |  | 2/E/11 Item D | D | Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Type AL-03; 3mm thick solid core aluminium cladding panels;PVDF coated; colour RAL 050 50 10 (Teakwood Brown - Light Brown, Matte finish, Smooth textured), including secondary support framing system and thermal insulation; water proofing where required; including all fixings, fittings, accessories and all ancillary works as per drawings and specifications — To ground floor and podium walls | -64 | m2 | 1133 | -72512 | -72512 | 2 - Main!A1777
Candidate — not yet raised | Duplicate item code | Duplicated item references | The below item references appear more than once within the same sequence. Please confirm the numbering. |  |  |  | 2/E/11 Item E | E | Bill 2 — SECTION E - METALWORK (2/E) — VARIANCE IN QUANTITY — Type AL-03; 3mm thick solid core aluminium cladding panels;PVDF coated; colour RAL 050 50 10 (Teakwood Brown - Light Brown, Matte finish, Smooth textured), including secondary support framing system and thermal insulation; water proofing where required; including all fixings, fittings, accessories and all ancillary works as per drawings and specifications — To tower walls | -543 | m2 | 1133 | -615219 | -615219 | 2 - Main!A1778